## Sheet1
Activity ID | Project | Cost Code | Vendor | Activity Name | Original Duration | Remaining Duration | Schedule % Complete | Start | Finish | Total Float | At Completion Labor Units | Spreadsheet Field | time axis 2010-11-01 to 2013-12-13
EC2430 | 1345006 |  |  | Substantial Completion - All TCO | 0 | 0 | 0% |  | 2013-12-13 | 0 | 0 | At Completion Labor Units
EC1080 | 1345006 |  |  | Permits Received - Start Site Work | 0 | 0 | 0% | 2010-11-02 |  | 0 | 0 | At Completion Labor Units
EC1010 | 1345006 |  |  | Building Pad Delivered by Owner | 0 | 0 | 0% | 2010-11-01 |  | 0 | 0 | At Completion Labor Units
EC2440 | 1345006 |  |  | Complete Building 1 | 0 | 0 | 0% |  | 2013-12-13 | 0 | 0 | At Completion Labor Units
EC1650 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor 4 | 10 | 10 | 0% | 2011-11-09 | 2011-11-23 | 0 | 77 | At Completion Labor Units | 2011-11-09: 3; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 8; 2011-11-23: 2
EC1580 | 1345006 | 3000 | ACMEGC | Stucco Bands | 10 | 10 | 0% | 2011-11-09 | 2011-11-22 | 0 | 77 | At Completion Labor Units | 2011-11-09: 6; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 6
EC1660 | 1345006 | 3000 | ACMEGC | Stucco Grey | 19 | 19 | 0% | 2011-11-22 | 2011-12-19 | 0 | 154 | At Completion Labor Units | 2011-11-22: 2; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 8; 2011-11-29: 8; 2011-11-30: 8; 2011-12-01: 8; 2011-12-02: 8; 2011-12-05: 8; 2011-12-06: 8; 2011-12-07: 8; 2011-12-08: 8; 2011-12-09: 8; 2011-12-12: 8; 2011-12-13: 8; 2011-12-14: 8; 2011-12-15: 8; 2011-12-16: 8; 2011-12-19: 8; 2011-12-20: 8
EC1690 | 1345006 | 3000 | ACMEGC | Stucco Finish Coat | 24 | 24 | 0% | 2011-12-20 | 2012-01-20 | 0 | 192 | At Completion Labor Units | 2011-12-20: 8; 2011-12-21: 8; 2011-12-22: 8; 2011-12-23: 8; 2011-12-27: 8; 2011-12-28: 8; 2011-12-29: 8; 2011-12-30: 8; 2012-01-03: 8; 2012-01-04: 8; 2012-01-05: 8; 2012-01-06: 8; 2012-01-09: 8; 2012-01-10: 8; 2012-01-11: 8; 2012-01-12: 8; 2012-01-13: 8; 2012-01-16: 8; 2012-01-17: 8; 2012-01-18: 8; 2012-01-19: 8; 2012-01-20: 8; 2012-01-23: 8; 2012-01-24: 8
EC1840 | 1345006 | 3000 | ACMEGC | Caulk | 10 | 10 | 0% | 2012-01-23 | 2012-02-03 | 0 | 77 | At Completion Labor Units | 2012-01-23: 8; 2012-01-24: 8; 2012-01-25: 8; 2012-01-26: 8; 2012-01-27: 8; 2012-01-30: 8; 2012-01-31: 8; 2012-02-01: 8; 2012-02-02: 8; 2012-02-03: 5
EC1900 | 1345006 | 3000 | ACMEGC | Stucco Band Trim | 12 | 12 | 0% | 2012-02-03 | 2012-02-21 | 0 | 96 | At Completion Labor Units | 2012-02-03: 3; 2012-02-06: 8; 2012-02-07: 8; 2012-02-08: 8; 2012-02-09: 8; 2012-02-10: 8; 2012-02-13: 8; 2012-02-14: 8; 2012-02-15: 8; 2012-02-16: 8; 2012-02-17: 8; 2012-02-20: 8; 2012-02-21: 5
EC1980 | 1345006 | 3000 | ACMEGC | Paint Exterior | 12 | 12 | 0% | 2012-02-28 | 2012-03-15 | 0 | 96 | At Completion Labor Units | 2012-02-28: 3; 2012-02-29: 8; 2012-03-01: 8; 2012-03-02: 8; 2012-03-05: 8; 2012-03-06: 8; 2012-03-07: 8; 2012-03-08: 8; 2012-03-09: 8; 2012-03-12: 8; 2012-03-13: 8; 2012-03-14: 8; 2012-03-15: 5
EC2110 | 1345006 | 3000 | ACMEGC | Demobilize Scaffolding | 12 | 12 | 0% | 2012-03-15 | 2012-04-02 | 0 | 96 | At Completion Labor Units | 2012-03-15: 3; 2012-03-16: 8; 2012-03-19: 8; 2012-03-20: 8; 2012-03-21: 8; 2012-03-22: 8; 2012-03-23: 8; 2012-03-26: 8; 2012-03-27: 8; 2012-03-28: 8; 2012-03-29: 8; 2012-03-30: 8; 2012-04-02: 5
EC1360 | 1345006 | 3000 | ACMEGC | Mobilize Scaffolding | 12 | 12 | 0% | 2011-08-03 | 2011-08-19 | 31 | 96 | At Completion Labor Units | 2011-08-03: 2; 2011-08-04: 8; 2011-08-05: 8; 2011-08-08: 8; 2011-08-09: 8; 2011-08-10: 8; 2011-08-11: 8; 2011-08-12: 8; 2011-08-15: 8; 2011-08-16: 8; 2011-08-17: 8; 2011-08-18: 8; 2011-08-19: 6
EC2140 | 1345006 | 3000 |  | Shell Complete | 0 | 0 | 0% |  | 2012-04-18 | 144 | 0 | At Completion Labor Units
EC1990 | 1345006 | 3000 | ACMEGC | Install Railings | 36 | 36 | 0% | 2012-02-28 | 2012-04-18 | 144 | 288 | At Completion Labor Units | 2012-02-28: 3; 2012-02-29: 8; 2012-03-01: 8; 2012-03-02: 8; 2012-03-05: 8; 2012-03-06: 8; 2012-03-07: 8; 2012-03-08: 8; 2012-03-09: 8; 2012-03-12: 8; 2012-03-13: 8; 2012-03-14: 8; 2012-03-15: 8; 2012-03-16: 8; 2012-03-19: 8; 2012-03-20: 8; 2012-03-21: 8; 2012-03-22: 8; 2012-03-23: 8; 2012-03-26: 8; 2012-03-27: 8; 2012-03-28: 8; 2012-03-29: 8; 2012-03-30: 8; 2012-04-02: 8; 2012-04-03: 8; 2012-04-04: 8; 2012-04-05: 8; 2012-04-06: 8; 2012-04-09: 8; 2012-04-10: 8; 2012-04-11: 8; 2012-04-12: 8; 2012-04-13: 8; 2012-04-16: 8; 2012-04-17: 8; 2012-04-18: 5
EC1410 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 1 | 19 | 19 | 0% | 2011-08-19 | 2011-09-15 | 0 | 154 | At Completion Labor Units | 2011-08-19: 2; 2011-08-22: 8; 2011-08-23: 8; 2011-08-24: 8; 2011-08-25: 8; 2011-08-26: 8; 2011-08-29: 8; 2011-08-30: 8; 2011-08-31: 8; 2011-09-01: 8; 2011-09-02: 8; 2011-09-06: 8; 2011-09-07: 8; 2011-09-08: 8; 2011-09-09: 8; 2011-09-12: 8; 2011-09-13: 8; 2011-09-14: 8; 2011-09-15: 8; 2011-09-16: 8
EC1470 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 2 | 19 | 19 | 0% | 2011-09-09 | 2011-10-06 | 0 | 154 | At Completion Labor Units | 2011-09-09: 8; 2011-09-12: 8; 2011-09-13: 8; 2011-09-14: 8; 2011-09-15: 8; 2011-09-16: 8; 2011-09-19: 8; 2011-09-20: 8; 2011-09-21: 8; 2011-09-22: 8; 2011-09-23: 8; 2011-09-26: 8; 2011-09-27: 8; 2011-09-28: 8; 2011-09-29: 8; 2011-09-30: 8; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 2
EC1500 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 3 | 17 | 17 | 0% | 2011-09-29 | 2011-10-21 | 0 | 134 | At Completion Labor Units | 2011-09-29: 6; 2011-09-30: 8; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8
EC1520 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 4 | 22 | 22 | 0% | 2011-10-17 | 2011-11-15 | 0 | 173 | At Completion Labor Units | 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 8; 2011-10-28: 8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 5
EC1490 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor1 | 10 | 10 | 0% | 2011-09-12 | 2011-09-23 | 16 | 77 | At Completion Labor Units | 2011-09-12: 8; 2011-09-13: 8; 2011-09-14: 8; 2011-09-15: 8; 2011-09-16: 8; 2011-09-19: 8; 2011-09-20: 8; 2011-09-21: 8; 2011-09-22: 8; 2011-09-23: 5
EC1510 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor 2 | 10 | 10 | 0% | 2011-09-30 | 2011-10-13 | 12 | 77 | At Completion Labor Units | 2011-09-30: 6; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 6
EC1570 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor 3 | 7 | 7 | 0% | 2011-10-18 | 2011-10-27 | 9 | 58 | At Completion Labor Units | 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 2
EC2370 | 1345006 | 4000 | ACMEGC | Final Inspections and Punchlist | 34 | 34 | 0% | 2012-10-30 | 2012-12-17 | 259 | 528 | At Completion Labor Units | 2012-10-30: 7; 2012-10-31: 17; 2012-11-01: 17; 2012-11-02: 17; 2012-11-05: 17; 2012-11-06: 17; 2012-11-07: 17; 2012-11-08: 17; 2012-11-09: 17; 2012-11-12: 17; 2012-11-13: 17; 2012-11-14: 17; 2012-11-15: 15; 2012-11-16: 15; 2012-11-19: 15; 2012-11-20: 15; 2012-11-21: 15; 2012-11-23: 15; 2012-11-26: 15; 2012-11-27: 15; 2012-11-28: 15; 2012-11-29: 15; 2012-11-30: 15; 2012-12-03: 15; 2012-12-04: 15; 2012-12-05: 15; 2012-12-06: 15; 2012-12-07: 15; 2012-12-10: 15; 2012-12-11: 15; 2012-12-12: 15; 2012-12-13: 15; 2012-12-14: 15; 2012-12-17: 15; 2012-12-18: 3
EC1820 | 1345006 | 4000 | ACMEGC | Building 2 Elevators Complete | 70 | 70 | 0% | 2011-11-25 | 2012-03-01 | 375 | 768 | At Completion Labor Units | 2011-11-25: 7; 2011-11-28: 11; 2011-11-29: 11; 2011-11-30: 11; 2011-12-01: 11; 2011-12-02: 11; 2011-12-05: 11; 2011-12-06: 11; 2011-12-07: 11; 2011-12-08: 11; 2011-12-09: 11; 2011-12-12: 11; 2011-12-13: 11; 2011-12-14: 11; 2011-12-15: 11; 2011-12-16: 11; 2011-12-19: 11; 2011-12-20: 11; 2011-12-21: 11; 2011-12-22: 11; 2011-12-23: 11; 2011-12-27: 11; 2011-12-28: 11; 2011-12-29: 11; 2011-12-30: 11; 2012-01-03: 11; 2012-01-04: 11; 2012-01-05: 11; 2012-01-06: 11; 2012-01-09: 11; 2012-01-10: 11; 2012-01-11: 11; 2012-01-12: 11; 2012-01-13: 11; 2012-01-16: 11; 2012-01-17: 11; 2012-01-18: 11; 2012-01-19: 11; 2012-01-20: 11; 2012-01-23: 11; 2012-01-24: 11; 2012-01-25: 11; 2012-01-26: 11; 2012-01-27: 11; 2012-01-30: 11; 2012-01-31: 11; 2012-02-01: 11; 2012-02-02: 11; 2012-02-03: 11; 2012-02-06: 11; 2012-02-07: 11; 2012-02-08: 11; 2012-02-09: 11; 2012-02-10: 11; 2012-02-13: 11; 2012-02-14: 11; 2012-02-15: 11; 2012-02-16: 11; 2012-02-17: 11; 2012-02-20: 11; 2012-02-21: 11; 2012-02-22: 11; 2012-02-23: 11; 2012-02-24: 11; 2012-02-27: 11; 2012-02-28: 11; 2012-02-29: 11; 2012-03-01: 11; 2012-03-02: 11; 2012-03-05: 11
EC2240 | 1345006 | 4000 | ACMEGC | Tenant Finishes for Clubhouse Areas | 127 | 127 | 0% | 2012-06-21 | 2012-12-17 | 259 | 1760 | At Completion Labor Units | 2012-06-21: 15; 2012-06-22: 15; 2012-06-25: 15; 2012-06-26: 15; 2012-06-27: 15; 2012-06-28: 15; 2012-06-29: 15; 2012-07-02: 15; 2012-07-03: 15; 2012-07-05: 15; 2012-07-06: 15; 2012-07-09: 15; 2012-07-10: 15; 2012-07-11: 15; 2012-07-12: 15; 2012-07-13: 15; 2012-07-16: 15; 2012-07-17: 15; 2012-07-18: 15; 2012-07-19: 15; 2012-07-20: 15; 2012-07-23: 15; 2012-07-24: 15; 2012-07-25: 15; 2012-07-26: 15; 2012-07-27: 15; 2012-07-30: 15; 2012-07-31: 15; 2012-08-01: 15; 2012-08-02: 15; 2012-08-03: 15; 2012-08-06: 15; 2012-08-07: 15; 2012-08-08: 15; 2012-08-09: 15; 2012-08-10: 15; 2012-08-13: 15; 2012-08-14: 15; 2012-08-15: 15; 2012-08-16: 15; 2012-08-17: 15; 2012-08-20: 15; 2012-08-21: 14; 2012-08-22: 13; 2012-08-23: 13; 2012-08-24: 13; 2012-08-27: 13; 2012-08-28: 13; 2012-08-29: 13; 2012-08-30: 13; 2012-08-31: 13; 2012-09-04: 13; 2012-09-05: 13; 2012-09-06: 13; 2012-09-07: 13; 2012-09-10: 13; 2012-09-11: 13; 2012-09-12: 13; 2012-09-13: 13; 2012-09-14: 13; 2012-09-17: 13; 2012-09-18: 13; 2012-09-19: 13; 2012-09-20: 13; 2012-09-21: 13; 2012-09-24: 13; 2012-09-25: 13; 2012-09-26: 13; 2012-09-27: 13; 2012-09-28: 13; 2012-10-01: 13; 2012-10-02: 13; 2012-10-03: 13; 2012-10-04: 13; 2012-10-05: 13; 2012-10-08: 13; 2012-10-09: 13; 2012-10-10: 13; 2012-10-11: 13; 2012-10-12: 13; 2012-10-15: 13; 2012-10-16: 13; 2012-10-17: 13; 2012-10-18: 13; 2012-10-19: 13; 2012-10-22: 13; 2012-10-23: 13; 2012-10-24: 13; 2012-10-25: 13; 2012-10-26: 13; 2012-10-29: 13; 2012-10-30: 13; 2012-10-31: 13; 2012-11-01: 13; 2012-11-02: 13; 2012-11-05: 13; 2012-11-06: 13; 2012-11-07: 13; 2012-11-08: 13; 2012-11-09: 13; 2012-11-12: 13; 2012-11-13: 13; 2012-11-14: 13; 2012-11-15: 13; 2012-11-16: 13; 2012-11-19: 13; 2012-11-20: 13; 2012-11-21: 13; 2012-11-23: 13; 2012-11-26: 13; 2012-11-27: 13; 2012-11-28: 13; 2012-11-29: 13; 2012-11-30: 13; 2012-12-03: 13; 2012-12-04: 13; 2012-12-05: 13; 2012-12-06: 13; 2012-12-07: 13; 2012-12-10: 13; 2012-12-11: 13; 2012-12-12: 13; 2012-12-13: 13; 2012-12-14: 13; 2012-12-17: 13; 2012-12-18: 13; 2012-12-19: 13; 2012-12-20: 3
EC1550 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 1 | 197 | 197 | 0% | 2011-09-22 | 2012-06-25 | 259 | 902 | At Completion Labor Units | 2011-09-22: 1; 2011-09-23: 5; 2011-09-26: 5; 2011-09-27: 5; 2011-09-28: 5; 2011-09-29: 5; 2011-09-30: 5; 2011-10-03: 5; 2011-10-04: 5; 2011-10-05: 5; 2011-10-06: 5; 2011-10-07: 5; 2011-10-10: 5; 2011-10-11: 5; 2011-10-12: 5; 2011-10-13: 5; 2011-10-14: 5; 2011-10-17: 5; 2011-10-18: 5; 2011-10-19: 5; 2011-10-20: 5; 2011-10-21: 5; 2011-10-24: 5; 2011-10-25: 5; 2011-10-26: 5; 2011-10-27: 5; 2011-10-28: 5; 2011-10-31: 5; 2011-11-01: 5; 2011-11-02: 5; 2011-11-03: 5; 2011-11-04: 5; 2011-11-07: 5; 2011-11-08: 5; 2011-11-09: 5; 2011-11-10: 5; 2011-11-11: 5; 2011-11-14: 5; 2011-11-15: 5; 2011-11-16: 5; 2011-11-17: 5; 2011-11-18: 5; 2011-11-21: 5; 2011-11-22: 5; 2011-11-23: 5; 2011-11-25: 5; 2011-11-28: 5; 2011-11-29: 5; 2011-11-30: 5; 2011-12-01: 5; 2011-12-02: 5; 2011-12-05: 5; 2011-12-06: 5; 2011-12-07: 5; 2011-12-08: 5; 2011-12-09: 5; 2011-12-12: 5; 2011-12-13: 5; 2011-12-14: 5; 2011-12-15: 5; 2011-12-16: 5; 2011-12-19: 5; 2011-12-20: 5; 2011-12-21: 5; 2011-12-22: 5; 2011-12-23: 5; 2011-12-27: 5; 2011-12-28: 4; 2011-12-29: 4; 2011-12-30: 4; 2012-01-03: 4; 2012-01-04: 4; 2012-01-05: 4; 2012-01-06: 4; 2012-01-09: 4; 2012-01-10: 4; 2012-01-11: 4; 2012-01-12: 4; 2012-01-13: 4; 2012-01-16: 4; 2012-01-17: 4; 2012-01-18: 4; 2012-01-19: 4; 2012-01-20: 4; 2012-01-23: 4; 2012-01-24: 4; 2012-01-25: 4; 2012-01-26: 4; 2012-01-27: 4; 2012-01-30: 4; 2012-01-31: 4; 2012-02-01: 4; 2012-02-02: 4; 2012-02-03: 4; 2012-02-06: 4; 2012-02-07: 4; 2012-02-08: 4; 2012-02-09: 4; 2012-02-10: 4; 2012-02-13: 4; 2012-02-14: 4; 2012-02-15: 4; 2012-02-16: 4; 2012-02-17: 4; 2012-02-20: 4; 2012-02-21: 4; 2012-02-22: 4; 2012-02-23: 4; 2012-02-24: 4; 2012-02-27: 4; 2012-02-28: 4; 2012-02-29: 4; 2012-03-01: 4; 2012-03-02: 4; 2012-03-05: 4; 2012-03-06: 4; 2012-03-07: 4; 2012-03-08: 4; 2012-03-09: 4; 2012-03-12: 4; 2012-03-13: 4; 2012-03-14: 4; 2012-03-15: 4; 2012-03-16: 4; 2012-03-19: 4; 2012-03-20: 4; 2012-03-21: 4; 2012-03-22: 4; 2012-03-23: 4; 2012-03-26: 4; 2012-03-27: 4; 2012-03-28: 4; 2012-03-29: 4; 2012-03-30: 4; 2012-04-02: 4; 2012-04-03: 4; 2012-04-04: 4; 2012-04-05: 4; 2012-04-06: 4; 2012-04-09: 4; 2012-04-10: 4; 2012-04-11: 4; 2012-04-12: 4; 2012-04-13: 4; 2012-04-16: 4; 2012-04-17: 4; 2012-04-18: 4; 2012-04-19: 4; 2012-04-20: 4; 2012-04-23: 4; 2012-04-24: 4; 2012-04-25: 4; 2012-04-26: 4; 2012-04-27: 4; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 3
EC1630 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 1 | 199 | 199 | 0% | 2011-09-29 | 2012-07-04 | 259 | 902 | At Completion Labor Units | 2011-09-29: 1; 2011-09-30: 5; 2011-10-03: 5; 2011-10-04: 5; 2011-10-05: 5; 2011-10-06: 5; 2011-10-07: 5; 2011-10-10: 5; 2011-10-11: 5; 2011-10-12: 5; 2011-10-13: 5; 2011-10-14: 5; 2011-10-17: 5; 2011-10-18: 5; 2011-10-19: 5; 2011-10-20: 5; 2011-10-21: 5; 2011-10-24: 5; 2011-10-25: 5; 2011-10-26: 5; 2011-10-27: 5; 2011-10-28: 5; 2011-10-31: 5; 2011-11-01: 5; 2011-11-02: 5; 2011-11-03: 5; 2011-11-04: 5; 2011-11-07: 5; 2011-11-08: 5; 2011-11-09: 5; 2011-11-10: 5; 2011-11-11: 5; 2011-11-14: 5; 2011-11-15: 5; 2011-11-16: 5; 2011-11-17: 5; 2011-11-18: 5; 2011-11-21: 5; 2011-11-22: 5; 2011-11-23: 5; 2011-11-25: 5; 2011-11-28: 5; 2011-11-29: 5; 2011-11-30: 5; 2011-12-01: 5; 2011-12-02: 5; 2011-12-05: 5; 2011-12-06: 5; 2011-12-07: 5; 2011-12-08: 5; 2011-12-09: 5; 2011-12-12: 5; 2011-12-13: 5; 2011-12-14: 5; 2011-12-15: 5; 2011-12-16: 5; 2011-12-19: 5; 2011-12-20: 5; 2011-12-21: 5; 2011-12-22: 5; 2011-12-23: 5; 2011-12-27: 5; 2011-12-28: 5; 2011-12-29: 5; 2011-12-30: 5; 2012-01-03: 5; 2012-01-04: 5; 2012-01-05: 4; 2012-01-06: 4; 2012-01-09: 4; 2012-01-10: 4; 2012-01-11: 4; 2012-01-12: 4; 2012-01-13: 4; 2012-01-16: 4; 2012-01-17: 4; 2012-01-18: 4; 2012-01-19: 4; 2012-01-20: 4; 2012-01-23: 4; 2012-01-24: 4; 2012-01-25: 4; 2012-01-26: 4; 2012-01-27: 4; 2012-01-30: 4; 2012-01-31: 4; 2012-02-01: 4; 2012-02-02: 4; 2012-02-03: 4; 2012-02-06: 4; 2012-02-07: 4; 2012-02-08: 4; 2012-02-09: 4; 2012-02-10: 4; 2012-02-13: 4; 2012-02-14: 4; 2012-02-15: 4; 2012-02-16: 4; 2012-02-17: 4; 2012-02-20: 4; 2012-02-21: 4; 2012-02-22: 4; 2012-02-23: 4; 2012-02-24: 4; 2012-02-27: 4; 2012-02-28: 4; 2012-02-29: 4; 2012-03-01: 4; 2012-03-02: 4; 2012-03-05: 4; 2012-03-06: 4; 2012-03-07: 4; 2012-03-08: 4; 2012-03-09: 4; 2012-03-12: 4; 2012-03-13: 4; 2012-03-14: 4; 2012-03-15: 4; 2012-03-16: 4; 2012-03-19: 4; 2012-03-20: 4; 2012-03-21: 4; 2012-03-22: 4; 2012-03-23: 4; 2012-03-26: 4; 2012-03-27: 4; 2012-03-28: 4; 2012-03-29: 4; 2012-03-30: 4; 2012-04-02: 4; 2012-04-03: 4; 2012-04-04: 4; 2012-04-05: 4; 2012-04-06: 4; 2012-04-09: 4; 2012-04-10: 4; 2012-04-11: 4; 2012-04-12: 4; 2012-04-13: 4; 2012-04-16: 4; 2012-04-17: 4; 2012-04-18: 4; 2012-04-19: 4; 2012-04-20: 4; 2012-04-23: 4; 2012-04-24: 4; 2012-04-25: 4; 2012-04-26: 4; 2012-04-27: 4; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4
EC1670 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 2 | 199 | 199 | 0% | 2011-10-06 | 2012-07-11 | 311 | 902 | At Completion Labor Units | 2011-10-06: 1; 2011-10-07: 5; 2011-10-10: 5; 2011-10-11: 5; 2011-10-12: 5; 2011-10-13: 5; 2011-10-14: 5; 2011-10-17: 5; 2011-10-18: 5; 2011-10-19: 5; 2011-10-20: 5; 2011-10-21: 5; 2011-10-24: 5; 2011-10-25: 5; 2011-10-26: 5; 2011-10-27: 5; 2011-10-28: 5; 2011-10-31: 5; 2011-11-01: 5; 2011-11-02: 5; 2011-11-03: 5; 2011-11-04: 5; 2011-11-07: 5; 2011-11-08: 5; 2011-11-09: 5; 2011-11-10: 5; 2011-11-11: 5; 2011-11-14: 5; 2011-11-15: 5; 2011-11-16: 5; 2011-11-17: 5; 2011-11-18: 5; 2011-11-21: 5; 2011-11-22: 5; 2011-11-23: 5; 2011-11-25: 5; 2011-11-28: 5; 2011-11-29: 5; 2011-11-30: 5; 2011-12-01: 5; 2011-12-02: 5; 2011-12-05: 5; 2011-12-06: 5; 2011-12-07: 5; 2011-12-08: 5; 2011-12-09: 5; 2011-12-12: 5; 2011-12-13: 5; 2011-12-14: 5; 2011-12-15: 5; 2011-12-16: 5; 2011-12-19: 5; 2011-12-20: 5; 2011-12-21: 5; 2011-12-22: 5; 2011-12-23: 5; 2011-12-27: 5; 2011-12-28: 5; 2011-12-29: 5; 2011-12-30: 5; 2012-01-03: 5; 2012-01-04: 5; 2012-01-05: 5; 2012-01-06: 5; 2012-01-09: 5; 2012-01-10: 5; 2012-01-11: 5; 2012-01-12: 4; 2012-01-13: 4; 2012-01-16: 4; 2012-01-17: 4; 2012-01-18: 4; 2012-01-19: 4; 2012-01-20: 4; 2012-01-23: 4; 2012-01-24: 4; 2012-01-25: 4; 2012-01-26: 4; 2012-01-27: 4; 2012-01-30: 4; 2012-01-31: 4; 2012-02-01: 4; 2012-02-02: 4; 2012-02-03: 4; 2012-02-06: 4; 2012-02-07: 4; 2012-02-08: 4; 2012-02-09: 4; 2012-02-10: 4; 2012-02-13: 4; 2012-02-14: 4; 2012-02-15: 4; 2012-02-16: 4; 2012-02-17: 4; 2012-02-20: 4; 2012-02-21: 4; 2012-02-22: 4; 2012-02-23: 4; 2012-02-24: 4; 2012-02-27: 4; 2012-02-28: 4; 2012-02-29: 4; 2012-03-01: 4; 2012-03-02: 4; 2012-03-05: 4; 2012-03-06: 4; 2012-03-07: 4; 2012-03-08: 4; 2012-03-09: 4; 2012-03-12: 4; 2012-03-13: 4; 2012-03-14: 4; 2012-03-15: 4; 2012-03-16: 4; 2012-03-19: 4; 2012-03-20: 4; 2012-03-21: 4; 2012-03-22: 4; 2012-03-23: 4; 2012-03-26: 4; 2012-03-27: 4; 2012-03-28: 4; 2012-03-29: 4; 2012-03-30: 4; 2012-04-02: 4; 2012-04-03: 4; 2012-04-04: 4; 2012-04-05: 4; 2012-04-06: 4; 2012-04-09: 4; 2012-04-10: 4; 2012-04-11: 4; 2012-04-12: 4; 2012-04-13: 4; 2012-04-16: 4; 2012-04-17: 4; 2012-04-18: 4; 2012-04-19: 4; 2012-04-20: 4; 2012-04-23: 4; 2012-04-24: 4; 2012-04-25: 4; 2012-04-26: 4; 2012-04-27: 4; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4; 2012-07-12: 4; 2012-07-13: 4; 2012-07-16: 4; 2012-07-17: 4; 2012-07-18: 4
EC1700 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 2 | 199 | 199 | 0% | 2011-10-13 | 2012-07-18 | 311 | 902 | At Completion Labor Units | 2011-10-13: 1; 2011-10-14: 5; 2011-10-17: 5; 2011-10-18: 5; 2011-10-19: 5; 2011-10-20: 5; 2011-10-21: 5; 2011-10-24: 5; 2011-10-25: 5; 2011-10-26: 5; 2011-10-27: 5; 2011-10-28: 5; 2011-10-31: 5; 2011-11-01: 5; 2011-11-02: 5; 2011-11-03: 5; 2011-11-04: 5; 2011-11-07: 5; 2011-11-08: 5; 2011-11-09: 5; 2011-11-10: 5; 2011-11-11: 5; 2011-11-14: 5; 2011-11-15: 5; 2011-11-16: 5; 2011-11-17: 5; 2011-11-18: 5; 2011-11-21: 5; 2011-11-22: 5; 2011-11-23: 5; 2011-11-25: 5; 2011-11-28: 5; 2011-11-29: 5; 2011-11-30: 5; 2011-12-01: 5; 2011-12-02: 5; 2011-12-05: 5; 2011-12-06: 5; 2011-12-07: 5; 2011-12-08: 5; 2011-12-09: 5; 2011-12-12: 5; 2011-12-13: 5; 2011-12-14: 5; 2011-12-15: 5; 2011-12-16: 5; 2011-12-19: 5; 2011-12-20: 5; 2011-12-21: 5; 2011-12-22: 5; 2011-12-23: 5; 2011-12-27: 5; 2011-12-28: 5; 2011-12-29: 5; 2011-12-30: 5; 2012-01-03: 5; 2012-01-04: 5; 2012-01-05: 5; 2012-01-06: 5; 2012-01-09: 5; 2012-01-10: 5; 2012-01-11: 5; 2012-01-12: 5; 2012-01-13: 5; 2012-01-16: 5; 2012-01-17: 5; 2012-01-18: 5; 2012-01-19: 4; 2012-01-20: 4; 2012-01-23: 4; 2012-01-24: 4; 2012-01-25: 4; 2012-01-26: 4; 2012-01-27: 4; 2012-01-30: 4; 2012-01-31: 4; 2012-02-01: 4; 2012-02-02: 4; 2012-02-03: 4; 2012-02-06: 4; 2012-02-07: 4; 2012-02-08: 4; 2012-02-09: 4; 2012-02-10: 4; 2012-02-13: 4; 2012-02-14: 4; 2012-02-15: 4; 2012-02-16: 4; 2012-02-17: 4; 2012-02-20: 4; 2012-02-21: 4; 2012-02-22: 4; 2012-02-23: 4; 2012-02-24: 4; 2012-02-27: 4; 2012-02-28: 4; 2012-02-29: 4; 2012-03-01: 4; 2012-03-02: 4; 2012-03-05: 4; 2012-03-06: 4; 2012-03-07: 4; 2012-03-08: 4; 2012-03-09: 4; 2012-03-12: 4; 2012-03-13: 4; 2012-03-14: 4; 2012-03-15: 4; 2012-03-16: 4; 2012-03-19: 4; 2012-03-20: 4; 2012-03-21: 4; 2012-03-22: 4; 2012-03-23: 4; 2012-03-26: 4; 2012-03-27: 4; 2012-03-28: 4; 2012-03-29: 4; 2012-03-30: 4; 2012-04-02: 4; 2012-04-03: 4; 2012-04-04: 4; 2012-04-05: 4; 2012-04-06: 4; 2012-04-09: 4; 2012-04-10: 4; 2012-04-11: 4; 2012-04-12: 4; 2012-04-13: 4; 2012-04-16: 4; 2012-04-17: 4; 2012-04-18: 4; 2012-04-19: 4; 2012-04-20: 4; 2012-04-23: 4; 2012-04-24: 4; 2012-04-25: 4; 2012-04-26: 4; 2012-04-27: 4; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4; 2012-07-12: 4; 2012-07-13: 4; 2012-07-16: 4; 2012-07-17: 4; 2012-07-18: 4; 2012-07-19: 4; 2012-07-20: 4; 2012-07-23: 4; 2012-07-24: 4; 2012-07-25: 4
EC1790 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 3 | 199 | 199 | 0% | 2011-10-20 | 2012-07-25 | 311 | 902 | At Completion Labor Units | 2011-10-20: 1; 2011-10-21: 5; 2011-10-24: 5; 2011-10-25: 5; 2011-10-26: 5; 2011-10-27: 5; 2011-10-28: 5; 2011-10-31: 5; 2011-11-01: 5; 2011-11-02: 5; 2011-11-03: 5; 2011-11-04: 5; 2011-11-07: 5; 2011-11-08: 5; 2011-11-09: 5; 2011-11-10: 5; 2011-11-11: 5; 2011-11-14: 5; 2011-11-15: 5; 2011-11-16: 5; 2011-11-17: 5; 2011-11-18: 5; 2011-11-21: 5; 2011-11-22: 5; 2011-11-23: 5; 2011-11-25: 5; 2011-11-28: 5; 2011-11-29: 5; 2011-11-30: 5; 2011-12-01: 5; 2011-12-02: 5; 2011-12-05: 5; 2011-12-06: 5; 2011-12-07: 5; 2011-12-08: 5; 2011-12-09: 5; 2011-12-12: 5; 2011-12-13: 5; 2011-12-14: 5; 2011-12-15: 5; 2011-12-16: 5; 2011-12-19: 5; 2011-12-20: 5; 2011-12-21: 5; 2011-12-22: 5; 2011-12-23: 5; 2011-12-27: 5; 2011-12-28: 5; 2011-12-29: 5; 2011-12-30: 5; 2012-01-03: 5; 2012-01-04: 5; 2012-01-05: 5; 2012-01-06: 5; 2012-01-09: 5; 2012-01-10: 5; 2012-01-11: 5; 2012-01-12: 5; 2012-01-13: 5; 2012-01-16: 5; 2012-01-17: 5; 2012-01-18: 5; 2012-01-19: 5; 2012-01-20: 5; 2012-01-23: 5; 2012-01-24: 5; 2012-01-25: 5; 2012-01-26: 4; 2012-01-27: 4; 2012-01-30: 4; 2012-01-31: 4; 2012-02-01: 4; 2012-02-02: 4; 2012-02-03: 4; 2012-02-06: 4; 2012-02-07: 4; 2012-02-08: 4; 2012-02-09: 4; 2012-02-10: 4; 2012-02-13: 4; 2012-02-14: 4; 2012-02-15: 4; 2012-02-16: 4; 2012-02-17: 4; 2012-02-20: 4; 2012-02-21: 4; 2012-02-22: 4; 2012-02-23: 4; 2012-02-24: 4; 2012-02-27: 4; 2012-02-28: 4; 2012-02-29: 4; 2012-03-01: 4; 2012-03-02: 4; 2012-03-05: 4; 2012-03-06: 4; 2012-03-07: 4; 2012-03-08: 4; 2012-03-09: 4; 2012-03-12: 4; 2012-03-13: 4; 2012-03-14: 4; 2012-03-15: 4; 2012-03-16: 4; 2012-03-19: 4; 2012-03-20: 4; 2012-03-21: 4; 2012-03-22: 4; 2012-03-23: 4; 2012-03-26: 4; 2012-03-27: 4; 2012-03-28: 4; 2012-03-29: 4; 2012-03-30: 4; 2012-04-02: 4; 2012-04-03: 4; 2012-04-04: 4; 2012-04-05: 4; 2012-04-06: 4; 2012-04-09: 4; 2012-04-10: 4; 2012-04-11: 4; 2012-04-12: 4; 2012-04-13: 4; 2012-04-16: 4; 2012-04-17: 4; 2012-04-18: 4; 2012-04-19: 4; 2012-04-20: 4; 2012-04-23: 4; 2012-04-24: 4; 2012-04-25: 4; 2012-04-26: 4; 2012-04-27: 4; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4; 2012-07-12: 4; 2012-07-13: 4; 2012-07-16: 4; 2012-07-17: 4; 2012-07-18: 4; 2012-07-19: 4; 2012-07-20: 4; 2012-07-23: 4; 2012-07-24: 4; 2012-07-25: 4; 2012-07-26: 4; 2012-07-27: 4; 2012-07-30: 4; 2012-07-31: 4; 2012-08-01: 4
EC1850 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 3 | 199 | 199 | 0% | 2011-10-27 | 2012-08-01 | 311 | 902 | At Completion Labor Units | 2011-10-27: 1; 2011-10-28: 5; 2011-10-31: 5; 2011-11-01: 5; 2011-11-02: 5; 2011-11-03: 5; 2011-11-04: 5; 2011-11-07: 5; 2011-11-08: 5; 2011-11-09: 5; 2011-11-10: 5; 2011-11-11: 5; 2011-11-14: 5; 2011-11-15: 5; 2011-11-16: 5; 2011-11-17: 5; 2011-11-18: 5; 2011-11-21: 5; 2011-11-22: 5; 2011-11-23: 5; 2011-11-25: 5; 2011-11-28: 5; 2011-11-29: 5; 2011-11-30: 5; 2011-12-01: 5; 2011-12-02: 5; 2011-12-05: 5; 2011-12-06: 5; 2011-12-07: 5; 2011-12-08: 5; 2011-12-09: 5; 2011-12-12: 5; 2011-12-13: 5; 2011-12-14: 5; 2011-12-15: 5; 2011-12-16: 5; 2011-12-19: 5; 2011-12-20: 5; 2011-12-21: 5; 2011-12-22: 5; 2011-12-23: 5; 2011-12-27: 5; 2011-12-28: 5; 2011-12-29: 5; 2011-12-30: 5; 2012-01-03: 5; 2012-01-04: 5; 2012-01-05: 5; 2012-01-06: 5; 2012-01-09: 5; 2012-01-10: 5; 2012-01-11: 5; 2012-01-12: 5; 2012-01-13: 5; 2012-01-16: 5; 2012-01-17: 5; 2012-01-18: 5; 2012-01-19: 5; 2012-01-20: 5; 2012-01-23: 5; 2012-01-24: 5; 2012-01-25: 5; 2012-01-26: 5; 2012-01-27: 5; 2012-01-30: 5; 2012-01-31: 5; 2012-02-01: 5; 2012-02-02: 4; 2012-02-03: 4; 2012-02-06: 4; 2012-02-07: 4; 2012-02-08: 4; 2012-02-09: 4; 2012-02-10: 4; 2012-02-13: 4; 2012-02-14: 4; 2012-02-15: 4; 2012-02-16: 4; 2012-02-17: 4; 2012-02-20: 4; 2012-02-21: 4; 2012-02-22: 4; 2012-02-23: 4; 2012-02-24: 4; 2012-02-27: 4; 2012-02-28: 4; 2012-02-29: 4; 2012-03-01: 4; 2012-03-02: 4; 2012-03-05: 4; 2012-03-06: 4; 2012-03-07: 4; 2012-03-08: 4; 2012-03-09: 4; 2012-03-12: 4; 2012-03-13: 4; 2012-03-14: 4; 2012-03-15: 4; 2012-03-16: 4; 2012-03-19: 4; 2012-03-20: 4; 2012-03-21: 4; 2012-03-22: 4; 2012-03-23: 4; 2012-03-26: 4; 2012-03-27: 4; 2012-03-28: 4; 2012-03-29: 4; 2012-03-30: 4; 2012-04-02: 4; 2012-04-03: 4; 2012-04-04: 4; 2012-04-05: 4; 2012-04-06: 4; 2012-04-09: 4; 2012-04-10: 4; 2012-04-11: 4; 2012-04-12: 4; 2012-04-13: 4; 2012-04-16: 4; 2012-04-17: 4; 2012-04-18: 4; 2012-04-19: 4; 2012-04-20: 4; 2012-04-23: 4; 2012-04-24: 4; 2012-04-25: 4; 2012-04-26: 4; 2012-04-27: 4; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4; 2012-07-12: 4; 2012-07-13: 4; 2012-07-16: 4; 2012-07-17: 4; 2012-07-18: 4; 2012-07-19: 4; 2012-07-20: 4; 2012-07-23: 4; 2012-07-24: 4; 2012-07-25: 4; 2012-07-26: 4; 2012-07-27: 4; 2012-07-30: 4; 2012-07-31: 4; 2012-08-01: 4; 2012-08-02: 4; 2012-08-03: 4; 2012-08-06: 4; 2012-08-07: 4; 2012-08-08: 4
EC1910 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 4 | 202 | 202 | 0% | 2011-11-03 | 2012-08-13 | 311 | 902 | At Completion Labor Units | 2011-11-03: 1; 2011-11-04: 5; 2011-11-07: 5; 2011-11-08: 5; 2011-11-09: 5; 2011-11-10: 5; 2011-11-11: 5; 2011-11-14: 5; 2011-11-15: 5; 2011-11-16: 5; 2011-11-17: 5; 2011-11-18: 5; 2011-11-21: 5; 2011-11-22: 5; 2011-11-23: 5; 2011-11-25: 5; 2011-11-28: 5; 2011-11-29: 5; 2011-11-30: 5; 2011-12-01: 5; 2011-12-02: 5; 2011-12-05: 5; 2011-12-06: 5; 2011-12-07: 5; 2011-12-08: 5; 2011-12-09: 5; 2011-12-12: 5; 2011-12-13: 5; 2011-12-14: 5; 2011-12-15: 5; 2011-12-16: 5; 2011-12-19: 5; 2011-12-20: 5; 2011-12-21: 5; 2011-12-22: 5; 2011-12-23: 5; 2011-12-27: 5; 2011-12-28: 5; 2011-12-29: 5; 2011-12-30: 5; 2012-01-03: 5; 2012-01-04: 5; 2012-01-05: 5; 2012-01-06: 5; 2012-01-09: 5; 2012-01-10: 5; 2012-01-11: 5; 2012-01-12: 5; 2012-01-13: 5; 2012-01-16: 5; 2012-01-17: 5; 2012-01-18: 5; 2012-01-19: 5; 2012-01-20: 5; 2012-01-23: 5; 2012-01-24: 5; 2012-01-25: 5; 2012-01-26: 5; 2012-01-27: 5; 2012-01-30: 5; 2012-01-31: 5; 2012-02-01: 5; 2012-02-02: 5; 2012-02-03: 5; 2012-02-06: 5; 2012-02-07: 5; 2012-02-08: 5; 2012-02-09: 5; 2012-02-10: 4; 2012-02-13: 4; 2012-02-14: 4; 2012-02-15: 4; 2012-02-16: 4; 2012-02-17: 4; 2012-02-20: 4; 2012-02-21: 4; 2012-02-22: 4; 2012-02-23: 4; 2012-02-24: 4; 2012-02-27: 4; 2012-02-28: 4; 2012-02-29: 4; 2012-03-01: 4; 2012-03-02: 4; 2012-03-05: 4; 2012-03-06: 4; 2012-03-07: 4; 2012-03-08: 4; 2012-03-09: 4; 2012-03-12: 4; 2012-03-13: 4; 2012-03-14: 4; 2012-03-15: 4; 2012-03-16: 4; 2012-03-19: 4; 2012-03-20: 4; 2012-03-21: 4; 2012-03-22: 4; 2012-03-23: 4; 2012-03-26: 4; 2012-03-27: 4; 2012-03-28: 4; 2012-03-29: 4; 2012-03-30: 4; 2012-04-02: 4; 2012-04-03: 4; 2012-04-04: 4; 2012-04-05: 4; 2012-04-06: 4; 2012-04-09: 4; 2012-04-10: 4; 2012-04-11: 4; 2012-04-12: 4; 2012-04-13: 4; 2012-04-16: 4; 2012-04-17: 4; 2012-04-18: 4; 2012-04-19: 4; 2012-04-20: 4; 2012-04-23: 4; 2012-04-24: 4; 2012-04-25: 4; 2012-04-26: 4; 2012-04-27: 4; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4; 2012-07-12: 4; 2012-07-13: 4; 2012-07-16: 4; 2012-07-17: 4; 2012-07-18: 4; 2012-07-19: 4; 2012-07-20: 4; 2012-07-23: 4; 2012-07-24: 4; 2012-07-25: 4; 2012-07-26: 4; 2012-07-27: 4; 2012-07-30: 4; 2012-07-31: 4; 2012-08-01: 4; 2012-08-02: 4; 2012-08-03: 4; 2012-08-06: 4; 2012-08-07: 4; 2012-08-08: 4; 2012-08-09: 4; 2012-08-10: 4; 2012-08-13: 4; 2012-08-14: 4; 2012-08-15: 4; 2012-08-16: 4; 2012-08-17: 4; 2012-08-20: 2
EC1950 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 4 | 202 | 202 | 0% | 2011-11-10 | 2012-08-20 | 311 | 902 | At Completion Labor Units | 2011-11-10: 1; 2011-11-11: 5; 2011-11-14: 5; 2011-11-15: 5; 2011-11-16: 5; 2011-11-17: 5; 2011-11-18: 5; 2011-11-21: 5; 2011-11-22: 5; 2011-11-23: 5; 2011-11-25: 5; 2011-11-28: 5; 2011-11-29: 5; 2011-11-30: 5; 2011-12-01: 5; 2011-12-02: 5; 2011-12-05: 5; 2011-12-06: 5; 2011-12-07: 5; 2011-12-08: 5; 2011-12-09: 5; 2011-12-12: 5; 2011-12-13: 5; 2011-12-14: 5; 2011-12-15: 5; 2011-12-16: 5; 2011-12-19: 5; 2011-12-20: 5; 2011-12-21: 5; 2011-12-22: 5; 2011-12-23: 5; 2011-12-27: 5; 2011-12-28: 5; 2011-12-29: 5; 2011-12-30: 5; 2012-01-03: 5; 2012-01-04: 5; 2012-01-05: 5; 2012-01-06: 5; 2012-01-09: 5; 2012-01-10: 5; 2012-01-11: 5; 2012-01-12: 5; 2012-01-13: 5; 2012-01-16: 5; 2012-01-17: 5; 2012-01-18: 5; 2012-01-19: 5; 2012-01-20: 5; 2012-01-23: 5; 2012-01-24: 5; 2012-01-25: 5; 2012-01-26: 5; 2012-01-27: 5; 2012-01-30: 5; 2012-01-31: 5; 2012-02-01: 5; 2012-02-02: 5; 2012-02-03: 5; 2012-02-06: 5; 2012-02-07: 5; 2012-02-08: 5; 2012-02-09: 5; 2012-02-10: 5; 2012-02-13: 5; 2012-02-14: 5; 2012-02-15: 5; 2012-02-16: 5; 2012-02-17: 4; 2012-02-20: 4; 2012-02-21: 4; 2012-02-22: 4; 2012-02-23: 4; 2012-02-24: 4; 2012-02-27: 4; 2012-02-28: 4; 2012-02-29: 4; 2012-03-01: 4; 2012-03-02: 4; 2012-03-05: 4; 2012-03-06: 4; 2012-03-07: 4; 2012-03-08: 4; 2012-03-09: 4; 2012-03-12: 4; 2012-03-13: 4; 2012-03-14: 4; 2012-03-15: 4; 2012-03-16: 4; 2012-03-19: 4; 2012-03-20: 4; 2012-03-21: 4; 2012-03-22: 4; 2012-03-23: 4; 2012-03-26: 4; 2012-03-27: 4; 2012-03-28: 4; 2012-03-29: 4; 2012-03-30: 4; 2012-04-02: 4; 2012-04-03: 4; 2012-04-04: 4; 2012-04-05: 4; 2012-04-06: 4; 2012-04-09: 4; 2012-04-10: 4; 2012-04-11: 4; 2012-04-12: 4; 2012-04-13: 4; 2012-04-16: 4; 2012-04-17: 4; 2012-04-18: 4; 2012-04-19: 4; 2012-04-20: 4; 2012-04-23: 4; 2012-04-24: 4; 2012-04-25: 4; 2012-04-26: 4; 2012-04-27: 4; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4; 2012-07-12: 4; 2012-07-13: 4; 2012-07-16: 4; 2012-07-17: 4; 2012-07-18: 4; 2012-07-19: 4; 2012-07-20: 4; 2012-07-23: 4; 2012-07-24: 4; 2012-07-25: 4; 2012-07-26: 4; 2012-07-27: 4; 2012-07-30: 4; 2012-07-31: 4; 2012-08-01: 4; 2012-08-02: 4; 2012-08-03: 4; 2012-08-06: 4; 2012-08-07: 4; 2012-08-08: 4; 2012-08-09: 4; 2012-08-10: 4; 2012-08-13: 4; 2012-08-14: 4; 2012-08-15: 4; 2012-08-16: 4; 2012-08-17: 4; 2012-08-20: 4; 2012-08-21: 4; 2012-08-22: 4; 2012-08-23: 4; 2012-08-24: 4; 2012-08-27: 2
EC2080 | 1345006 | 5000 | ACMEGC | Pool & Deck | 142 | 142 | 0% | 2012-03-19 | 2012-10-03 | 0 | 672 | At Completion Labor Units | 2012-03-19: 2; 2012-03-20: 5; 2012-03-21: 5; 2012-03-22: 5; 2012-03-23: 5; 2012-03-26: 5; 2012-03-27: 5; 2012-03-28: 5; 2012-03-29: 5; 2012-03-30: 5; 2012-04-02: 5; 2012-04-03: 5; 2012-04-04: 5; 2012-04-05: 5; 2012-04-06: 5; 2012-04-09: 5; 2012-04-10: 5; 2012-04-11: 5; 2012-04-12: 5; 2012-04-13: 5; 2012-04-16: 5; 2012-04-17: 5; 2012-04-18: 5; 2012-04-19: 5; 2012-04-20: 5; 2012-04-23: 5; 2012-04-24: 5; 2012-04-25: 5; 2012-04-26: 5; 2012-04-27: 5; 2012-04-30: 5; 2012-05-01: 5; 2012-05-02: 5; 2012-05-03: 5; 2012-05-04: 5; 2012-05-07: 5; 2012-05-08: 5; 2012-05-09: 5; 2012-05-10: 5; 2012-05-11: 5; 2012-05-14: 5; 2012-05-15: 5; 2012-05-16: 5; 2012-05-17: 5; 2012-05-18: 5; 2012-05-21: 5; 2012-05-22: 5; 2012-05-23: 5; 2012-05-24: 5; 2012-05-25: 5; 2012-05-29: 5; 2012-05-30: 5; 2012-05-31: 5; 2012-06-01: 5; 2012-06-04: 5; 2012-06-05: 5; 2012-06-06: 5; 2012-06-07: 5; 2012-06-08: 5; 2012-06-11: 5; 2012-06-12: 5; 2012-06-13: 5; 2012-06-14: 5; 2012-06-15: 5; 2012-06-18: 5; 2012-06-19: 5; 2012-06-20: 5; 2012-06-21: 5; 2012-06-22: 5; 2012-06-25: 5; 2012-06-26: 5; 2012-06-27: 5; 2012-06-28: 5; 2012-06-29: 5; 2012-07-02: 5; 2012-07-03: 5; 2012-07-05: 5; 2012-07-06: 5; 2012-07-09: 5; 2012-07-10: 5; 2012-07-11: 5; 2012-07-12: 5; 2012-07-13: 5; 2012-07-16: 5; 2012-07-17: 5; 2012-07-18: 5; 2012-07-19: 5; 2012-07-20: 5; 2012-07-23: 5; 2012-07-24: 5; 2012-07-25: 5; 2012-07-26: 5; 2012-07-27: 5; 2012-07-30: 5; 2012-07-31: 5; 2012-08-01: 5; 2012-08-02: 5; 2012-08-03: 5; 2012-08-06: 5; 2012-08-07: 5; 2012-08-08: 5; 2012-08-09: 5; 2012-08-10: 5; 2012-08-13: 5; 2012-08-14: 5; 2012-08-15: 5; 2012-08-16: 5; 2012-08-17: 5; 2012-08-20: 5; 2012-08-21: 5; 2012-08-22: 5; 2012-08-23: 5; 2012-08-24: 5; 2012-08-27: 5; 2012-08-28: 5; 2012-08-29: 5; 2012-08-30: 5; 2012-08-31: 5; 2012-09-04: 5; 2012-09-05: 5; 2012-09-06: 5; 2012-09-07: 5; 2012-09-10: 5; 2012-09-11: 5; 2012-09-12: 5; 2012-09-13: 5; 2012-09-14: 5; 2012-09-17: 5; 2012-09-18: 5; 2012-09-19: 5; 2012-09-20: 5; 2012-09-21: 5; 2012-09-24: 5; 2012-09-25: 5; 2012-09-26: 5; 2012-09-27: 5; 2012-09-28: 5; 2012-10-01: 5; 2012-10-02: 5; 2012-10-03: 5; 2012-10-04: 5; 2012-10-05: 5; 2012-10-08: 1
EC2270 | 1345006 | 5000 | ACMEGC | Pergola and Amenities | 50 | 50 | 0% | 2012-09-05 | 2012-11-14 | 0 | 403 | At Completion Labor Units | 2012-09-05: 6; 2012-09-06: 8; 2012-09-07: 8; 2012-09-10: 8; 2012-09-11: 8; 2012-09-12: 8; 2012-09-13: 8; 2012-09-14: 8; 2012-09-17: 8; 2012-09-18: 8; 2012-09-19: 8; 2012-09-20: 8; 2012-09-21: 8; 2012-09-24: 8; 2012-09-25: 8; 2012-09-26: 8; 2012-09-27: 8; 2012-09-28: 8; 2012-10-01: 8; 2012-10-02: 8; 2012-10-03: 8; 2012-10-04: 8; 2012-10-05: 8; 2012-10-08: 8; 2012-10-09: 8; 2012-10-10: 8; 2012-10-11: 8; 2012-10-12: 8; 2012-10-15: 8; 2012-10-16: 8; 2012-10-17: 8; 2012-10-18: 8; 2012-10-19: 8; 2012-10-22: 8; 2012-10-23: 8; 2012-10-24: 8; 2012-10-25: 8; 2012-10-26: 8; 2012-10-29: 8; 2012-10-30: 8; 2012-10-31: 8; 2012-11-01: 8; 2012-11-02: 8; 2012-11-05: 8; 2012-11-06: 8; 2012-11-07: 8; 2012-11-08: 8; 2012-11-09: 8; 2012-11-12: 8; 2012-11-13: 8; 2012-11-14: 5
EC1090 | 1345006 | 1000 | ACMEGC | Building Pad Including UG Utils | 48 | 48 | 0% | 2010-11-02 | 2011-01-06 | 0 | 384 | At Completion Labor Units | 2010-11-02: 8; 2010-11-03: 8; 2010-11-04: 8; 2010-11-05: 8; 2010-11-08: 8; 2010-11-09: 8; 2010-11-10: 8; 2010-11-11: 8; 2010-11-12: 8; 2010-11-15: 8; 2010-11-16: 8; 2010-11-17: 8; 2010-11-18: 8; 2010-11-19: 8; 2010-11-22: 8; 2010-11-23: 8; 2010-11-24: 8; 2010-11-26: 8; 2010-11-29: 8; 2010-11-30: 8; 2010-12-01: 8; 2010-12-02: 8; 2010-12-03: 8; 2010-12-06: 8; 2010-12-07: 8; 2010-12-08: 8; 2010-12-09: 8; 2010-12-10: 8; 2010-12-13: 8; 2010-12-14: 8; 2010-12-15: 8; 2010-12-16: 8; 2010-12-17: 8; 2010-12-20: 8; 2010-12-21: 8; 2010-12-22: 8; 2010-12-23: 8; 2010-12-27: 8; 2010-12-28: 8; 2010-12-29: 8; 2010-12-30: 8; 2011-01-03: 8; 2011-01-04: 8; 2011-01-05: 8; 2011-01-06: 8; 2011-01-07: 8; 2011-01-10: 8; 2011-01-11: 8
EC1140 | 1345006 | 1000 | MASON | First Floor Masonry Structure | 12 | 12 | 0% | 2011-01-07 | 2011-01-24 | 0 | 96 | At Completion Labor Units | 2011-01-07: 8; 2011-01-10: 8; 2011-01-11: 8; 2011-01-12: 8; 2011-01-13: 8; 2011-01-14: 8; 2011-01-17: 8; 2011-01-18: 8; 2011-01-19: 8; 2011-01-20: 8; 2011-01-21: 8; 2011-01-24: 8
EC1170 | 1345006 | 1000 | STDPAV | Second Floor Slab & Collar Beam | 24 | 24 | 0% | 2011-01-25 | 2011-02-25 | 0 | 192 | At Completion Labor Units | 2011-01-25: 8; 2011-01-26: 8; 2011-01-27: 8; 2011-01-28: 8; 2011-01-31: 8; 2011-02-01: 8; 2011-02-02: 8; 2011-02-03: 8; 2011-02-04: 8; 2011-02-07: 8; 2011-02-08: 8; 2011-02-09: 8; 2011-02-10: 8; 2011-02-11: 8; 2011-02-14: 8; 2011-02-15: 8; 2011-02-16: 8; 2011-02-17: 8; 2011-02-18: 8; 2011-02-21: 8; 2011-02-22: 8; 2011-02-23: 8; 2011-02-24: 8; 2011-02-25: 8
EC1190 | 1345006 | 1000 | MASON | Second Floor Masonry Structure | 12 | 12 | 0% | 2011-02-28 | 2011-03-15 | 0 | 96 | At Completion Labor Units | 2011-02-28: 8; 2011-03-01: 8; 2011-03-02: 8; 2011-03-03: 8; 2011-03-04: 8; 2011-03-07: 8; 2011-03-08: 8; 2011-03-09: 8; 2011-03-10: 8; 2011-03-11: 8; 2011-03-14: 8; 2011-03-15: 8
EC1210 | 1345006 | 1000 | STDPAV | Third Floor Slab & Collar Beam | 24 | 24 | 0% | 2011-03-16 | 2011-04-18 | 0 | 192 | At Completion Labor Units | 2011-03-16: 8; 2011-03-17: 8; 2011-03-18: 8; 2011-03-21: 8; 2011-03-22: 8; 2011-03-23: 8; 2011-03-24: 8; 2011-03-25: 8; 2011-03-28: 8; 2011-03-29: 8; 2011-03-30: 8; 2011-03-31: 8; 2011-04-01: 8; 2011-04-04: 8; 2011-04-05: 8; 2011-04-06: 8; 2011-04-07: 8; 2011-04-08: 8; 2011-04-11: 8; 2011-04-12: 8; 2011-04-13: 8; 2011-04-14: 8; 2011-04-15: 8; 2011-04-18: 8
EC1240 | 1345006 | 1000 | MASON | Third Floor Masonry Structure | 12 | 12 | 0% | 2011-04-19 | 2011-05-04 | 0 | 96 | At Completion Labor Units | 2011-04-19: 8; 2011-04-20: 8; 2011-04-21: 8; 2011-04-22: 8; 2011-04-25: 8; 2011-04-26: 8; 2011-04-27: 8; 2011-04-28: 8; 2011-04-29: 8; 2011-05-02: 8; 2011-05-03: 8; 2011-05-04: 8
EC1250 | 1345006 | 1000 | STDPAV | Fourth Floor Slab & Collar Beam | 24 | 24 | 0% | 2011-05-05 | 2011-06-07 | 0 | 192 | At Completion Labor Units | 2011-05-05: 8; 2011-05-06: 8; 2011-05-09: 8; 2011-05-10: 8; 2011-05-11: 8; 2011-05-12: 8; 2011-05-13: 8; 2011-05-16: 8; 2011-05-17: 8; 2011-05-18: 8; 2011-05-19: 8; 2011-05-20: 8; 2011-05-23: 8; 2011-05-24: 8; 2011-05-25: 8; 2011-05-26: 8; 2011-05-27: 8; 2011-05-31: 8; 2011-06-01: 8; 2011-06-02: 8; 2011-06-03: 8; 2011-06-06: 8; 2011-06-07: 8; 2011-06-08: 8
EC1300 | 1345006 | 1000 | MASON | Fourth Floor Masonry Structure | 12 | 12 | 0% | 2011-06-08 | 2011-06-23 | 0 | 96 | At Completion Labor Units | 2011-06-08: 8; 2011-06-09: 8; 2011-06-10: 8; 2011-06-13: 8; 2011-06-14: 8; 2011-06-15: 8; 2011-06-16: 8; 2011-06-17: 8; 2011-06-20: 8; 2011-06-21: 8; 2011-06-22: 8; 2011-06-23: 8
EC1310 | 1345006 | 1000 | STDPAV | Roof Slab | 24 | 24 | 0% | 2011-06-24 | 2011-07-27 | 0 | 192 | At Completion Labor Units | 2011-06-24: 8; 2011-06-27: 8; 2011-06-28: 8; 2011-06-29: 8; 2011-06-30: 8; 2011-07-01: 8; 2011-07-05: 8; 2011-07-06: 8; 2011-07-07: 8; 2011-07-08: 8; 2011-07-11: 8; 2011-07-12: 8; 2011-07-13: 8; 2011-07-14: 8; 2011-07-15: 8; 2011-07-18: 8; 2011-07-19: 8; 2011-07-20: 8; 2011-07-21: 8; 2011-07-22: 8; 2011-07-25: 8; 2011-07-26: 8; 2011-07-27: 8; 2011-07-28: 8
EC1340 | 1345006 | 1000 | MASON | Stair and Elevator Masonry Structure | 5 | 5 | 0% | 2011-07-28 | 2011-08-03 | 0 | 38 | At Completion Labor Units | 2011-07-28: 8; 2011-07-29: 8; 2011-08-01: 8; 2011-08-02: 8; 2011-08-03: 6
EC1350 | 1345006 | 1000 | STDPAV | Roof Slab/Collar Beam | 12 | 12 | 0% | 2011-08-03 | 2011-08-19 | 0 | 96 | At Completion Labor Units | 2011-08-03: 2; 2011-08-04: 8; 2011-08-05: 8; 2011-08-08: 8; 2011-08-09: 8; 2011-08-10: 8; 2011-08-11: 8; 2011-08-12: 8; 2011-08-15: 8; 2011-08-16: 8; 2011-08-17: 8; 2011-08-18: 8; 2011-08-19: 6
EC1390 | 1345006 | 2000 | ACMEGC | Place Roof Trusses and Sheathing | 24 | 24 | 0% | 2011-08-19 | 2011-09-22 | 81 | 384 | At Completion Labor Units | 2011-08-19: 3; 2011-08-22: 16; 2011-08-23: 16; 2011-08-24: 16; 2011-08-25: 16; 2011-08-26: 16; 2011-08-29: 16; 2011-08-30: 16; 2011-08-31: 16; 2011-09-01: 16; 2011-09-02: 16; 2011-09-06: 16; 2011-09-07: 16; 2011-09-08: 16; 2011-09-09: 16; 2011-09-12: 16; 2011-09-13: 16; 2011-09-14: 16; 2011-09-15: 16; 2011-09-16: 16; 2011-09-19: 16; 2011-09-20: 16; 2011-09-21: 16; 2011-09-22: 16; 2011-09-23: 13
EC1400 | 1345006 | 2000 | MECH | Place Mechanical Equipment Supports | 24 | 24 | 0% | 2011-08-19 | 2011-09-22 | 259 | 192 | At Completion Labor Units | 2011-08-19: 2; 2011-08-22: 8; 2011-08-23: 8; 2011-08-24: 8; 2011-08-25: 8; 2011-08-26: 8; 2011-08-29: 8; 2011-08-30: 8; 2011-08-31: 8; 2011-09-01: 8; 2011-09-02: 8; 2011-09-06: 8; 2011-09-07: 8; 2011-09-08: 8; 2011-09-09: 8; 2011-09-12: 8; 2011-09-13: 8; 2011-09-14: 8; 2011-09-15: 8; 2011-09-16: 8; 2011-09-19: 8; 2011-09-20: 8; 2011-09-21: 8; 2011-09-22: 8; 2011-09-23: 6
EC1540 | 1345006 | 2000 | ACMEGC | Felt and Tile Roofing | 46 | 46 | 0% | 2011-09-22 | 2011-11-25 | 81 | 365 | At Completion Labor Units | 2011-09-22: 2; 2011-09-23: 8; 2011-09-26: 8; 2011-09-27: 8; 2011-09-28: 8; 2011-09-29: 8; 2011-09-30: 8; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 8; 2011-10-28: 8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 8; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 3
EC1780 | 1345006 | 2000 |  | Roof Complete | 0 | 0 | 0% |  | 2011-11-25 | 375 | 0 | At Completion Labor Units
EC1530 | 1345006 | 2000 | ACMEGC | Built-Up Asphalt Roofing | 34 | 34 | 0% | 2011-09-22 | 2011-11-09 | 259 | 269 | At Completion Labor Units | 2011-09-22: 2; 2011-09-23: 8; 2011-09-26: 8; 2011-09-27: 8; 2011-09-28: 8; 2011-09-29: 8; 2011-09-30: 8; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 8; 2011-10-28: 8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 3
EC1420 | 1345006 | 6000 |  | Start Garage | 0 | 0 | 0% | 2011-06-27 |  | 117 | 0 | At Completion Labor Units
EC1430 | 1345006 | 6000 | STEEL | Shop Drawings, Review & Approval | 72 | 72 | 0% | 2011-06-27 | 2011-10-04 | 117 | 614 | At Completion Labor Units | 2011-06-27: 9; 2011-06-28: 9; 2011-06-29: 9; 2011-06-30: 9; 2011-07-01: 9; 2011-07-05: 9; 2011-07-06: 9; 2011-07-07: 9; 2011-07-08: 9; 2011-07-11: 9; 2011-07-12: 9; 2011-07-13: 9; 2011-07-14: 9; 2011-07-15: 9; 2011-07-18: 9; 2011-07-19: 9; 2011-07-20: 9; 2011-07-21: 9; 2011-07-22: 9; 2011-07-25: 9; 2011-07-26: 9; 2011-07-27: 9; 2011-07-28: 9; 2011-07-29: 9; 2011-08-01: 9; 2011-08-02: 9; 2011-08-03: 9; 2011-08-04: 9; 2011-08-05: 9; 2011-08-08: 9; 2011-08-09: 9; 2011-08-10: 9; 2011-08-11: 9; 2011-08-12: 9; 2011-08-15: 9; 2011-08-16: 9; 2011-08-17: 9; 2011-08-18: 9; 2011-08-19: 9; 2011-08-22: 9; 2011-08-23: 9; 2011-08-24: 9; 2011-08-25: 9; 2011-08-26: 9; 2011-08-29: 9; 2011-08-30: 9; 2011-08-31: 9; 2011-09-01: 9; 2011-09-02: 9; 2011-09-06: 9; 2011-09-07: 9; 2011-09-08: 9; 2011-09-09: 9; 2011-09-12: 9; 2011-09-13: 9; 2011-09-14: 9; 2011-09-15: 9; 2011-09-16: 9; 2011-09-19: 9; 2011-09-20: 9; 2011-09-21: 9; 2011-09-22: 9; 2011-09-23: 9; 2011-09-26: 9; 2011-09-27: 9; 2011-09-28: 9; 2011-09-29: 9; 2011-09-30: 9; 2011-10-03: 9; 2011-10-04: 7; 2011-10-05: 4; 2011-10-06: 4
EC1810 | 1345006 | 6000 | STEEL | Fab & Delivery | 72 | 72 | 0% | 2011-10-05 | 2012-01-12 | 117 | 461 | At Completion Labor Units | 2011-10-05: 7; 2011-10-06: 7; 2011-10-07: 7; 2011-10-10: 7; 2011-10-11: 7; 2011-10-12: 7; 2011-10-13: 7; 2011-10-14: 7; 2011-10-17: 7; 2011-10-18: 7; 2011-10-19: 7; 2011-10-20: 7; 2011-10-21: 7; 2011-10-24: 7; 2011-10-25: 7; 2011-10-26: 7; 2011-10-27: 7; 2011-10-28: 7; 2011-10-31: 7; 2011-11-01: 7; 2011-11-02: 7; 2011-11-03: 7; 2011-11-04: 7; 2011-11-07: 7; 2011-11-08: 7; 2011-11-09: 7; 2011-11-10: 7; 2011-11-11: 7; 2011-11-14: 7; 2011-11-15: 7; 2011-11-16: 7; 2011-11-17: 7; 2011-11-18: 7; 2011-11-21: 7; 2011-11-22: 7; 2011-11-23: 7; 2011-11-25: 7; 2011-11-28: 7; 2011-11-29: 7; 2011-11-30: 7; 2011-12-01: 7; 2011-12-02: 7; 2011-12-05: 7; 2011-12-06: 7; 2011-12-07: 7; 2011-12-08: 7; 2011-12-09: 7; 2011-12-12: 7; 2011-12-13: 7; 2011-12-14: 7; 2011-12-15: 7; 2011-12-16: 7; 2011-12-19: 7; 2011-12-20: 7; 2011-12-21: 7; 2011-12-22: 7; 2011-12-23: 7; 2011-12-27: 7; 2011-12-28: 7; 2011-12-29: 7; 2011-12-30: 7; 2012-01-03: 7; 2012-01-04: 7; 2012-01-05: 7; 2012-01-06: 7; 2012-01-09: 7; 2012-01-10: 7; 2012-01-11: 7; 2012-01-12: 7; 2012-01-13: 5; 2012-01-16: 3; 2012-01-17: 3
EC2090 | 1345006 | 6000 | STEEL | Erect Precast Structure | 96 | 96 | 0% | 2012-01-13 | 2012-05-25 | 117 | 576 | At Completion Labor Units | 2012-01-13: 6; 2012-01-16: 6; 2012-01-17: 6; 2012-01-18: 6; 2012-01-19: 6; 2012-01-20: 6; 2012-01-23: 6; 2012-01-24: 6; 2012-01-25: 6; 2012-01-26: 6; 2012-01-27: 6; 2012-01-30: 6; 2012-01-31: 6; 2012-02-01: 6; 2012-02-02: 6; 2012-02-03: 6; 2012-02-06: 6; 2012-02-07: 6; 2012-02-08: 6; 2012-02-09: 6; 2012-02-10: 6; 2012-02-13: 6; 2012-02-14: 6; 2012-02-15: 6; 2012-02-16: 6; 2012-02-17: 6; 2012-02-20: 6; 2012-02-21: 6; 2012-02-22: 6; 2012-02-23: 6; 2012-02-24: 6; 2012-02-27: 6; 2012-02-28: 6; 2012-02-29: 6; 2012-03-01: 6; 2012-03-02: 6; 2012-03-05: 6; 2012-03-06: 6; 2012-03-07: 6; 2012-03-08: 6; 2012-03-09: 6; 2012-03-12: 6; 2012-03-13: 6; 2012-03-14: 6; 2012-03-15: 6; 2012-03-16: 6; 2012-03-19: 6; 2012-03-20: 6; 2012-03-21: 6; 2012-03-22: 6; 2012-03-23: 6; 2012-03-26: 6; 2012-03-27: 6; 2012-03-28: 6; 2012-03-29: 6; 2012-03-30: 6; 2012-04-02: 6; 2012-04-03: 6; 2012-04-04: 6; 2012-04-05: 6; 2012-04-06: 6; 2012-04-09: 6; 2012-04-10: 6; 2012-04-11: 6; 2012-04-12: 6; 2012-04-13: 6; 2012-04-16: 6; 2012-04-17: 6; 2012-04-18: 6; 2012-04-19: 6; 2012-04-20: 6; 2012-04-23: 6; 2012-04-24: 6; 2012-04-25: 6; 2012-04-26: 6; 2012-04-27: 6; 2012-04-30: 6; 2012-05-01: 6; 2012-05-02: 6; 2012-05-03: 6; 2012-05-04: 6; 2012-05-07: 6; 2012-05-08: 6; 2012-05-09: 6; 2012-05-10: 6; 2012-05-11: 6; 2012-05-14: 6; 2012-05-15: 6; 2012-05-16: 6; 2012-05-17: 6; 2012-05-18: 6; 2012-05-21: 6; 2012-05-22: 6; 2012-05-23: 5; 2012-05-24: 2; 2012-05-25: 2
EC2280 | 1345006 | 6000 | STEEL | Fire Protection and Lighting | 72 | 72 | 0% | 2012-05-28 | 2012-09-04 | 266 | 480 | At Completion Labor Units | 2012-05-29: 7; 2012-05-30: 7; 2012-05-31: 7; 2012-06-01: 7; 2012-06-04: 7; 2012-06-05: 7; 2012-06-06: 7; 2012-06-07: 7; 2012-06-08: 7; 2012-06-11: 7; 2012-06-12: 7; 2012-06-13: 7; 2012-06-14: 7; 2012-06-15: 7; 2012-06-18: 7; 2012-06-19: 7; 2012-06-20: 7; 2012-06-21: 7; 2012-06-22: 7; 2012-06-25: 7; 2012-06-26: 7; 2012-06-27: 7; 2012-06-28: 7; 2012-06-29: 7; 2012-07-02: 7; 2012-07-03: 7; 2012-07-05: 7; 2012-07-06: 7; 2012-07-09: 7; 2012-07-10: 7; 2012-07-11: 7; 2012-07-12: 7; 2012-07-13: 7; 2012-07-16: 7; 2012-07-17: 7; 2012-07-18: 7; 2012-07-19: 7; 2012-07-20: 7; 2012-07-23: 7; 2012-07-24: 7; 2012-07-25: 7; 2012-07-26: 7; 2012-07-27: 7; 2012-07-30: 7; 2012-07-31: 7; 2012-08-01: 7; 2012-08-02: 7; 2012-08-03: 7; 2012-08-06: 7; 2012-08-07: 7; 2012-08-08: 7; 2012-08-09: 7; 2012-08-10: 7; 2012-08-13: 7; 2012-08-14: 7; 2012-08-15: 7; 2012-08-16: 7; 2012-08-17: 7; 2012-08-20: 7; 2012-08-21: 7; 2012-08-22: 7; 2012-08-23: 7; 2012-08-24: 7; 2012-08-27: 7; 2012-08-28: 7; 2012-08-29: 7; 2012-08-30: 7; 2012-08-31: 7; 2012-09-04: 7; 2012-09-05: 7; 2012-09-06: 7; 2012-09-07: 7
EC2310 | 1345006 | 6000 | STEEL | Finishes, Barrier Cables & Striping | 72 | 72 | 0% | 2012-08-08 | 2012-11-15 | 266 | 768 | At Completion Labor Units | 2012-08-08: 11; 2012-08-09: 11; 2012-08-10: 11; 2012-08-13: 11; 2012-08-14: 11; 2012-08-15: 11; 2012-08-16: 11; 2012-08-17: 11; 2012-08-20: 11; 2012-08-21: 11; 2012-08-22: 11; 2012-08-23: 11; 2012-08-24: 11; 2012-08-27: 11; 2012-08-28: 11; 2012-08-29: 11; 2012-08-30: 11; 2012-08-31: 11; 2012-09-04: 11; 2012-09-05: 11; 2012-09-06: 11; 2012-09-07: 11; 2012-09-10: 11; 2012-09-11: 11; 2012-09-12: 11; 2012-09-13: 11; 2012-09-14: 11; 2012-09-17: 11; 2012-09-18: 11; 2012-09-19: 11; 2012-09-20: 11; 2012-09-21: 11; 2012-09-24: 11; 2012-09-25: 11; 2012-09-26: 11; 2012-09-27: 11; 2012-09-28: 11; 2012-10-01: 11; 2012-10-02: 11; 2012-10-03: 11; 2012-10-04: 11; 2012-10-05: 11; 2012-10-08: 11; 2012-10-09: 11; 2012-10-10: 11; 2012-10-11: 11; 2012-10-12: 11; 2012-10-15: 11; 2012-10-16: 11; 2012-10-17: 11; 2012-10-18: 11; 2012-10-19: 11; 2012-10-22: 11; 2012-10-23: 11; 2012-10-24: 11; 2012-10-25: 11; 2012-10-26: 11; 2012-10-29: 11; 2012-10-30: 11; 2012-10-31: 11; 2012-11-01: 11; 2012-11-02: 11; 2012-11-05: 11; 2012-11-06: 11; 2012-11-07: 11; 2012-11-08: 11; 2012-11-09: 11; 2012-11-12: 11; 2012-11-13: 11; 2012-11-14: 11; 2012-11-15: 11; 2012-11-16: 11
EC2400 | 1345006 | 6000 |  | Complete Garage | 0 | 0 | 0% |  | 2012-12-06 | 266 | 0 | At Completion Labor Units
EC2380 | 1345006 | 6000 | STEEL | Punchlist Garage | 14 | 14 | 0% | 2012-11-16 | 2012-12-06 | 266 | 192 | At Completion Labor Units | 2012-11-16: 16; 2012-11-19: 16; 2012-11-20: 16; 2012-11-21: 16; 2012-11-23: 16; 2012-11-26: 16; 2012-11-27: 16; 2012-11-28: 16; 2012-11-29: 16; 2012-11-30: 13; 2012-12-03: 8; 2012-12-04: 8; 2012-12-05: 8; 2012-12-06: 8; 2012-12-07: 3
EC2390 | 1345006 | 6000 |  | Complete Garage 1 | 0 | 0 | 0% |  | 2012-12-06 | 266 | 0 | At Completion Labor Units
EC2420 | 1345006 |  |  | Complete Building 2 | 0 | 0 | 0% |  | 2013-02-25 | 209 | 0 | At Completion Labor Units
EC1640 | 1345006 | 1000 | STDPAV | Roof Slab/Collar Beam | 24 | 24 | 0% | 2011-08-29 | 2011-09-30 | 117 | 192 | At Completion Labor Units | 2011-08-29: 5; 2011-08-30: 8; 2011-08-31: 8; 2011-09-01: 8; 2011-09-02: 8; 2011-09-06: 8; 2011-09-07: 8; 2011-09-08: 8; 2011-09-09: 8; 2011-09-12: 8; 2011-09-13: 8; 2011-09-14: 8; 2011-09-15: 8; 2011-09-16: 8; 2011-09-19: 8; 2011-09-20: 8; 2011-09-21: 8; 2011-09-22: 8; 2011-09-23: 8; 2011-09-26: 8; 2011-09-27: 8; 2011-09-28: 8; 2011-09-29: 8; 2011-09-30: 8; 2011-10-03: 3
EC1150 | 1345006 | 1000 | STDPAV | Building Slab Incl. UG Utils | 48 | 48 | 0% | 2010-11-30 | 2011-02-03 | 117 | 768 | At Completion Labor Units | 2010-11-30: 16; 2010-12-01: 16; 2010-12-02: 16; 2010-12-03: 16; 2010-12-06: 16; 2010-12-07: 16; 2010-12-08: 16; 2010-12-09: 16; 2010-12-10: 16; 2010-12-13: 16; 2010-12-14: 16; 2010-12-15: 16; 2010-12-16: 16; 2010-12-17: 16; 2010-12-20: 16; 2010-12-21: 16; 2010-12-22: 16; 2010-12-23: 16; 2010-12-27: 16; 2010-12-28: 16; 2010-12-29: 16; 2010-12-30: 16; 2011-01-03: 16; 2011-01-04: 16; 2011-01-05: 16; 2011-01-06: 16; 2011-01-07: 16; 2011-01-10: 16; 2011-01-11: 16; 2011-01-12: 16; 2011-01-13: 16; 2011-01-14: 16; 2011-01-17: 16; 2011-01-18: 16; 2011-01-19: 16; 2011-01-20: 16; 2011-01-21: 16; 2011-01-24: 16; 2011-01-25: 16; 2011-01-26: 16; 2011-01-27: 16; 2011-01-28: 16; 2011-01-31: 16; 2011-02-01: 16; 2011-02-02: 16; 2011-02-03: 16; 2011-02-04: 16; 2011-02-07: 16
EC1220 | 1345006 | 1000 | MASON | First Floor Masonry Structure | 12 | 12 | 0% | 2011-02-04 | 2011-02-21 | 117 | 96 | At Completion Labor Units | 2011-02-04: 8; 2011-02-07: 8; 2011-02-08: 8; 2011-02-09: 8; 2011-02-10: 8; 2011-02-11: 8; 2011-02-14: 8; 2011-02-15: 8; 2011-02-16: 8; 2011-02-17: 8; 2011-02-18: 8; 2011-02-21: 8
EC1230 | 1345006 | 1000 | STDPAV | Second Floor Slab & Collar Beam | 24 | 24 | 0% | 2011-02-22 | 2011-03-25 | 117 | 192 | At Completion Labor Units | 2011-02-22: 8; 2011-02-23: 8; 2011-02-24: 8; 2011-02-25: 8; 2011-02-28: 8; 2011-03-01: 8; 2011-03-02: 8; 2011-03-03: 8; 2011-03-04: 8; 2011-03-07: 8; 2011-03-08: 8; 2011-03-09: 8; 2011-03-10: 8; 2011-03-11: 8; 2011-03-14: 8; 2011-03-15: 8; 2011-03-16: 8; 2011-03-17: 8; 2011-03-18: 8; 2011-03-21: 8; 2011-03-22: 8; 2011-03-23: 8; 2011-03-24: 8; 2011-03-25: 8
EC1260 | 1345006 | 1000 | MASON | Second Floor Masonry Structure | 12 | 12 | 0% | 2011-03-28 | 2011-04-12 | 117 | 96 | At Completion Labor Units | 2011-03-28: 8; 2011-03-29: 8; 2011-03-30: 8; 2011-03-31: 8; 2011-04-01: 8; 2011-04-04: 8; 2011-04-05: 8; 2011-04-06: 8; 2011-04-07: 8; 2011-04-08: 8; 2011-04-11: 8; 2011-04-12: 8
EC1290 | 1345006 | 1000 | STDPAV | Third Floor Slab & Collar Beam | 24 | 24 | 0% | 2011-04-13 | 2011-05-16 | 117 | 192 | At Completion Labor Units | 2011-04-13: 8; 2011-04-14: 8; 2011-04-15: 8; 2011-04-18: 8; 2011-04-19: 8; 2011-04-20: 8; 2011-04-21: 8; 2011-04-22: 8; 2011-04-25: 8; 2011-04-26: 8; 2011-04-27: 8; 2011-04-28: 8; 2011-04-29: 8; 2011-05-02: 8; 2011-05-03: 8; 2011-05-04: 8; 2011-05-05: 8; 2011-05-06: 8; 2011-05-09: 8; 2011-05-10: 8; 2011-05-11: 8; 2011-05-12: 8; 2011-05-13: 8; 2011-05-16: 8
EC1320 | 1345006 | 1000 | MASON | Third Floor Masonry Structure | 12 | 12 | 0% | 2011-05-17 | 2011-06-01 | 117 | 96 | At Completion Labor Units | 2011-05-17: 8; 2011-05-18: 8; 2011-05-19: 8; 2011-05-20: 8; 2011-05-23: 8; 2011-05-24: 8; 2011-05-25: 8; 2011-05-26: 8; 2011-05-27: 8; 2011-05-31: 8; 2011-06-01: 8; 2011-06-02: 8
EC1330 | 1345006 | 1000 | STDPAV | Fourth Floor Slab & Collar Beam | 24 | 24 | 0% | 2011-06-02 | 2011-07-05 | 117 | 192 | At Completion Labor Units | 2011-06-02: 8; 2011-06-03: 8; 2011-06-06: 8; 2011-06-07: 8; 2011-06-08: 8; 2011-06-09: 8; 2011-06-10: 8; 2011-06-13: 8; 2011-06-14: 8; 2011-06-15: 8; 2011-06-16: 8; 2011-06-17: 8; 2011-06-20: 8; 2011-06-21: 8; 2011-06-22: 8; 2011-06-23: 8; 2011-06-24: 8; 2011-06-27: 8; 2011-06-28: 8; 2011-06-29: 8; 2011-06-30: 8; 2011-07-01: 8; 2011-07-05: 8; 2011-07-06: 8
EC1380 | 1345006 | 1000 | MASON | Fourth Floor Masonry Structure | 12 | 12 | 0% | 2011-07-06 | 2011-07-21 | 117 | 96 | At Completion Labor Units | 2011-07-06: 8; 2011-07-07: 8; 2011-07-08: 8; 2011-07-11: 8; 2011-07-12: 8; 2011-07-13: 8; 2011-07-14: 8; 2011-07-15: 8; 2011-07-18: 8; 2011-07-19: 8; 2011-07-20: 8; 2011-07-21: 8
EC1480 | 1345006 | 1000 | STDPAV | Roof Slab | 22 | 22 | 0% | 2011-07-22 | 2011-08-22 | 117 | 173 | At Completion Labor Units | 2011-07-22: 8; 2011-07-25: 8; 2011-07-26: 8; 2011-07-27: 8; 2011-07-28: 8; 2011-07-29: 8; 2011-08-01: 8; 2011-08-02: 8; 2011-08-03: 8; 2011-08-04: 8; 2011-08-05: 8; 2011-08-08: 8; 2011-08-09: 8; 2011-08-10: 8; 2011-08-11: 8; 2011-08-12: 8; 2011-08-15: 8; 2011-08-16: 8; 2011-08-17: 8; 2011-08-18: 8; 2011-08-19: 8; 2011-08-22: 5
EC1620 | 1345006 | 1000 | MASON | Stair and Elevator Masonry Structure | 5 | 5 | 0% | 2011-08-22 | 2011-08-29 | 117 | 38 | At Completion Labor Units | 2011-08-22: 3; 2011-08-23: 8; 2011-08-24: 8; 2011-08-25: 8; 2011-08-26: 8; 2011-08-29: 3
EC1710 | 1345006 | 2000 | ACMEGC | Place Roof Trusses and Sheathing | 24 | 24 | 0% | 2011-09-30 | 2011-11-03 | 117 | 384 | At Completion Labor Units | 2011-09-30: 10; 2011-10-03: 16; 2011-10-04: 16; 2011-10-05: 16; 2011-10-06: 16; 2011-10-07: 16; 2011-10-10: 16; 2011-10-11: 16; 2011-10-12: 16; 2011-10-13: 16; 2011-10-14: 16; 2011-10-17: 16; 2011-10-18: 16; 2011-10-19: 16; 2011-10-20: 16; 2011-10-21: 16; 2011-10-24: 16; 2011-10-25: 16; 2011-10-26: 16; 2011-10-27: 16; 2011-10-28: 16; 2011-10-31: 16; 2011-11-01: 16; 2011-11-02: 16; 2011-11-03: 6
EC1720 | 1345006 | 2000 | MECH | Place Mechanical Equipment Supports | 24 | 24 | 0% | 2011-09-30 | 2011-11-03 | 129 | 192 | At Completion Labor Units | 2011-09-30: 5; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 8; 2011-10-28: 8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 3
EC1860 | 1345006 | 2000 | ACMEGC | Built-Up Asphalt Roofing | 34 | 34 | 0% | 2011-11-03 | 2011-12-20 | 129 | 269 | At Completion Labor Units | 2011-11-03: 5; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 8; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 8; 2011-11-29: 8; 2011-11-30: 8; 2011-12-01: 8; 2011-12-02: 8; 2011-12-05: 8; 2011-12-06: 8; 2011-12-07: 8; 2011-12-08: 8; 2011-12-09: 8; 2011-12-12: 8; 2011-12-13: 8; 2011-12-14: 8; 2011-12-15: 8; 2011-12-16: 8; 2011-12-19: 8; 2011-12-20: 8; 2011-12-21: 8
EC1870 | 1345006 | 2000 | ACMEGC | Felt and Tile Roofing | 46 | 46 | 0% | 2011-11-03 | 2012-01-05 | 117 | 365 | At Completion Labor Units | 2011-11-03: 5; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 8; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 8; 2011-11-29: 8; 2011-11-30: 8; 2011-12-01: 8; 2011-12-02: 8; 2011-12-05: 8; 2011-12-06: 8; 2011-12-07: 8; 2011-12-08: 8; 2011-12-09: 8; 2011-12-12: 8; 2011-12-13: 8; 2011-12-14: 8; 2011-12-15: 8; 2011-12-16: 8; 2011-12-19: 8; 2011-12-20: 8; 2011-12-21: 8; 2011-12-22: 8; 2011-12-23: 8; 2011-12-27: 8; 2011-12-28: 8; 2011-12-29: 8; 2011-12-30: 8; 2012-01-03: 8; 2012-01-04: 8; 2012-01-05: 8; 2012-01-06: 8; 2012-01-09: 8; 2012-01-10: 8
EC2020 | 1345006 | 2000 |  | Roof Complete | 0 | 0 | 0% |  | 2012-01-05 | 117 | 0 | At Completion Labor Units
EC1730 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 1 | 24 | 24 | 0% | 2011-09-30 | 2011-11-03 | 249 | 384 | At Completion Labor Units | 2011-09-30: 10; 2011-10-03: 16; 2011-10-04: 16; 2011-10-05: 16; 2011-10-06: 16; 2011-10-07: 16; 2011-10-10: 16; 2011-10-11: 16; 2011-10-12: 16; 2011-10-13: 16; 2011-10-14: 16; 2011-10-17: 16; 2011-10-18: 16; 2011-10-19: 16; 2011-10-20: 16; 2011-10-21: 16; 2011-10-24: 16; 2011-10-25: 16; 2011-10-26: 16; 2011-10-27: 16; 2011-10-28: 16; 2011-10-31: 16; 2011-11-01: 16; 2011-11-02: 16; 2011-11-03: 6
EC1800 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 2 | 22 | 22 | 0% | 2011-10-27 | 2011-11-25 | 249 | 346 | At Completion Labor Units | 2011-10-27: 10; 2011-10-28: 16; 2011-10-31: 16; 2011-11-01: 16; 2011-11-02: 16; 2011-11-03: 16; 2011-11-04: 16; 2011-11-07: 16; 2011-11-08: 16; 2011-11-09: 16; 2011-11-10: 16; 2011-11-11: 16; 2011-11-14: 16; 2011-11-15: 16; 2011-11-16: 16; 2011-11-17: 16; 2011-11-18: 16; 2011-11-21: 16; 2011-11-22: 16; 2011-11-23: 16; 2011-11-25: 16; 2011-11-28: 16
EC1880 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 3 | 22 | 22 | 0% | 2011-11-21 | 2011-12-20 | 249 | 346 | At Completion Labor Units | 2011-11-21: 16; 2011-11-22: 16; 2011-11-23: 16; 2011-11-25: 16; 2011-11-28: 16; 2011-11-29: 16; 2011-11-30: 16; 2011-12-01: 16; 2011-12-02: 16; 2011-12-05: 16; 2011-12-06: 16; 2011-12-07: 16; 2011-12-08: 16; 2011-12-09: 16; 2011-12-12: 16; 2011-12-13: 16; 2011-12-14: 16; 2011-12-15: 16; 2011-12-16: 16; 2011-12-19: 16; 2011-12-20: 16; 2011-12-21: 10
EC1920 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 4 | 24 | 24 | 0% | 2011-12-13 | 2012-01-16 | 249 | 384 | At Completion Labor Units | 2011-12-13: 6; 2011-12-14: 16; 2011-12-15: 16; 2011-12-16: 16; 2011-12-19: 16; 2011-12-20: 16; 2011-12-21: 16; 2011-12-22: 16; 2011-12-23: 16; 2011-12-27: 16; 2011-12-28: 16; 2011-12-29: 16; 2011-12-30: 16; 2012-01-03: 16; 2012-01-04: 16; 2012-01-05: 16; 2012-01-06: 16; 2012-01-09: 16; 2012-01-10: 16; 2012-01-11: 16; 2012-01-12: 16; 2012-01-13: 16; 2012-01-16: 16; 2012-01-17: 16; 2012-01-18: 10
EC1830 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor1 | 12 | 12 | 0% | 2011-10-28 | 2011-11-15 | 267 | 96 | At Completion Labor Units | 2011-10-28: 5; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 3
EC1890 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor 2 | 10 | 10 | 0% | 2011-11-22 | 2011-12-05 | 263 | 77 | At Completion Labor Units | 2011-11-22: 8; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 8; 2011-11-29: 8; 2011-11-30: 8; 2011-12-01: 8; 2011-12-02: 8; 2011-12-05: 8; 2011-12-06: 5
EC1930 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor 3 | 12 | 12 | 0% | 2011-12-14 | 2011-12-30 | 256 | 96 | At Completion Labor Units | 2011-12-14: 3; 2011-12-15: 8; 2011-12-16: 8; 2011-12-19: 8; 2011-12-20: 8; 2011-12-21: 8; 2011-12-22: 8; 2011-12-23: 8; 2011-12-27: 8; 2011-12-28: 8; 2011-12-29: 8; 2011-12-30: 8; 2012-01-03: 5
EC1960 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor 4 | 12 | 12 | 0% | 2012-01-10 | 2012-01-26 | 249 | 96 | At Completion Labor Units | 2012-01-10: 3; 2012-01-11: 8; 2012-01-12: 8; 2012-01-13: 8; 2012-01-16: 8; 2012-01-17: 8; 2012-01-18: 8; 2012-01-19: 8; 2012-01-20: 8; 2012-01-23: 8; 2012-01-24: 8; 2012-01-25: 8; 2012-01-26: 5
EC1940 | 1345006 | 3000 | ACMEGC | Stucco Bands | 12 | 12 | 0% | 2012-01-12 | 2012-01-30 | 249 | 96 | At Completion Labor Units | 2012-01-12: 3; 2012-01-13: 8; 2012-01-16: 8; 2012-01-17: 8; 2012-01-18: 8; 2012-01-19: 8; 2012-01-20: 8; 2012-01-23: 8; 2012-01-24: 8; 2012-01-25: 8; 2012-01-26: 8; 2012-01-27: 8; 2012-01-30: 5
EC1970 | 1345006 | 3000 | ACMEGC | Stucco Grey | 24 | 24 | 0% | 2012-01-30 | 2012-03-02 | 249 | 192 | At Completion Labor Units | 2012-01-30: 3; 2012-01-31: 8; 2012-02-01: 8; 2012-02-02: 8; 2012-02-03: 8; 2012-02-06: 8; 2012-02-07: 8; 2012-02-08: 8; 2012-02-09: 8; 2012-02-10: 8; 2012-02-13: 8; 2012-02-14: 8; 2012-02-15: 8; 2012-02-16: 8; 2012-02-17: 8; 2012-02-20: 8; 2012-02-21: 8; 2012-02-22: 8; 2012-02-23: 8; 2012-02-24: 8; 2012-02-27: 8; 2012-02-28: 8; 2012-02-29: 8; 2012-03-01: 8; 2012-03-02: 5
EC2050 | 1345006 | 3000 | ACMEGC | Stucco Finish Coat | 24 | 24 | 0% | 2012-03-02 | 2012-04-05 | 249 | 192 | At Completion Labor Units | 2012-03-02: 3; 2012-03-05: 8; 2012-03-06: 8; 2012-03-07: 8; 2012-03-08: 8; 2012-03-09: 8; 2012-03-12: 8; 2012-03-13: 8; 2012-03-14: 8; 2012-03-15: 8; 2012-03-16: 8; 2012-03-19: 8; 2012-03-20: 8; 2012-03-21: 8; 2012-03-22: 8; 2012-03-23: 8; 2012-03-26: 8; 2012-03-27: 8; 2012-03-28: 8; 2012-03-29: 8; 2012-03-30: 8; 2012-04-02: 8; 2012-04-03: 8; 2012-04-04: 8; 2012-04-05: 5
EC2130 | 1345006 | 3000 | ACMEGC | Caulk | 12 | 12 | 0% | 2012-04-05 | 2012-04-23 | 249 | 96 | At Completion Labor Units | 2012-04-05: 3; 2012-04-06: 8; 2012-04-09: 8; 2012-04-10: 8; 2012-04-11: 8; 2012-04-12: 8; 2012-04-13: 8; 2012-04-16: 8; 2012-04-17: 8; 2012-04-18: 8; 2012-04-19: 8; 2012-04-20: 8; 2012-04-23: 5
EC2160 | 1345006 | 3000 | ACMEGC | Stucco Band Trim | 24 | 24 | 0% | 2012-04-23 | 2012-05-25 | 249 | 192 | At Completion Labor Units | 2012-04-23: 3; 2012-04-24: 8; 2012-04-25: 8; 2012-04-26: 8; 2012-04-27: 8; 2012-04-30: 8; 2012-05-01: 8; 2012-05-02: 8; 2012-05-03: 8; 2012-05-04: 8; 2012-05-07: 8; 2012-05-08: 8; 2012-05-09: 8; 2012-05-10: 8; 2012-05-11: 8; 2012-05-14: 8; 2012-05-15: 8; 2012-05-16: 8; 2012-05-17: 8; 2012-05-18: 8; 2012-05-21: 8; 2012-05-22: 8; 2012-05-23: 8; 2012-05-24: 8; 2012-05-25: 5
EC2220 | 1345006 | 3000 | ACMEGC | Paint Exterior | 48 | 48 | 0% | 2012-06-01 | 2012-08-08 | 249 | 384 | At Completion Labor Units | 2012-06-01: 3; 2012-06-04: 8; 2012-06-05: 8; 2012-06-06: 8; 2012-06-07: 8; 2012-06-08: 8; 2012-06-11: 8; 2012-06-12: 8; 2012-06-13: 8; 2012-06-14: 8; 2012-06-15: 8; 2012-06-18: 8; 2012-06-19: 8; 2012-06-20: 8; 2012-06-21: 8; 2012-06-22: 8; 2012-06-25: 8; 2012-06-26: 8; 2012-06-27: 8; 2012-06-28: 8; 2012-06-29: 8; 2012-07-02: 8; 2012-07-03: 8; 2012-07-05: 8; 2012-07-06: 8; 2012-07-09: 8; 2012-07-10: 8; 2012-07-11: 8; 2012-07-12: 8; 2012-07-13: 8; 2012-07-16: 8; 2012-07-17: 8; 2012-07-18: 8; 2012-07-19: 8; 2012-07-20: 8; 2012-07-23: 8; 2012-07-24: 8; 2012-07-25: 8; 2012-07-26: 8; 2012-07-27: 8; 2012-07-30: 8; 2012-07-31: 8; 2012-08-01: 8; 2012-08-02: 8; 2012-08-03: 8; 2012-08-06: 8; 2012-08-07: 8; 2012-08-08: 8; 2012-08-09: 5
EC2300 | 1345006 | 3000 | ACMEGC | Demobilize Scaffolding | 12 | 12 | 0% | 2012-08-08 | 2012-08-24 | 249 | 96 | At Completion Labor Units | 2012-08-08: 3; 2012-08-09: 8; 2012-08-10: 8; 2012-08-13: 8; 2012-08-14: 8; 2012-08-15: 8; 2012-08-16: 8; 2012-08-17: 8; 2012-08-20: 8; 2012-08-21: 8; 2012-08-22: 8; 2012-08-23: 8; 2012-08-24: 5
EC1740 | 1345006 | 3000 | ACMEGC | Mobilize Scaffolding | 12 | 12 | 0% | 2011-09-30 | 2011-10-18 | 275 | 96 | At Completion Labor Units | 2011-09-30: 5; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 3
EC2320 | 1345006 | 3000 |  | Shell Complete | 0 | 0 | 0% |  | 2012-08-24 | 261 | 0 | At Completion Labor Units
EC2230 | 1345006 | 3000 | ACMEGC | Install Railings | 36 | 36 | 0% | 2012-06-01 | 2012-07-23 | 285 | 288 | At Completion Labor Units | 2012-06-01: 3; 2012-06-04: 8; 2012-06-05: 8; 2012-06-06: 8; 2012-06-07: 8; 2012-06-08: 8; 2012-06-11: 8; 2012-06-12: 8; 2012-06-13: 8; 2012-06-14: 8; 2012-06-15: 8; 2012-06-18: 8; 2012-06-19: 8; 2012-06-20: 8; 2012-06-21: 8; 2012-06-22: 8; 2012-06-25: 8; 2012-06-26: 8; 2012-06-27: 8; 2012-06-28: 8; 2012-06-29: 8; 2012-07-02: 8; 2012-07-03: 8; 2012-07-05: 8; 2012-07-06: 8; 2012-07-09: 8; 2012-07-10: 8; 2012-07-11: 8; 2012-07-12: 8; 2012-07-13: 8; 2012-07-16: 8; 2012-07-17: 8; 2012-07-18: 8; 2012-07-19: 8; 2012-07-20: 8; 2012-07-23: 8; 2012-07-24: 5
EC2150 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 3 | 197 | 197 | 0% | 2012-01-27 | 2012-10-29 | 209 | 896 | At Completion Labor Units | 2012-01-27: 5; 2012-01-30: 5; 2012-01-31: 5; 2012-02-01: 5; 2012-02-02: 5; 2012-02-03: 5; 2012-02-06: 5; 2012-02-07: 5; 2012-02-08: 5; 2012-02-09: 5; 2012-02-10: 5; 2012-02-13: 5; 2012-02-14: 5; 2012-02-15: 5; 2012-02-16: 5; 2012-02-17: 5; 2012-02-20: 5; 2012-02-21: 5; 2012-02-22: 5; 2012-02-23: 5; 2012-02-24: 5; 2012-02-27: 5; 2012-02-28: 5; 2012-02-29: 5; 2012-03-01: 5; 2012-03-02: 5; 2012-03-05: 5; 2012-03-06: 5; 2012-03-07: 5; 2012-03-08: 5; 2012-03-09: 5; 2012-03-12: 5; 2012-03-13: 5; 2012-03-14: 5; 2012-03-15: 5; 2012-03-16: 5; 2012-03-19: 5; 2012-03-20: 5; 2012-03-21: 5; 2012-03-22: 5; 2012-03-23: 5; 2012-03-26: 5; 2012-03-27: 5; 2012-03-28: 5; 2012-03-29: 5; 2012-03-30: 5; 2012-04-02: 5; 2012-04-03: 5; 2012-04-04: 5; 2012-04-05: 5; 2012-04-06: 5; 2012-04-09: 5; 2012-04-10: 5; 2012-04-11: 5; 2012-04-12: 5; 2012-04-13: 5; 2012-04-16: 5; 2012-04-17: 5; 2012-04-18: 5; 2012-04-19: 5; 2012-04-20: 5; 2012-04-23: 5; 2012-04-24: 5; 2012-04-25: 5; 2012-04-26: 5; 2012-04-27: 5; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4; 2012-07-12: 4; 2012-07-13: 4; 2012-07-16: 4; 2012-07-17: 4; 2012-07-18: 4; 2012-07-19: 4; 2012-07-20: 4; 2012-07-23: 4; 2012-07-24: 4; 2012-07-25: 4; 2012-07-26: 4; 2012-07-27: 4; 2012-07-30: 4; 2012-07-31: 4; 2012-08-01: 4; 2012-08-02: 4; 2012-08-03: 4; 2012-08-06: 4; 2012-08-07: 4; 2012-08-08: 4; 2012-08-09: 4; 2012-08-10: 4; 2012-08-13: 4; 2012-08-14: 4; 2012-08-15: 4; 2012-08-16: 4; 2012-08-17: 4; 2012-08-20: 4; 2012-08-21: 4; 2012-08-22: 4; 2012-08-23: 4; 2012-08-24: 4; 2012-08-27: 4; 2012-08-28: 4; 2012-08-29: 4; 2012-08-30: 4; 2012-08-31: 4; 2012-09-04: 4; 2012-09-05: 4; 2012-09-06: 4; 2012-09-07: 4; 2012-09-10: 4; 2012-09-11: 4; 2012-09-12: 4; 2012-09-13: 4; 2012-09-14: 4; 2012-09-17: 4; 2012-09-18: 4; 2012-09-19: 4; 2012-09-20: 4; 2012-09-21: 4; 2012-09-24: 4; 2012-09-25: 4; 2012-09-26: 4; 2012-09-27: 4; 2012-09-28: 4; 2012-10-01: 4; 2012-10-02: 4; 2012-10-03: 4; 2012-10-04: 4; 2012-10-05: 4; 2012-10-08: 4; 2012-10-09: 4; 2012-10-10: 4; 2012-10-11: 4; 2012-10-12: 4; 2012-10-15: 4; 2012-10-16: 4; 2012-10-17: 4; 2012-10-18: 4; 2012-10-19: 4; 2012-10-22: 4; 2012-10-23: 4; 2012-10-24: 4; 2012-10-25: 4; 2012-10-26: 4; 2012-10-29: 4; 2012-10-30: 4; 2012-10-31: 4; 2012-11-01: 4
EC2170 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 3 | 197 | 197 | 0% | 2012-02-03 | 2012-11-05 | 209 | 896 | At Completion Labor Units | 2012-02-03: 5; 2012-02-06: 5; 2012-02-07: 5; 2012-02-08: 5; 2012-02-09: 5; 2012-02-10: 5; 2012-02-13: 5; 2012-02-14: 5; 2012-02-15: 5; 2012-02-16: 5; 2012-02-17: 5; 2012-02-20: 5; 2012-02-21: 5; 2012-02-22: 5; 2012-02-23: 5; 2012-02-24: 5; 2012-02-27: 5; 2012-02-28: 5; 2012-02-29: 5; 2012-03-01: 5; 2012-03-02: 5; 2012-03-05: 5; 2012-03-06: 5; 2012-03-07: 5; 2012-03-08: 5; 2012-03-09: 5; 2012-03-12: 5; 2012-03-13: 5; 2012-03-14: 5; 2012-03-15: 5; 2012-03-16: 5; 2012-03-19: 5; 2012-03-20: 5; 2012-03-21: 5; 2012-03-22: 5; 2012-03-23: 5; 2012-03-26: 5; 2012-03-27: 5; 2012-03-28: 5; 2012-03-29: 5; 2012-03-30: 5; 2012-04-02: 5; 2012-04-03: 5; 2012-04-04: 5; 2012-04-05: 5; 2012-04-06: 5; 2012-04-09: 5; 2012-04-10: 5; 2012-04-11: 5; 2012-04-12: 5; 2012-04-13: 5; 2012-04-16: 5; 2012-04-17: 5; 2012-04-18: 5; 2012-04-19: 5; 2012-04-20: 5; 2012-04-23: 5; 2012-04-24: 5; 2012-04-25: 5; 2012-04-26: 5; 2012-04-27: 5; 2012-04-30: 5; 2012-05-01: 5; 2012-05-02: 5; 2012-05-03: 5; 2012-05-04: 5; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4; 2012-07-12: 4; 2012-07-13: 4; 2012-07-16: 4; 2012-07-17: 4; 2012-07-18: 4; 2012-07-19: 4; 2012-07-20: 4; 2012-07-23: 4; 2012-07-24: 4; 2012-07-25: 4; 2012-07-26: 4; 2012-07-27: 4; 2012-07-30: 4; 2012-07-31: 4; 2012-08-01: 4; 2012-08-02: 4; 2012-08-03: 4; 2012-08-06: 4; 2012-08-07: 4; 2012-08-08: 4; 2012-08-09: 4; 2012-08-10: 4; 2012-08-13: 4; 2012-08-14: 4; 2012-08-15: 4; 2012-08-16: 4; 2012-08-17: 4; 2012-08-20: 4; 2012-08-21: 4; 2012-08-22: 4; 2012-08-23: 4; 2012-08-24: 4; 2012-08-27: 4; 2012-08-28: 4; 2012-08-29: 4; 2012-08-30: 4; 2012-08-31: 4; 2012-09-04: 4; 2012-09-05: 4; 2012-09-06: 4; 2012-09-07: 4; 2012-09-10: 4; 2012-09-11: 4; 2012-09-12: 4; 2012-09-13: 4; 2012-09-14: 4; 2012-09-17: 4; 2012-09-18: 4; 2012-09-19: 4; 2012-09-20: 4; 2012-09-21: 4; 2012-09-24: 4; 2012-09-25: 4; 2012-09-26: 4; 2012-09-27: 4; 2012-09-28: 4; 2012-10-01: 4; 2012-10-02: 4; 2012-10-03: 4; 2012-10-04: 4; 2012-10-05: 4; 2012-10-08: 4; 2012-10-09: 4; 2012-10-10: 4; 2012-10-11: 4; 2012-10-12: 4; 2012-10-15: 4; 2012-10-16: 4; 2012-10-17: 4; 2012-10-18: 4; 2012-10-19: 4; 2012-10-22: 4; 2012-10-23: 4; 2012-10-24: 4; 2012-10-25: 4; 2012-10-26: 4; 2012-10-29: 4; 2012-10-30: 4; 2012-10-31: 4; 2012-11-01: 4; 2012-11-02: 4; 2012-11-05: 4; 2012-11-06: 4; 2012-11-07: 4; 2012-11-08: 4
EC2200 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 4 | 194 | 194 | 0% | 2012-02-10 | 2012-11-08 | 209 | 896 | At Completion Labor Units | 2012-02-10: 5; 2012-02-13: 5; 2012-02-14: 5; 2012-02-15: 5; 2012-02-16: 5; 2012-02-17: 5; 2012-02-20: 5; 2012-02-21: 5; 2012-02-22: 5; 2012-02-23: 5; 2012-02-24: 5; 2012-02-27: 5; 2012-02-28: 5; 2012-02-29: 5; 2012-03-01: 5; 2012-03-02: 5; 2012-03-05: 5; 2012-03-06: 5; 2012-03-07: 5; 2012-03-08: 5; 2012-03-09: 5; 2012-03-12: 5; 2012-03-13: 5; 2012-03-14: 5; 2012-03-15: 5; 2012-03-16: 5; 2012-03-19: 5; 2012-03-20: 5; 2012-03-21: 5; 2012-03-22: 5; 2012-03-23: 5; 2012-03-26: 5; 2012-03-27: 5; 2012-03-28: 5; 2012-03-29: 5; 2012-03-30: 5; 2012-04-02: 5; 2012-04-03: 5; 2012-04-04: 5; 2012-04-05: 5; 2012-04-06: 5; 2012-04-09: 5; 2012-04-10: 5; 2012-04-11: 5; 2012-04-12: 5; 2012-04-13: 5; 2012-04-16: 5; 2012-04-17: 5; 2012-04-18: 5; 2012-04-19: 5; 2012-04-20: 5; 2012-04-23: 5; 2012-04-24: 5; 2012-04-25: 5; 2012-04-26: 5; 2012-04-27: 5; 2012-04-30: 5; 2012-05-01: 5; 2012-05-02: 5; 2012-05-03: 5; 2012-05-04: 5; 2012-05-07: 5; 2012-05-08: 5; 2012-05-09: 5; 2012-05-10: 5; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4; 2012-07-12: 4; 2012-07-13: 4; 2012-07-16: 4; 2012-07-17: 4; 2012-07-18: 4; 2012-07-19: 4; 2012-07-20: 4; 2012-07-23: 4; 2012-07-24: 4; 2012-07-25: 4; 2012-07-26: 4; 2012-07-27: 4; 2012-07-30: 4; 2012-07-31: 4; 2012-08-01: 4; 2012-08-02: 4; 2012-08-03: 4; 2012-08-06: 4; 2012-08-07: 4; 2012-08-08: 4; 2012-08-09: 4; 2012-08-10: 4; 2012-08-13: 4; 2012-08-14: 4; 2012-08-15: 4; 2012-08-16: 4; 2012-08-17: 4; 2012-08-20: 4; 2012-08-21: 4; 2012-08-22: 4; 2012-08-23: 4; 2012-08-24: 4; 2012-08-27: 4; 2012-08-28: 4; 2012-08-29: 4; 2012-08-30: 4; 2012-08-31: 4; 2012-09-04: 4; 2012-09-05: 4; 2012-09-06: 4; 2012-09-07: 4; 2012-09-10: 4; 2012-09-11: 4; 2012-09-12: 4; 2012-09-13: 4; 2012-09-14: 4; 2012-09-17: 4; 2012-09-18: 4; 2012-09-19: 4; 2012-09-20: 4; 2012-09-21: 4; 2012-09-24: 4; 2012-09-25: 4; 2012-09-26: 4; 2012-09-27: 4; 2012-09-28: 4; 2012-10-01: 4; 2012-10-02: 4; 2012-10-03: 4; 2012-10-04: 4; 2012-10-05: 4; 2012-10-08: 4; 2012-10-09: 4; 2012-10-10: 4; 2012-10-11: 4; 2012-10-12: 4; 2012-10-15: 4; 2012-10-16: 4; 2012-10-17: 4; 2012-10-18: 4; 2012-10-19: 4; 2012-10-22: 4; 2012-10-23: 4; 2012-10-24: 4; 2012-10-25: 4; 2012-10-26: 4; 2012-10-29: 4; 2012-10-30: 4; 2012-10-31: 4; 2012-11-01: 4; 2012-11-02: 4; 2012-11-05: 4; 2012-11-06: 4; 2012-11-07: 4; 2012-11-08: 4; 2012-11-09: 4; 2012-11-12: 4; 2012-11-13: 2
EC2210 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 4 | 194 | 194 | 0% | 2012-02-17 | 2012-11-15 | 209 | 896 | At Completion Labor Units | 2012-02-17: 5; 2012-02-20: 5; 2012-02-21: 5; 2012-02-22: 5; 2012-02-23: 5; 2012-02-24: 5; 2012-02-27: 5; 2012-02-28: 5; 2012-02-29: 5; 2012-03-01: 5; 2012-03-02: 5; 2012-03-05: 5; 2012-03-06: 5; 2012-03-07: 5; 2012-03-08: 5; 2012-03-09: 5; 2012-03-12: 5; 2012-03-13: 5; 2012-03-14: 5; 2012-03-15: 5; 2012-03-16: 5; 2012-03-19: 5; 2012-03-20: 5; 2012-03-21: 5; 2012-03-22: 5; 2012-03-23: 5; 2012-03-26: 5; 2012-03-27: 5; 2012-03-28: 5; 2012-03-29: 5; 2012-03-30: 5; 2012-04-02: 5; 2012-04-03: 5; 2012-04-04: 5; 2012-04-05: 5; 2012-04-06: 5; 2012-04-09: 5; 2012-04-10: 5; 2012-04-11: 5; 2012-04-12: 5; 2012-04-13: 5; 2012-04-16: 5; 2012-04-17: 5; 2012-04-18: 5; 2012-04-19: 5; 2012-04-20: 5; 2012-04-23: 5; 2012-04-24: 5; 2012-04-25: 5; 2012-04-26: 5; 2012-04-27: 5; 2012-04-30: 5; 2012-05-01: 5; 2012-05-02: 5; 2012-05-03: 5; 2012-05-04: 5; 2012-05-07: 5; 2012-05-08: 5; 2012-05-09: 5; 2012-05-10: 5; 2012-05-11: 5; 2012-05-14: 5; 2012-05-15: 5; 2012-05-16: 5; 2012-05-17: 5; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4; 2012-07-12: 4; 2012-07-13: 4; 2012-07-16: 4; 2012-07-17: 4; 2012-07-18: 4; 2012-07-19: 4; 2012-07-20: 4; 2012-07-23: 4; 2012-07-24: 4; 2012-07-25: 4; 2012-07-26: 4; 2012-07-27: 4; 2012-07-30: 4; 2012-07-31: 4; 2012-08-01: 4; 2012-08-02: 4; 2012-08-03: 4; 2012-08-06: 4; 2012-08-07: 4; 2012-08-08: 4; 2012-08-09: 4; 2012-08-10: 4; 2012-08-13: 4; 2012-08-14: 4; 2012-08-15: 4; 2012-08-16: 4; 2012-08-17: 4; 2012-08-20: 4; 2012-08-21: 4; 2012-08-22: 4; 2012-08-23: 4; 2012-08-24: 4; 2012-08-27: 4; 2012-08-28: 4; 2012-08-29: 4; 2012-08-30: 4; 2012-08-31: 4; 2012-09-04: 4; 2012-09-05: 4; 2012-09-06: 4; 2012-09-07: 4; 2012-09-10: 4; 2012-09-11: 4; 2012-09-12: 4; 2012-09-13: 4; 2012-09-14: 4; 2012-09-17: 4; 2012-09-18: 4; 2012-09-19: 4; 2012-09-20: 4; 2012-09-21: 4; 2012-09-24: 4; 2012-09-25: 4; 2012-09-26: 4; 2012-09-27: 4; 2012-09-28: 4; 2012-10-01: 4; 2012-10-02: 4; 2012-10-03: 4; 2012-10-04: 4; 2012-10-05: 4; 2012-10-08: 4; 2012-10-09: 4; 2012-10-10: 4; 2012-10-11: 4; 2012-10-12: 4; 2012-10-15: 4; 2012-10-16: 4; 2012-10-17: 4; 2012-10-18: 4; 2012-10-19: 4; 2012-10-22: 4; 2012-10-23: 4; 2012-10-24: 4; 2012-10-25: 4; 2012-10-26: 4; 2012-10-29: 4; 2012-10-30: 4; 2012-10-31: 4; 2012-11-01: 4; 2012-11-02: 4; 2012-11-05: 4; 2012-11-06: 4; 2012-11-07: 4; 2012-11-08: 4; 2012-11-09: 4; 2012-11-12: 4; 2012-11-13: 4; 2012-11-14: 4; 2012-11-15: 4; 2012-11-16: 4; 2012-11-19: 4; 2012-11-20: 2
EC2410 | 1345006 | 4000 | ACMEGC | Final Inspections and Punchlist | 72 | 72 | 0% | 2012-11-15 | 2013-02-25 | 209 | 456 | At Completion Labor Units | 2012-11-15: 4; 2012-11-16: 7; 2012-11-19: 7; 2012-11-20: 7; 2012-11-21: 7; 2012-11-23: 7; 2012-11-26: 7; 2012-11-27: 7; 2012-11-28: 7; 2012-11-29: 7; 2012-11-30: 7; 2012-12-03: 7; 2012-12-04: 7; 2012-12-05: 7; 2012-12-06: 7; 2012-12-07: 7; 2012-12-10: 7; 2012-12-11: 7; 2012-12-12: 7; 2012-12-13: 7; 2012-12-14: 7; 2012-12-17: 7; 2012-12-18: 7; 2012-12-19: 7; 2012-12-20: 6; 2012-12-21: 6; 2012-12-24: 6; 2012-12-26: 6; 2012-12-27: 6; 2012-12-28: 6; 2012-12-31: 6; 2013-01-02: 6; 2013-01-03: 6; 2013-01-04: 6; 2013-01-07: 6; 2013-01-08: 6; 2013-01-09: 6; 2013-01-10: 6; 2013-01-11: 6; 2013-01-14: 6; 2013-01-15: 6; 2013-01-16: 6; 2013-01-17: 6; 2013-01-18: 6; 2013-01-21: 6; 2013-01-22: 6; 2013-01-23: 6; 2013-01-24: 6; 2013-01-25: 6; 2013-01-28: 6; 2013-01-29: 6; 2013-01-30: 6; 2013-01-31: 6; 2013-02-01: 6; 2013-02-04: 6; 2013-02-05: 6; 2013-02-06: 6; 2013-02-07: 6; 2013-02-08: 6; 2013-02-11: 6; 2013-02-12: 6; 2013-02-13: 6; 2013-02-14: 6; 2013-02-15: 6; 2013-02-18: 6; 2013-02-19: 6; 2013-02-20: 6; 2013-02-21: 6; 2013-02-22: 6; 2013-02-25: 6; 2013-02-26: 6; 2013-02-27: 6; 2013-02-28: 2
EC2040 | 1345006 | 4000 | ACMEGC | Building 1 Elevators Complete | 70 | 70 | 0% | 2012-01-06 | 2012-04-12 | 311 | 768 | At Completion Labor Units | 2012-01-06: 11; 2012-01-09: 11; 2012-01-10: 11; 2012-01-11: 11; 2012-01-12: 11; 2012-01-13: 11; 2012-01-16: 11; 2012-01-17: 11; 2012-01-18: 11; 2012-01-19: 11; 2012-01-20: 11; 2012-01-23: 11; 2012-01-24: 11; 2012-01-25: 11; 2012-01-26: 11; 2012-01-27: 11; 2012-01-30: 11; 2012-01-31: 11; 2012-02-01: 11; 2012-02-02: 11; 2012-02-03: 11; 2012-02-06: 11; 2012-02-07: 11; 2012-02-08: 11; 2012-02-09: 11; 2012-02-10: 11; 2012-02-13: 11; 2012-02-14: 11; 2012-02-15: 11; 2012-02-16: 11; 2012-02-17: 11; 2012-02-20: 11; 2012-02-21: 11; 2012-02-22: 11; 2012-02-23: 11; 2012-02-24: 11; 2012-02-27: 11; 2012-02-28: 11; 2012-02-29: 11; 2012-03-01: 11; 2012-03-02: 11; 2012-03-05: 11; 2012-03-06: 11; 2012-03-07: 11; 2012-03-08: 11; 2012-03-09: 11; 2012-03-12: 11; 2012-03-13: 11; 2012-03-14: 11; 2012-03-15: 11; 2012-03-16: 11; 2012-03-19: 11; 2012-03-20: 11; 2012-03-21: 11; 2012-03-22: 11; 2012-03-23: 11; 2012-03-26: 11; 2012-03-27: 11; 2012-03-28: 11; 2012-03-29: 11; 2012-03-30: 11; 2012-04-02: 11; 2012-04-03: 11; 2012-04-04: 11; 2012-04-05: 11; 2012-04-06: 11; 2012-04-09: 11; 2012-04-10: 11; 2012-04-11: 11; 2012-04-12: 7
EC2070 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 2 | 197 | 197 | 0% | 2012-01-13 | 2012-10-15 | 209 | 896 | At Completion Labor Units | 2012-01-13: 5; 2012-01-16: 5; 2012-01-17: 5; 2012-01-18: 5; 2012-01-19: 5; 2012-01-20: 5; 2012-01-23: 5; 2012-01-24: 5; 2012-01-25: 5; 2012-01-26: 5; 2012-01-27: 5; 2012-01-30: 5; 2012-01-31: 5; 2012-02-01: 5; 2012-02-02: 5; 2012-02-03: 5; 2012-02-06: 5; 2012-02-07: 5; 2012-02-08: 5; 2012-02-09: 5; 2012-02-10: 5; 2012-02-13: 5; 2012-02-14: 5; 2012-02-15: 5; 2012-02-16: 5; 2012-02-17: 5; 2012-02-20: 5; 2012-02-21: 5; 2012-02-22: 5; 2012-02-23: 5; 2012-02-24: 5; 2012-02-27: 5; 2012-02-28: 5; 2012-02-29: 5; 2012-03-01: 5; 2012-03-02: 5; 2012-03-05: 5; 2012-03-06: 5; 2012-03-07: 5; 2012-03-08: 5; 2012-03-09: 5; 2012-03-12: 5; 2012-03-13: 5; 2012-03-14: 5; 2012-03-15: 5; 2012-03-16: 5; 2012-03-19: 5; 2012-03-20: 5; 2012-03-21: 5; 2012-03-22: 5; 2012-03-23: 5; 2012-03-26: 5; 2012-03-27: 5; 2012-03-28: 5; 2012-03-29: 5; 2012-03-30: 5; 2012-04-02: 5; 2012-04-03: 5; 2012-04-04: 5; 2012-04-05: 5; 2012-04-06: 5; 2012-04-09: 5; 2012-04-10: 5; 2012-04-11: 5; 2012-04-12: 5; 2012-04-13: 5; 2012-04-16: 4; 2012-04-17: 4; 2012-04-18: 4; 2012-04-19: 4; 2012-04-20: 4; 2012-04-23: 4; 2012-04-24: 4; 2012-04-25: 4; 2012-04-26: 4; 2012-04-27: 4; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4; 2012-07-12: 4; 2012-07-13: 4; 2012-07-16: 4; 2012-07-17: 4; 2012-07-18: 4; 2012-07-19: 4; 2012-07-20: 4; 2012-07-23: 4; 2012-07-24: 4; 2012-07-25: 4; 2012-07-26: 4; 2012-07-27: 4; 2012-07-30: 4; 2012-07-31: 4; 2012-08-01: 4; 2012-08-02: 4; 2012-08-03: 4; 2012-08-06: 4; 2012-08-07: 4; 2012-08-08: 4; 2012-08-09: 4; 2012-08-10: 4; 2012-08-13: 4; 2012-08-14: 4; 2012-08-15: 4; 2012-08-16: 4; 2012-08-17: 4; 2012-08-20: 4; 2012-08-21: 4; 2012-08-22: 4; 2012-08-23: 4; 2012-08-24: 4; 2012-08-27: 4; 2012-08-28: 4; 2012-08-29: 4; 2012-08-30: 4; 2012-08-31: 4; 2012-09-04: 4; 2012-09-05: 4; 2012-09-06: 4; 2012-09-07: 4; 2012-09-10: 4; 2012-09-11: 4; 2012-09-12: 4; 2012-09-13: 4; 2012-09-14: 4; 2012-09-17: 4; 2012-09-18: 4; 2012-09-19: 4; 2012-09-20: 4; 2012-09-21: 4; 2012-09-24: 4; 2012-09-25: 4; 2012-09-26: 4; 2012-09-27: 4; 2012-09-28: 4; 2012-10-01: 4; 2012-10-02: 4; 2012-10-03: 4; 2012-10-04: 4; 2012-10-05: 4; 2012-10-08: 4; 2012-10-09: 4; 2012-10-10: 4; 2012-10-11: 4; 2012-10-12: 4; 2012-10-15: 4; 2012-10-16: 4; 2012-10-17: 4; 2012-10-18: 4
EC2120 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 2 | 197 | 197 | 0% | 2012-01-20 | 2012-10-22 | 209 | 896 | At Completion Labor Units | 2012-01-20: 5; 2012-01-23: 5; 2012-01-24: 5; 2012-01-25: 5; 2012-01-26: 5; 2012-01-27: 5; 2012-01-30: 5; 2012-01-31: 5; 2012-02-01: 5; 2012-02-02: 5; 2012-02-03: 5; 2012-02-06: 5; 2012-02-07: 5; 2012-02-08: 5; 2012-02-09: 5; 2012-02-10: 5; 2012-02-13: 5; 2012-02-14: 5; 2012-02-15: 5; 2012-02-16: 5; 2012-02-17: 5; 2012-02-20: 5; 2012-02-21: 5; 2012-02-22: 5; 2012-02-23: 5; 2012-02-24: 5; 2012-02-27: 5; 2012-02-28: 5; 2012-02-29: 5; 2012-03-01: 5; 2012-03-02: 5; 2012-03-05: 5; 2012-03-06: 5; 2012-03-07: 5; 2012-03-08: 5; 2012-03-09: 5; 2012-03-12: 5; 2012-03-13: 5; 2012-03-14: 5; 2012-03-15: 5; 2012-03-16: 5; 2012-03-19: 5; 2012-03-20: 5; 2012-03-21: 5; 2012-03-22: 5; 2012-03-23: 5; 2012-03-26: 5; 2012-03-27: 5; 2012-03-28: 5; 2012-03-29: 5; 2012-03-30: 5; 2012-04-02: 5; 2012-04-03: 5; 2012-04-04: 5; 2012-04-05: 5; 2012-04-06: 5; 2012-04-09: 5; 2012-04-10: 5; 2012-04-11: 5; 2012-04-12: 5; 2012-04-13: 5; 2012-04-16: 5; 2012-04-17: 5; 2012-04-18: 5; 2012-04-19: 5; 2012-04-20: 5; 2012-04-23: 4; 2012-04-24: 4; 2012-04-25: 4; 2012-04-26: 4; 2012-04-27: 4; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4; 2012-07-12: 4; 2012-07-13: 4; 2012-07-16: 4; 2012-07-17: 4; 2012-07-18: 4; 2012-07-19: 4; 2012-07-20: 4; 2012-07-23: 4; 2012-07-24: 4; 2012-07-25: 4; 2012-07-26: 4; 2012-07-27: 4; 2012-07-30: 4; 2012-07-31: 4; 2012-08-01: 4; 2012-08-02: 4; 2012-08-03: 4; 2012-08-06: 4; 2012-08-07: 4; 2012-08-08: 4; 2012-08-09: 4; 2012-08-10: 4; 2012-08-13: 4; 2012-08-14: 4; 2012-08-15: 4; 2012-08-16: 4; 2012-08-17: 4; 2012-08-20: 4; 2012-08-21: 4; 2012-08-22: 4; 2012-08-23: 4; 2012-08-24: 4; 2012-08-27: 4; 2012-08-28: 4; 2012-08-29: 4; 2012-08-30: 4; 2012-08-31: 4; 2012-09-04: 4; 2012-09-05: 4; 2012-09-06: 4; 2012-09-07: 4; 2012-09-10: 4; 2012-09-11: 4; 2012-09-12: 4; 2012-09-13: 4; 2012-09-14: 4; 2012-09-17: 4; 2012-09-18: 4; 2012-09-19: 4; 2012-09-20: 4; 2012-09-21: 4; 2012-09-24: 4; 2012-09-25: 4; 2012-09-26: 4; 2012-09-27: 4; 2012-09-28: 4; 2012-10-01: 4; 2012-10-02: 4; 2012-10-03: 4; 2012-10-04: 4; 2012-10-05: 4; 2012-10-08: 4; 2012-10-09: 4; 2012-10-10: 4; 2012-10-11: 4; 2012-10-12: 4; 2012-10-15: 4; 2012-10-16: 4; 2012-10-17: 4; 2012-10-18: 4; 2012-10-19: 4; 2012-10-22: 4; 2012-10-23: 4; 2012-10-24: 4; 2012-10-25: 4
EC2000 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 1 | 202 | 202 | 0% | 2011-12-30 | 2012-10-08 | 209 | 896 | At Completion Labor Units | 2011-12-30: 5; 2012-01-03: 5; 2012-01-04: 5; 2012-01-05: 5; 2012-01-06: 5; 2012-01-09: 5; 2012-01-10: 5; 2012-01-11: 5; 2012-01-12: 5; 2012-01-13: 5; 2012-01-16: 5; 2012-01-17: 5; 2012-01-18: 5; 2012-01-19: 5; 2012-01-20: 5; 2012-01-23: 5; 2012-01-24: 5; 2012-01-25: 5; 2012-01-26: 5; 2012-01-27: 5; 2012-01-30: 5; 2012-01-31: 5; 2012-02-01: 5; 2012-02-02: 5; 2012-02-03: 5; 2012-02-06: 5; 2012-02-07: 5; 2012-02-08: 5; 2012-02-09: 5; 2012-02-10: 5; 2012-02-13: 5; 2012-02-14: 5; 2012-02-15: 5; 2012-02-16: 5; 2012-02-17: 5; 2012-02-20: 5; 2012-02-21: 5; 2012-02-22: 5; 2012-02-23: 5; 2012-02-24: 5; 2012-02-27: 5; 2012-02-28: 5; 2012-02-29: 5; 2012-03-01: 5; 2012-03-02: 5; 2012-03-05: 5; 2012-03-06: 5; 2012-03-07: 5; 2012-03-08: 5; 2012-03-09: 5; 2012-03-12: 5; 2012-03-13: 5; 2012-03-14: 5; 2012-03-15: 5; 2012-03-16: 5; 2012-03-19: 5; 2012-03-20: 5; 2012-03-21: 5; 2012-03-22: 5; 2012-03-23: 5; 2012-03-26: 5; 2012-03-27: 5; 2012-03-28: 5; 2012-03-29: 5; 2012-03-30: 5; 2012-04-02: 5; 2012-04-03: 5; 2012-04-04: 4; 2012-04-05: 4; 2012-04-06: 4; 2012-04-09: 4; 2012-04-10: 4; 2012-04-11: 4; 2012-04-12: 4; 2012-04-13: 4; 2012-04-16: 4; 2012-04-17: 4; 2012-04-18: 4; 2012-04-19: 4; 2012-04-20: 4; 2012-04-23: 4; 2012-04-24: 4; 2012-04-25: 4; 2012-04-26: 4; 2012-04-27: 4; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4; 2012-07-12: 4; 2012-07-13: 4; 2012-07-16: 4; 2012-07-17: 4; 2012-07-18: 4; 2012-07-19: 4; 2012-07-20: 4; 2012-07-23: 4; 2012-07-24: 4; 2012-07-25: 4; 2012-07-26: 4; 2012-07-27: 4; 2012-07-30: 4; 2012-07-31: 4; 2012-08-01: 4; 2012-08-02: 4; 2012-08-03: 4; 2012-08-06: 4; 2012-08-07: 4; 2012-08-08: 4; 2012-08-09: 4; 2012-08-10: 4; 2012-08-13: 4; 2012-08-14: 4; 2012-08-15: 4; 2012-08-16: 4; 2012-08-17: 4; 2012-08-20: 4; 2012-08-21: 4; 2012-08-22: 4; 2012-08-23: 4; 2012-08-24: 4; 2012-08-27: 4; 2012-08-28: 4; 2012-08-29: 4; 2012-08-30: 4; 2012-08-31: 4; 2012-09-04: 4; 2012-09-05: 4; 2012-09-06: 4; 2012-09-07: 4; 2012-09-10: 4; 2012-09-11: 4; 2012-09-12: 4; 2012-09-13: 4; 2012-09-14: 4; 2012-09-17: 4; 2012-09-18: 4; 2012-09-19: 4; 2012-09-20: 4; 2012-09-21: 4; 2012-09-24: 4; 2012-09-25: 4; 2012-09-26: 4; 2012-09-27: 4; 2012-09-28: 4; 2012-10-01: 4; 2012-10-02: 4; 2012-10-03: 4; 2012-10-04: 4; 2012-10-05: 4; 2012-10-08: 4; 2012-10-09: 4; 2012-10-10: 4; 2012-10-11: 4; 2012-10-12: 3
EC2030 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 1 | 202 | 202 | 0% | 2012-01-06 | 2012-10-15 | 209 | 896 | At Completion Labor Units | 2012-01-06: 5; 2012-01-09: 5; 2012-01-10: 5; 2012-01-11: 5; 2012-01-12: 5; 2012-01-13: 5; 2012-01-16: 5; 2012-01-17: 5; 2012-01-18: 5; 2012-01-19: 5; 2012-01-20: 5; 2012-01-23: 5; 2012-01-24: 5; 2012-01-25: 5; 2012-01-26: 5; 2012-01-27: 5; 2012-01-30: 5; 2012-01-31: 5; 2012-02-01: 5; 2012-02-02: 5; 2012-02-03: 5; 2012-02-06: 5; 2012-02-07: 5; 2012-02-08: 5; 2012-02-09: 5; 2012-02-10: 5; 2012-02-13: 5; 2012-02-14: 5; 2012-02-15: 5; 2012-02-16: 5; 2012-02-17: 5; 2012-02-20: 5; 2012-02-21: 5; 2012-02-22: 5; 2012-02-23: 5; 2012-02-24: 5; 2012-02-27: 5; 2012-02-28: 5; 2012-02-29: 5; 2012-03-01: 5; 2012-03-02: 5; 2012-03-05: 5; 2012-03-06: 5; 2012-03-07: 5; 2012-03-08: 5; 2012-03-09: 5; 2012-03-12: 5; 2012-03-13: 5; 2012-03-14: 5; 2012-03-15: 5; 2012-03-16: 5; 2012-03-19: 5; 2012-03-20: 5; 2012-03-21: 5; 2012-03-22: 5; 2012-03-23: 5; 2012-03-26: 5; 2012-03-27: 5; 2012-03-28: 5; 2012-03-29: 5; 2012-03-30: 5; 2012-04-02: 5; 2012-04-03: 5; 2012-04-04: 5; 2012-04-05: 5; 2012-04-06: 5; 2012-04-09: 5; 2012-04-10: 4; 2012-04-11: 4; 2012-04-12: 4; 2012-04-13: 4; 2012-04-16: 4; 2012-04-17: 4; 2012-04-18: 4; 2012-04-19: 4; 2012-04-20: 4; 2012-04-23: 4; 2012-04-24: 4; 2012-04-25: 4; 2012-04-26: 4; 2012-04-27: 4; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4; 2012-06-18: 4; 2012-06-19: 4; 2012-06-20: 4; 2012-06-21: 4; 2012-06-22: 4; 2012-06-25: 4; 2012-06-26: 4; 2012-06-27: 4; 2012-06-28: 4; 2012-06-29: 4; 2012-07-02: 4; 2012-07-03: 4; 2012-07-05: 4; 2012-07-06: 4; 2012-07-09: 4; 2012-07-10: 4; 2012-07-11: 4; 2012-07-12: 4; 2012-07-13: 4; 2012-07-16: 4; 2012-07-17: 4; 2012-07-18: 4; 2012-07-19: 4; 2012-07-20: 4; 2012-07-23: 4; 2012-07-24: 4; 2012-07-25: 4; 2012-07-26: 4; 2012-07-27: 4; 2012-07-30: 4; 2012-07-31: 4; 2012-08-01: 4; 2012-08-02: 4; 2012-08-03: 4; 2012-08-06: 4; 2012-08-07: 4; 2012-08-08: 4; 2012-08-09: 4; 2012-08-10: 4; 2012-08-13: 4; 2012-08-14: 4; 2012-08-15: 4; 2012-08-16: 4; 2012-08-17: 4; 2012-08-20: 4; 2012-08-21: 4; 2012-08-22: 4; 2012-08-23: 4; 2012-08-24: 4; 2012-08-27: 4; 2012-08-28: 4; 2012-08-29: 4; 2012-08-30: 4; 2012-08-31: 4; 2012-09-04: 4; 2012-09-05: 4; 2012-09-06: 4; 2012-09-07: 4; 2012-09-10: 4; 2012-09-11: 4; 2012-09-12: 4; 2012-09-13: 4; 2012-09-14: 4; 2012-09-17: 4; 2012-09-18: 4; 2012-09-19: 4; 2012-09-20: 4; 2012-09-21: 4; 2012-09-24: 4; 2012-09-25: 4; 2012-09-26: 4; 2012-09-27: 4; 2012-09-28: 4; 2012-10-01: 4; 2012-10-02: 4; 2012-10-03: 4; 2012-10-04: 4; 2012-10-05: 4; 2012-10-08: 4; 2012-10-09: 4; 2012-10-10: 4; 2012-10-11: 4; 2012-10-12: 4; 2012-10-15: 4; 2012-10-16: 4; 2012-10-17: 4; 2012-10-18: 3
EC2330 | 1345006 | 5000 | STDPAV | Courtyard Walks and Amenities | 91 | 91 | 0% | 2012-08-24 | 2012-12-31 | 249 | 720 | At Completion Labor Units | 2012-08-24: 3; 2012-08-27: 8; 2012-08-28: 8; 2012-08-29: 8; 2012-08-30: 8; 2012-08-31: 8; 2012-09-04: 8; 2012-09-05: 8; 2012-09-06: 8; 2012-09-07: 8; 2012-09-10: 8; 2012-09-11: 8; 2012-09-12: 8; 2012-09-13: 8; 2012-09-14: 8; 2012-09-17: 8; 2012-09-18: 8; 2012-09-19: 8; 2012-09-20: 8; 2012-09-21: 8; 2012-09-24: 8; 2012-09-25: 8; 2012-09-26: 8; 2012-09-27: 8; 2012-09-28: 8; 2012-10-01: 8; 2012-10-02: 8; 2012-10-03: 8; 2012-10-04: 8; 2012-10-05: 8; 2012-10-08: 8; 2012-10-09: 8; 2012-10-10: 8; 2012-10-11: 8; 2012-10-12: 8; 2012-10-15: 8; 2012-10-16: 8; 2012-10-17: 8; 2012-10-18: 8; 2012-10-19: 8; 2012-10-22: 8; 2012-10-23: 8; 2012-10-24: 8; 2012-10-25: 8; 2012-10-26: 8; 2012-10-29: 8; 2012-10-30: 8; 2012-10-31: 8; 2012-11-01: 8; 2012-11-02: 8; 2012-11-05: 8; 2012-11-06: 8; 2012-11-07: 8; 2012-11-08: 8; 2012-11-09: 8; 2012-11-12: 8; 2012-11-13: 8; 2012-11-14: 8; 2012-11-15: 8; 2012-11-16: 8; 2012-11-19: 8; 2012-11-20: 8; 2012-11-21: 8; 2012-11-23: 8; 2012-11-26: 8; 2012-11-27: 8; 2012-11-28: 8; 2012-11-29: 8; 2012-11-30: 8; 2012-12-03: 8; 2012-12-04: 8; 2012-12-05: 8; 2012-12-06: 8; 2012-12-07: 8; 2012-12-10: 8; 2012-12-11: 8; 2012-12-12: 8; 2012-12-13: 8; 2012-12-14: 8; 2012-12-17: 8; 2012-12-18: 8; 2012-12-19: 8; 2012-12-20: 8; 2012-12-21: 8; 2012-12-24: 8; 2012-12-26: 8; 2012-12-27: 8; 2012-12-28: 8; 2012-12-31: 8; 2013-01-02: 8; 2013-01-03: 8; 2013-01-04: 6
EC1020 | 1345006 | 6000 |  | Start Garage | 0 | 0 | 0% | 2010-11-01 |  | 391 | 0 | At Completion Labor Units
EC1030 | 1345006 | 6000 | STEEL | Shop Drawings, Review and Approval | 72 | 72 | 0% | 2010-11-01 | 2011-02-08 | 391 | 614 | At Completion Labor Units | 2010-11-01: 9; 2010-11-02: 9; 2010-11-03: 9; 2010-11-04: 9; 2010-11-05: 9; 2010-11-08: 9; 2010-11-09: 9; 2010-11-10: 9; 2010-11-11: 9; 2010-11-12: 9; 2010-11-15: 9; 2010-11-16: 9; 2010-11-17: 9; 2010-11-18: 9; 2010-11-19: 9; 2010-11-22: 9; 2010-11-23: 9; 2010-11-24: 9; 2010-11-26: 9; 2010-11-29: 9; 2010-11-30: 9; 2010-12-01: 9; 2010-12-02: 9; 2010-12-03: 9; 2010-12-06: 9; 2010-12-07: 9; 2010-12-08: 9; 2010-12-09: 9; 2010-12-10: 9; 2010-12-13: 9; 2010-12-14: 9; 2010-12-15: 9; 2010-12-16: 9; 2010-12-17: 9; 2010-12-20: 9; 2010-12-21: 9; 2010-12-22: 9; 2010-12-23: 9; 2010-12-27: 9; 2010-12-28: 9; 2010-12-29: 9; 2010-12-30: 9; 2011-01-03: 9; 2011-01-04: 9; 2011-01-05: 9; 2011-01-06: 9; 2011-01-07: 9; 2011-01-10: 9; 2011-01-11: 9; 2011-01-12: 9; 2011-01-13: 9; 2011-01-14: 9; 2011-01-17: 9; 2011-01-18: 9; 2011-01-19: 9; 2011-01-20: 9; 2011-01-21: 9; 2011-01-24: 9; 2011-01-25: 9; 2011-01-26: 9; 2011-01-27: 9; 2011-01-28: 9; 2011-01-31: 9; 2011-02-01: 9; 2011-02-02: 9; 2011-02-03: 9; 2011-02-04: 9; 2011-02-07: 9; 2011-02-08: 9; 2011-02-09: 7; 2011-02-10: 4; 2011-02-11: 4
EC1180 | 1345006 | 6000 | STEEL | Fab & Delivery | 72 | 72 | 0% | 2011-02-09 | 2011-05-19 | 391 | 461 | At Completion Labor Units | 2011-02-09: 6; 2011-02-10: 6; 2011-02-11: 6; 2011-02-14: 6; 2011-02-15: 6; 2011-02-16: 6; 2011-02-17: 6; 2011-02-18: 6; 2011-02-21: 6; 2011-02-22: 6; 2011-02-23: 6; 2011-02-24: 6; 2011-02-25: 6; 2011-02-28: 6; 2011-03-01: 6; 2011-03-02: 6; 2011-03-03: 6; 2011-03-04: 6; 2011-03-07: 6; 2011-03-08: 6; 2011-03-09: 6; 2011-03-10: 6; 2011-03-11: 6; 2011-03-14: 6; 2011-03-15: 6; 2011-03-16: 6; 2011-03-17: 6; 2011-03-18: 6; 2011-03-21: 6; 2011-03-22: 6; 2011-03-23: 6; 2011-03-24: 6; 2011-03-25: 6; 2011-03-28: 6; 2011-03-29: 6; 2011-03-30: 6; 2011-03-31: 6; 2011-04-01: 6; 2011-04-04: 6; 2011-04-05: 6; 2011-04-06: 6; 2011-04-07: 6; 2011-04-08: 6; 2011-04-11: 6; 2011-04-12: 6; 2011-04-13: 6; 2011-04-14: 6; 2011-04-15: 6; 2011-04-18: 6; 2011-04-19: 6; 2011-04-20: 6; 2011-04-21: 6; 2011-04-22: 6; 2011-04-25: 6; 2011-04-26: 6; 2011-04-27: 6; 2011-04-28: 6; 2011-04-29: 6; 2011-05-02: 6; 2011-05-03: 6; 2011-05-04: 6; 2011-05-05: 6; 2011-05-06: 6; 2011-05-09: 6; 2011-05-10: 6; 2011-05-11: 6; 2011-05-12: 6; 2011-05-13: 6; 2011-05-16: 6; 2011-05-17: 6; 2011-05-18: 6; 2011-05-19: 6
EC1280 | 1345006 | 6000 | STEEL | Erect Precast Structure | 96 | 96 | 0% | 2011-05-20 | 2011-09-30 | 391 | 576 | At Completion Labor Units | 2011-05-20: 6; 2011-05-23: 6; 2011-05-24: 6; 2011-05-25: 6; 2011-05-26: 6; 2011-05-27: 6; 2011-05-31: 6; 2011-06-01: 6; 2011-06-02: 6; 2011-06-03: 6; 2011-06-06: 6; 2011-06-07: 6; 2011-06-08: 6; 2011-06-09: 6; 2011-06-10: 6; 2011-06-13: 6; 2011-06-14: 6; 2011-06-15: 6; 2011-06-16: 6; 2011-06-17: 6; 2011-06-20: 6; 2011-06-21: 6; 2011-06-22: 6; 2011-06-23: 6; 2011-06-24: 6; 2011-06-27: 6; 2011-06-28: 6; 2011-06-29: 6; 2011-06-30: 6; 2011-07-01: 6; 2011-07-05: 6; 2011-07-06: 6; 2011-07-07: 6; 2011-07-08: 6; 2011-07-11: 6; 2011-07-12: 6; 2011-07-13: 6; 2011-07-14: 6; 2011-07-15: 6; 2011-07-18: 6; 2011-07-19: 6; 2011-07-20: 6; 2011-07-21: 6; 2011-07-22: 6; 2011-07-25: 6; 2011-07-26: 6; 2011-07-27: 6; 2011-07-28: 6; 2011-07-29: 6; 2011-08-01: 6; 2011-08-02: 6; 2011-08-03: 6; 2011-08-04: 6; 2011-08-05: 6; 2011-08-08: 6; 2011-08-09: 6; 2011-08-10: 6; 2011-08-11: 6; 2011-08-12: 6; 2011-08-15: 6; 2011-08-16: 6; 2011-08-17: 6; 2011-08-18: 6; 2011-08-19: 6; 2011-08-22: 6; 2011-08-23: 6; 2011-08-24: 6; 2011-08-25: 6; 2011-08-26: 6; 2011-08-29: 6; 2011-08-30: 6; 2011-08-31: 6; 2011-09-01: 6; 2011-09-02: 6; 2011-09-06: 6; 2011-09-07: 6; 2011-09-08: 6; 2011-09-09: 6; 2011-09-12: 6; 2011-09-13: 6; 2011-09-14: 6; 2011-09-15: 6; 2011-09-16: 6; 2011-09-19: 6; 2011-09-20: 6; 2011-09-21: 6; 2011-09-22: 6; 2011-09-23: 6; 2011-09-26: 6; 2011-09-27: 3; 2011-09-28: 3; 2011-09-29: 3; 2011-09-30: 3; 2011-10-03: 3; 2011-10-04: 3; 2011-10-05: 3
EC1590 | 1345006 | 6000 | STEEL | Fire Protection and Lighting | 72 | 72 | 0% | 2011-10-03 | 2012-01-10 | 391 | 480 | At Completion Labor Units | 2011-10-03: 7; 2011-10-04: 7; 2011-10-05: 7; 2011-10-06: 7; 2011-10-07: 7; 2011-10-10: 7; 2011-10-11: 7; 2011-10-12: 7; 2011-10-13: 7; 2011-10-14: 7; 2011-10-17: 7; 2011-10-18: 7; 2011-10-19: 7; 2011-10-20: 7; 2011-10-21: 7; 2011-10-24: 7; 2011-10-25: 7; 2011-10-26: 7; 2011-10-27: 7; 2011-10-28: 7; 2011-10-31: 7; 2011-11-01: 7; 2011-11-02: 7; 2011-11-03: 7; 2011-11-04: 7; 2011-11-07: 7; 2011-11-08: 7; 2011-11-09: 7; 2011-11-10: 7; 2011-11-11: 7; 2011-11-14: 7; 2011-11-15: 7; 2011-11-16: 7; 2011-11-17: 7; 2011-11-18: 7; 2011-11-21: 7; 2011-11-22: 7; 2011-11-23: 7; 2011-11-25: 7; 2011-11-28: 7; 2011-11-29: 7; 2011-11-30: 7; 2011-12-01: 7; 2011-12-02: 7; 2011-12-05: 7; 2011-12-06: 7; 2011-12-07: 7; 2011-12-08: 7; 2011-12-09: 7; 2011-12-12: 7; 2011-12-13: 7; 2011-12-14: 7; 2011-12-15: 7; 2011-12-16: 7; 2011-12-19: 7; 2011-12-20: 7; 2011-12-21: 7; 2011-12-22: 7; 2011-12-23: 7; 2011-12-27: 7; 2011-12-28: 7; 2011-12-29: 7; 2011-12-30: 7; 2012-01-03: 7; 2012-01-04: 7; 2012-01-05: 7; 2012-01-06: 7; 2012-01-09: 7; 2012-01-10: 7; 2012-01-11: 5; 2012-01-12: 2; 2012-01-13: 2
EC1680 | 1345006 | 6000 | STEEL | Finishes and Striping | 84 | 84 | 0% | 2011-12-14 | 2012-04-09 | 391 | 768 | At Completion Labor Units | 2011-12-14: 9; 2011-12-15: 9; 2011-12-16: 9; 2011-12-19: 9; 2011-12-20: 9; 2011-12-21: 9; 2011-12-22: 9; 2011-12-23: 9; 2011-12-27: 9; 2011-12-28: 9; 2011-12-29: 9; 2011-12-30: 9; 2012-01-03: 9; 2012-01-04: 9; 2012-01-05: 9; 2012-01-06: 9; 2012-01-09: 9; 2012-01-10: 9; 2012-01-11: 9; 2012-01-12: 9; 2012-01-13: 9; 2012-01-16: 9; 2012-01-17: 9; 2012-01-18: 9; 2012-01-19: 9; 2012-01-20: 9; 2012-01-23: 9; 2012-01-24: 9; 2012-01-25: 9; 2012-01-26: 9; 2012-01-27: 9; 2012-01-30: 9; 2012-01-31: 9; 2012-02-01: 9; 2012-02-02: 9; 2012-02-03: 9; 2012-02-06: 9; 2012-02-07: 9; 2012-02-08: 9; 2012-02-09: 9; 2012-02-10: 9; 2012-02-13: 9; 2012-02-14: 9; 2012-02-15: 9; 2012-02-16: 9; 2012-02-17: 9; 2012-02-20: 9; 2012-02-21: 9; 2012-02-22: 9; 2012-02-23: 9; 2012-02-24: 9; 2012-02-27: 9; 2012-02-28: 9; 2012-02-29: 9; 2012-03-01: 9; 2012-03-02: 9; 2012-03-05: 9; 2012-03-06: 9; 2012-03-07: 9; 2012-03-08: 9; 2012-03-09: 9; 2012-03-12: 9; 2012-03-13: 9; 2012-03-14: 9; 2012-03-15: 9; 2012-03-16: 9; 2012-03-19: 9; 2012-03-20: 9; 2012-03-21: 9; 2012-03-22: 9; 2012-03-23: 9; 2012-03-26: 9; 2012-03-27: 9; 2012-03-28: 9; 2012-03-29: 9; 2012-03-30: 9; 2012-04-02: 9; 2012-04-03: 9; 2012-04-04: 9; 2012-04-05: 9; 2012-04-06: 9; 2012-04-09: 9; 2012-04-10: 9; 2012-04-11: 9
EC2190 | 1345006 | 6000 |  | Complete Garage | 0 | 0 | 0% |  | 2012-06-14 | 391 | 0 | At Completion Labor Units
EC2060 | 1345006 | 6000 | STEEL | Punch List Garage | 48 | 48 | 0% | 2012-04-10 | 2012-06-14 | 391 | 192 | At Completion Labor Units | 2012-04-10: 4; 2012-04-11: 4; 2012-04-12: 4; 2012-04-13: 4; 2012-04-16: 4; 2012-04-17: 4; 2012-04-18: 4; 2012-04-19: 4; 2012-04-20: 4; 2012-04-23: 4; 2012-04-24: 4; 2012-04-25: 4; 2012-04-26: 4; 2012-04-27: 4; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4
EC2180 | 1345006 | 6000 |  | Complete Garage 2 | 0 | 0 | 0% |  | 2012-06-14 | 391 | 0 | At Completion Labor Units
EC2340 | 1345006 | 7000 | STDPAV | Curbs & Paving | 79 | 79 | 0% | 2012-08-24 | 2012-12-13 | 261 | 634 | At Completion Labor Units | 2012-08-24: 3; 2012-08-27: 8; 2012-08-28: 8; 2012-08-29: 8; 2012-08-30: 8; 2012-08-31: 8; 2012-09-04: 8; 2012-09-05: 8; 2012-09-06: 8; 2012-09-07: 8; 2012-09-10: 8; 2012-09-11: 8; 2012-09-12: 8; 2012-09-13: 8; 2012-09-14: 8; 2012-09-17: 8; 2012-09-18: 8; 2012-09-19: 8; 2012-09-20: 8; 2012-09-21: 8; 2012-09-24: 8; 2012-09-25: 8; 2012-09-26: 8; 2012-09-27: 8; 2012-09-28: 8; 2012-10-01: 8; 2012-10-02: 8; 2012-10-03: 8; 2012-10-04: 8; 2012-10-05: 8; 2012-10-08: 8; 2012-10-09: 8; 2012-10-10: 8; 2012-10-11: 8; 2012-10-12: 8; 2012-10-15: 8; 2012-10-16: 8; 2012-10-17: 8; 2012-10-18: 8; 2012-10-19: 8; 2012-10-22: 8; 2012-10-23: 8; 2012-10-24: 8; 2012-10-25: 8; 2012-10-26: 8; 2012-10-29: 8; 2012-10-30: 8; 2012-10-31: 8; 2012-11-01: 8; 2012-11-02: 8; 2012-11-05: 8; 2012-11-06: 8; 2012-11-07: 8; 2012-11-08: 8; 2012-11-09: 8; 2012-11-12: 8; 2012-11-13: 8; 2012-11-14: 8; 2012-11-15: 8; 2012-11-16: 8; 2012-11-19: 8; 2012-11-20: 8; 2012-11-21: 8; 2012-11-23: 8; 2012-11-26: 8; 2012-11-27: 8; 2012-11-28: 8; 2012-11-29: 8; 2012-11-30: 8; 2012-12-03: 8; 2012-12-04: 8; 2012-12-05: 8; 2012-12-06: 8; 2012-12-07: 8; 2012-12-10: 8; 2012-12-11: 8; 2012-12-12: 8; 2012-12-13: 8; 2012-12-14: 8; 2012-12-17: 6
EC1610 | 1345006 | 7000 | STDPAV | Curbs & Paving | 58 | 58 | 0% | 2011-10-03 | 2011-12-21 | 517 | 461 | At Completion Labor Units | 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 8; 2011-10-28: 8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 8; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 8; 2011-11-29: 8; 2011-11-30: 8; 2011-12-01: 8; 2011-12-02: 8; 2011-12-05: 8; 2011-12-06: 8; 2011-12-07: 8; 2011-12-08: 8; 2011-12-09: 8; 2011-12-12: 8; 2011-12-13: 8; 2011-12-14: 8; 2011-12-15: 8; 2011-12-16: 8; 2011-12-19: 8; 2011-12-20: 8; 2011-12-21: 8; 2011-12-22: 5
EC1000 | 1345006 | 7000 | STDPAV | Curbing | 72 | 72 | 0% | 2010-11-01 | 2011-02-08 | 622 | 576 | At Completion Labor Units | 2010-11-01: 8; 2010-11-02: 8; 2010-11-03: 8; 2010-11-04: 8; 2010-11-05: 8; 2010-11-08: 8; 2010-11-09: 8; 2010-11-10: 8; 2010-11-11: 8; 2010-11-12: 8; 2010-11-15: 8; 2010-11-16: 8; 2010-11-17: 8; 2010-11-18: 8; 2010-11-19: 8; 2010-11-22: 8; 2010-11-23: 8; 2010-11-24: 8; 2010-11-26: 8; 2010-11-29: 8; 2010-11-30: 8; 2010-12-01: 8; 2010-12-02: 8; 2010-12-03: 8; 2010-12-06: 8; 2010-12-07: 8; 2010-12-08: 8; 2010-12-09: 8; 2010-12-10: 8; 2010-12-13: 8; 2010-12-14: 8; 2010-12-15: 8; 2010-12-16: 8; 2010-12-17: 8; 2010-12-20: 8; 2010-12-21: 8; 2010-12-22: 8; 2010-12-23: 8; 2010-12-27: 8; 2010-12-28: 8; 2010-12-29: 8; 2010-12-30: 8; 2011-01-03: 8; 2011-01-04: 8; 2011-01-05: 8; 2011-01-06: 8; 2011-01-07: 8; 2011-01-10: 8; 2011-01-11: 8; 2011-01-12: 8; 2011-01-13: 8; 2011-01-14: 8; 2011-01-17: 8; 2011-01-18: 8; 2011-01-19: 8; 2011-01-20: 8; 2011-01-21: 8; 2011-01-24: 8; 2011-01-25: 8; 2011-01-26: 8; 2011-01-27: 8; 2011-01-28: 8; 2011-01-31: 8; 2011-02-01: 8; 2011-02-02: 8; 2011-02-03: 8; 2011-02-04: 8; 2011-02-07: 8; 2011-02-08: 8; 2011-02-09: 8; 2011-02-10: 8; 2011-02-11: 8
EC2260 | 1345006 | 7000 | STDPAV | Entry Feature/Sign Wall | 103 | 103 | 0% | 2012-05-28 | 2012-10-18 | 301 | 826 | At Completion Labor Units | 2012-05-29: 8; 2012-05-30: 8; 2012-05-31: 8; 2012-06-01: 8; 2012-06-04: 8; 2012-06-05: 8; 2012-06-06: 8; 2012-06-07: 8; 2012-06-08: 8; 2012-06-11: 8; 2012-06-12: 8; 2012-06-13: 8; 2012-06-14: 8; 2012-06-15: 8; 2012-06-18: 8; 2012-06-19: 8; 2012-06-20: 8; 2012-06-21: 8; 2012-06-22: 8; 2012-06-25: 8; 2012-06-26: 8; 2012-06-27: 8; 2012-06-28: 8; 2012-06-29: 8; 2012-07-02: 8; 2012-07-03: 8; 2012-07-05: 8; 2012-07-06: 8; 2012-07-09: 8; 2012-07-10: 8; 2012-07-11: 8; 2012-07-12: 8; 2012-07-13: 8; 2012-07-16: 8; 2012-07-17: 8; 2012-07-18: 8; 2012-07-19: 8; 2012-07-20: 8; 2012-07-23: 8; 2012-07-24: 8; 2012-07-25: 8; 2012-07-26: 8; 2012-07-27: 8; 2012-07-30: 8; 2012-07-31: 8; 2012-08-01: 8; 2012-08-02: 8; 2012-08-03: 8; 2012-08-06: 8; 2012-08-07: 8; 2012-08-08: 8; 2012-08-09: 8; 2012-08-10: 8; 2012-08-13: 8; 2012-08-14: 8; 2012-08-15: 8; 2012-08-16: 8; 2012-08-17: 8; 2012-08-20: 8; 2012-08-21: 8; 2012-08-22: 8; 2012-08-23: 8; 2012-08-24: 8; 2012-08-27: 8; 2012-08-28: 8; 2012-08-29: 8; 2012-08-30: 8; 2012-08-31: 8; 2012-09-04: 8; 2012-09-05: 8; 2012-09-06: 8; 2012-09-07: 8; 2012-09-10: 8; 2012-09-11: 8; 2012-09-12: 8; 2012-09-13: 8; 2012-09-14: 8; 2012-09-17: 8; 2012-09-18: 8; 2012-09-19: 8; 2012-09-20: 8; 2012-09-21: 8; 2012-09-24: 8; 2012-09-25: 8; 2012-09-26: 8; 2012-09-27: 8; 2012-09-28: 8; 2012-10-01: 8; 2012-10-02: 8; 2012-10-03: 8; 2012-10-04: 8; 2012-10-05: 8; 2012-10-08: 8; 2012-10-09: 8; 2012-10-10: 8; 2012-10-11: 8; 2012-10-12: 8; 2012-10-15: 8; 2012-10-16: 8; 2012-10-17: 8; 2012-10-18: 8; 2012-10-19: 8; 2012-10-22: 8; 2012-10-23: 2
EC2250 | 1345006 | 7000 | STDPAV | Fountain/Water Feature | 115 | 115 | 0% | 2012-05-22 | 2012-10-30 | 293 | 922 | At Completion Labor Units | 2012-05-22: 8; 2012-05-23: 8; 2012-05-24: 8; 2012-05-25: 8; 2012-05-29: 8; 2012-05-30: 8; 2012-05-31: 8; 2012-06-01: 8; 2012-06-04: 8; 2012-06-05: 8; 2012-06-06: 8; 2012-06-07: 8; 2012-06-08: 8; 2012-06-11: 8; 2012-06-12: 8; 2012-06-13: 8; 2012-06-14: 8; 2012-06-15: 8; 2012-06-18: 8; 2012-06-19: 8; 2012-06-20: 8; 2012-06-21: 8; 2012-06-22: 8; 2012-06-25: 8; 2012-06-26: 8; 2012-06-27: 8; 2012-06-28: 8; 2012-06-29: 8; 2012-07-02: 8; 2012-07-03: 8; 2012-07-05: 8; 2012-07-06: 8; 2012-07-09: 8; 2012-07-10: 8; 2012-07-11: 8; 2012-07-12: 8; 2012-07-13: 8; 2012-07-16: 8; 2012-07-17: 8; 2012-07-18: 8; 2012-07-19: 8; 2012-07-20: 8; 2012-07-23: 8; 2012-07-24: 8; 2012-07-25: 8; 2012-07-26: 8; 2012-07-27: 8; 2012-07-30: 8; 2012-07-31: 8; 2012-08-01: 8; 2012-08-02: 8; 2012-08-03: 8; 2012-08-06: 8; 2012-08-07: 8; 2012-08-08: 8; 2012-08-09: 8; 2012-08-10: 8; 2012-08-13: 8; 2012-08-14: 8; 2012-08-15: 8; 2012-08-16: 8; 2012-08-17: 8; 2012-08-20: 8; 2012-08-21: 8; 2012-08-22: 8; 2012-08-23: 8; 2012-08-24: 8; 2012-08-27: 8; 2012-08-28: 8; 2012-08-29: 8; 2012-08-30: 8; 2012-08-31: 8; 2012-09-04: 8; 2012-09-05: 8; 2012-09-06: 8; 2012-09-07: 8; 2012-09-10: 8; 2012-09-11: 8; 2012-09-12: 8; 2012-09-13: 8; 2012-09-14: 8; 2012-09-17: 8; 2012-09-18: 8; 2012-09-19: 8; 2012-09-20: 8; 2012-09-21: 8; 2012-09-24: 8; 2012-09-25: 8; 2012-09-26: 8; 2012-09-27: 8; 2012-09-28: 8; 2012-10-01: 8; 2012-10-02: 8; 2012-10-03: 8; 2012-10-04: 8; 2012-10-05: 8; 2012-10-08: 8; 2012-10-09: 8; 2012-10-10: 8; 2012-10-11: 8; 2012-10-12: 8; 2012-10-15: 8; 2012-10-16: 8; 2012-10-17: 8; 2012-10-18: 8; 2012-10-19: 8; 2012-10-22: 8; 2012-10-23: 8; 2012-10-24: 8; 2012-10-25: 8; 2012-10-26: 8; 2012-10-29: 8; 2012-10-30: 8; 2012-10-31: 8; 2012-11-01: 8; 2012-11-02: 2
EC1270 | 1345006 | 7000 | STDPAV | Finish Paving, Striping and Signs | 48 | 48 | 0% | 2011-05-20 | 2011-07-27 | 622 | 384 | At Completion Labor Units | 2011-05-20: 5; 2011-05-23: 8; 2011-05-24: 8; 2011-05-25: 8; 2011-05-26: 8; 2011-05-27: 8; 2011-05-31: 8; 2011-06-01: 8; 2011-06-02: 8; 2011-06-03: 8; 2011-06-06: 8; 2011-06-07: 8; 2011-06-08: 8; 2011-06-09: 8; 2011-06-10: 8; 2011-06-13: 8; 2011-06-14: 8; 2011-06-15: 8; 2011-06-16: 8; 2011-06-17: 8; 2011-06-20: 8; 2011-06-21: 8; 2011-06-22: 8; 2011-06-23: 8; 2011-06-24: 8; 2011-06-27: 8; 2011-06-28: 8; 2011-06-29: 8; 2011-06-30: 8; 2011-07-01: 8; 2011-07-05: 8; 2011-07-06: 8; 2011-07-07: 8; 2011-07-08: 8; 2011-07-11: 8; 2011-07-12: 8; 2011-07-13: 8; 2011-07-14: 8; 2011-07-15: 8; 2011-07-18: 8; 2011-07-19: 8; 2011-07-20: 8; 2011-07-21: 8; 2011-07-22: 8; 2011-07-25: 8; 2011-07-26: 8; 2011-07-27: 8; 2011-07-28: 8; 2011-07-29: 3
EC1130 | 1345006 | 7000 | STDPAV | Walkways | 67 | 67 | 0% | 2010-11-15 | 2011-02-16 | 622 | 538 | At Completion Labor Units | 2010-11-15: 8; 2010-11-16: 8; 2010-11-17: 8; 2010-11-18: 8; 2010-11-19: 8; 2010-11-22: 8; 2010-11-23: 8; 2010-11-24: 8; 2010-11-26: 8; 2010-11-29: 8; 2010-11-30: 8; 2010-12-01: 8; 2010-12-02: 8; 2010-12-03: 8; 2010-12-06: 8; 2010-12-07: 8; 2010-12-08: 8; 2010-12-09: 8; 2010-12-10: 8; 2010-12-13: 8; 2010-12-14: 8; 2010-12-15: 8; 2010-12-16: 8; 2010-12-17: 8; 2010-12-20: 8; 2010-12-21: 8; 2010-12-22: 8; 2010-12-23: 8; 2010-12-27: 8; 2010-12-28: 8; 2010-12-29: 8; 2010-12-30: 8; 2011-01-03: 8; 2011-01-04: 8; 2011-01-05: 8; 2011-01-06: 8; 2011-01-07: 8; 2011-01-10: 8; 2011-01-11: 8; 2011-01-12: 8; 2011-01-13: 8; 2011-01-14: 8; 2011-01-17: 8; 2011-01-18: 8; 2011-01-19: 8; 2011-01-20: 8; 2011-01-21: 8; 2011-01-24: 8; 2011-01-25: 8; 2011-01-26: 8; 2011-01-27: 8; 2011-01-28: 8; 2011-01-31: 8; 2011-02-01: 8; 2011-02-02: 8; 2011-02-03: 8; 2011-02-04: 8; 2011-02-07: 8; 2011-02-08: 8; 2011-02-09: 8; 2011-02-10: 8; 2011-02-11: 8; 2011-02-14: 8; 2011-02-15: 8; 2011-02-16: 8; 2011-02-17: 8; 2011-02-18: 8; 2011-02-21: 2
EC1200 | 1345006 | 7000 | STDPAV | Roadway Pavers | 67 | 67 | 0% | 2011-02-16 | 2011-05-20 | 622 | 422 | At Completion Labor Units | 2011-02-16: 5; 2011-02-17: 6; 2011-02-18: 6; 2011-02-21: 6; 2011-02-22: 6; 2011-02-23: 6; 2011-02-24: 6; 2011-02-25: 6; 2011-02-28: 6; 2011-03-01: 6; 2011-03-02: 6; 2011-03-03: 6; 2011-03-04: 6; 2011-03-07: 6; 2011-03-08: 6; 2011-03-09: 6; 2011-03-10: 6; 2011-03-11: 6; 2011-03-14: 6; 2011-03-15: 6; 2011-03-16: 6; 2011-03-17: 6; 2011-03-18: 6; 2011-03-21: 6; 2011-03-22: 6; 2011-03-23: 6; 2011-03-24: 6; 2011-03-25: 6; 2011-03-28: 6; 2011-03-29: 6; 2011-03-30: 6; 2011-03-31: 6; 2011-04-01: 6; 2011-04-04: 6; 2011-04-05: 6; 2011-04-06: 6; 2011-04-07: 6; 2011-04-08: 6; 2011-04-11: 6; 2011-04-12: 6; 2011-04-13: 6; 2011-04-14: 6; 2011-04-15: 6; 2011-04-18: 6; 2011-04-19: 6; 2011-04-20: 6; 2011-04-21: 6; 2011-04-22: 6; 2011-04-25: 6; 2011-04-26: 6; 2011-04-27: 6; 2011-04-28: 6; 2011-04-29: 6; 2011-05-02: 6; 2011-05-03: 6; 2011-05-04: 6; 2011-05-05: 6; 2011-05-06: 6; 2011-05-09: 6; 2011-05-10: 6; 2011-05-11: 6; 2011-05-12: 6; 2011-05-13: 6; 2011-05-16: 6; 2011-05-17: 6; 2011-05-18: 6; 2011-05-19: 6; 2011-05-20: 3
EC1100 | 1345006 | 7000 | STDPAV | Storm Drainage Site Work | 72 | 72 | 0% | 2010-11-02 | 2011-02-09 | 36 | 576 | At Completion Labor Units | 2010-11-02: 8; 2010-11-03: 8; 2010-11-04: 8; 2010-11-05: 8; 2010-11-08: 8; 2010-11-09: 8; 2010-11-10: 8; 2010-11-11: 8; 2010-11-12: 8; 2010-11-15: 8; 2010-11-16: 8; 2010-11-17: 8; 2010-11-18: 8; 2010-11-19: 8; 2010-11-22: 8; 2010-11-23: 8; 2010-11-24: 8; 2010-11-26: 8; 2010-11-29: 8; 2010-11-30: 8; 2010-12-01: 8; 2010-12-02: 8; 2010-12-03: 8; 2010-12-06: 8; 2010-12-07: 8; 2010-12-08: 8; 2010-12-09: 8; 2010-12-10: 8; 2010-12-13: 8; 2010-12-14: 8; 2010-12-15: 8; 2010-12-16: 8; 2010-12-17: 8; 2010-12-20: 8; 2010-12-21: 8; 2010-12-22: 8; 2010-12-23: 8; 2010-12-27: 8; 2010-12-28: 8; 2010-12-29: 8; 2010-12-30: 8; 2011-01-03: 8; 2011-01-04: 8; 2011-01-05: 8; 2011-01-06: 8; 2011-01-07: 8; 2011-01-10: 8; 2011-01-11: 8; 2011-01-12: 8; 2011-01-13: 8; 2011-01-14: 8; 2011-01-17: 8; 2011-01-18: 8; 2011-01-19: 8; 2011-01-20: 8; 2011-01-21: 8; 2011-01-24: 8; 2011-01-25: 8; 2011-01-26: 8; 2011-01-27: 8; 2011-01-28: 8; 2011-01-31: 8; 2011-02-01: 8; 2011-02-02: 8; 2011-02-03: 8; 2011-02-04: 8; 2011-02-07: 8; 2011-02-08: 8; 2011-02-09: 8; 2011-02-10: 8; 2011-02-11: 8; 2011-02-14: 8
EC1110 | 1345006 | 7000 | ELECTR | Site Electrical Work & Temp Power | 12 | 12 | 0% | 2010-11-02 | 2010-11-17 | 36 | 96 | At Completion Labor Units | 2010-11-02: 8; 2010-11-03: 8; 2010-11-04: 8; 2010-11-05: 8; 2010-11-08: 8; 2010-11-09: 8; 2010-11-10: 8; 2010-11-11: 8; 2010-11-12: 8; 2010-11-15: 8; 2010-11-16: 8; 2010-11-17: 8
EC1440 | 1345006 | 7000 | ELECTR | Electric to Building 2 Power Vault | 91 | 91 | 0% | 2011-08-19 | 2011-12-26 | 408 | 730 | At Completion Labor Units | 2011-08-19: 2; 2011-08-22: 8; 2011-08-23: 8; 2011-08-24: 8; 2011-08-25: 8; 2011-08-26: 8; 2011-08-29: 8; 2011-08-30: 8; 2011-08-31: 8; 2011-09-01: 8; 2011-09-02: 8; 2011-09-06: 8; 2011-09-07: 8; 2011-09-08: 8; 2011-09-09: 8; 2011-09-12: 8; 2011-09-13: 8; 2011-09-14: 8; 2011-09-15: 8; 2011-09-16: 8; 2011-09-19: 8; 2011-09-20: 8; 2011-09-21: 8; 2011-09-22: 8; 2011-09-23: 8; 2011-09-26: 8; 2011-09-27: 8; 2011-09-28: 8; 2011-09-29: 8; 2011-09-30: 8; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 8; 2011-10-28: 8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 8; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 8; 2011-11-29: 8; 2011-11-30: 8; 2011-12-01: 8; 2011-12-02: 8; 2011-12-05: 8; 2011-12-06: 8; 2011-12-07: 8; 2011-12-08: 8; 2011-12-09: 8; 2011-12-12: 8; 2011-12-13: 8; 2011-12-14: 8; 2011-12-15: 8; 2011-12-16: 8; 2011-12-19: 8; 2011-12-20: 8; 2011-12-21: 8; 2011-12-22: 8; 2011-12-23: 8; 2011-12-27: 8; 2011-12-28: 8; 2011-12-29: 8
EC1040 | 1345006 | 7000 | ELECTR | Electric to Building 4 Power Vault | 72 | 72 | 0% | 2010-11-01 | 2011-02-08 | 743 | 576 | At Completion Labor Units | 2010-11-01: 8; 2010-11-02: 8; 2010-11-03: 8; 2010-11-04: 8; 2010-11-05: 8; 2010-11-08: 8; 2010-11-09: 8; 2010-11-10: 8; 2010-11-11: 8; 2010-11-12: 8; 2010-11-15: 8; 2010-11-16: 8; 2010-11-17: 8; 2010-11-18: 8; 2010-11-19: 8; 2010-11-22: 8; 2010-11-23: 8; 2010-11-24: 8; 2010-11-26: 8; 2010-11-29: 8; 2010-11-30: 8; 2010-12-01: 8; 2010-12-02: 8; 2010-12-03: 8; 2010-12-06: 8; 2010-12-07: 8; 2010-12-08: 8; 2010-12-09: 8; 2010-12-10: 8; 2010-12-13: 8; 2010-12-14: 8; 2010-12-15: 8; 2010-12-16: 8; 2010-12-17: 8; 2010-12-20: 8; 2010-12-21: 8; 2010-12-22: 8; 2010-12-23: 8; 2010-12-27: 8; 2010-12-28: 8; 2010-12-29: 8; 2010-12-30: 8; 2011-01-03: 8; 2011-01-04: 8; 2011-01-05: 8; 2011-01-06: 8; 2011-01-07: 8; 2011-01-10: 8; 2011-01-11: 8; 2011-01-12: 8; 2011-01-13: 8; 2011-01-14: 8; 2011-01-17: 8; 2011-01-18: 8; 2011-01-19: 8; 2011-01-20: 8; 2011-01-21: 8; 2011-01-24: 8; 2011-01-25: 8; 2011-01-26: 8; 2011-01-27: 8; 2011-01-28: 8; 2011-01-31: 8; 2011-02-01: 8; 2011-02-02: 8; 2011-02-03: 8; 2011-02-04: 8; 2011-02-07: 8; 2011-02-08: 8; 2011-02-09: 8; 2011-02-10: 8; 2011-02-11: 8
EC1750 | 1345006 | 7000 | ELECTR | Electric to Building 1 Power Vault | 70 | 70 | 0% | 2011-09-30 | 2012-01-05 | 366 | 557 | At Completion Labor Units | 2011-09-30: 5; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 8; 2011-10-28: 8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 8; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 8; 2011-11-29: 8; 2011-11-30: 8; 2011-12-01: 8; 2011-12-02: 8; 2011-12-05: 8; 2011-12-06: 8; 2011-12-07: 8; 2011-12-08: 8; 2011-12-09: 8; 2011-12-12: 8; 2011-12-13: 8; 2011-12-14: 8; 2011-12-15: 8; 2011-12-16: 8; 2011-12-19: 8; 2011-12-20: 8; 2011-12-21: 8; 2011-12-22: 8; 2011-12-23: 8; 2011-12-27: 8; 2011-12-28: 8; 2011-12-29: 8; 2011-12-30: 8; 2012-01-03: 8; 2012-01-04: 8; 2012-01-05: 8; 2012-01-06: 8; 2012-01-09: 8; 2012-01-10: 8
EC1050 | 1345006 | 7000 | ELECTR | Electric to Building 3 Power Vault | 24 | 24 | 0% | 2010-11-01 | 2010-12-02 | 791 | 192 | At Completion Labor Units | 2010-11-01: 8; 2010-11-02: 8; 2010-11-03: 8; 2010-11-04: 8; 2010-11-05: 8; 2010-11-08: 8; 2010-11-09: 8; 2010-11-10: 8; 2010-11-11: 8; 2010-11-12: 8; 2010-11-15: 8; 2010-11-16: 8; 2010-11-17: 8; 2010-11-18: 8; 2010-11-19: 8; 2010-11-22: 8; 2010-11-23: 8; 2010-11-24: 8; 2010-11-26: 8; 2010-11-29: 8; 2010-11-30: 8; 2010-12-01: 8; 2010-12-02: 8; 2010-12-03: 8
EC2290 | 1345006 | 7000 | STDPAV | Curbs & Paving | 72 | 72 | 0% | 2012-05-28 | 2012-09-04 | 318 | 576 | At Completion Labor Units | 2012-05-29: 8; 2012-05-30: 8; 2012-05-31: 8; 2012-06-01: 8; 2012-06-04: 8; 2012-06-05: 8; 2012-06-06: 8; 2012-06-07: 8; 2012-06-08: 8; 2012-06-11: 8; 2012-06-12: 8; 2012-06-13: 8; 2012-06-14: 8; 2012-06-15: 8; 2012-06-18: 8; 2012-06-19: 8; 2012-06-20: 8; 2012-06-21: 8; 2012-06-22: 8; 2012-06-25: 8; 2012-06-26: 8; 2012-06-27: 8; 2012-06-28: 8; 2012-06-29: 8; 2012-07-02: 8; 2012-07-03: 8; 2012-07-05: 8; 2012-07-06: 8; 2012-07-09: 8; 2012-07-10: 8; 2012-07-11: 8; 2012-07-12: 8; 2012-07-13: 8; 2012-07-16: 8; 2012-07-17: 8; 2012-07-18: 8; 2012-07-19: 8; 2012-07-20: 8; 2012-07-23: 8; 2012-07-24: 8; 2012-07-25: 8; 2012-07-26: 8; 2012-07-27: 8; 2012-07-30: 8; 2012-07-31: 8; 2012-08-01: 8; 2012-08-02: 8; 2012-08-03: 8; 2012-08-06: 8; 2012-08-07: 8; 2012-08-08: 8; 2012-08-09: 8; 2012-08-10: 8; 2012-08-13: 8; 2012-08-14: 8; 2012-08-15: 8; 2012-08-16: 8; 2012-08-17: 8; 2012-08-20: 8; 2012-08-21: 8; 2012-08-22: 8; 2012-08-23: 8; 2012-08-24: 8; 2012-08-27: 8; 2012-08-28: 8; 2012-08-29: 8; 2012-08-30: 8; 2012-08-31: 8; 2012-09-04: 8; 2012-09-05: 8; 2012-09-06: 8; 2012-09-07: 8
EC1600 | 1345006 | 8000 | BRINK | Site Cleanup | 48 | 48 | 0% | 2011-05-18 | 2011-07-22 | 625 | 384 | At Completion Labor Units | 2011-05-18: 8; 2011-05-19: 8; 2011-05-20: 8; 2011-05-23: 8; 2011-05-24: 8; 2011-05-25: 8; 2011-05-26: 8; 2011-05-27: 8; 2011-05-31: 8; 2011-06-01: 8; 2011-06-02: 8; 2011-06-03: 8; 2011-06-06: 8; 2011-06-07: 8; 2011-06-08: 8; 2011-06-09: 8; 2011-06-10: 8; 2011-06-13: 8; 2011-06-14: 8; 2011-06-15: 8; 2011-06-16: 8; 2011-06-17: 8; 2011-06-20: 8; 2011-06-21: 8; 2011-06-22: 8; 2011-06-23: 8; 2011-06-24: 8; 2011-06-27: 8; 2011-06-28: 8; 2011-06-29: 8; 2011-06-30: 8; 2011-07-01: 8; 2011-07-05: 8; 2011-07-06: 8; 2011-07-07: 8; 2011-07-08: 8; 2011-07-11: 8; 2011-07-12: 8; 2011-07-13: 8; 2011-07-14: 8; 2011-07-15: 8; 2011-07-18: 8; 2011-07-19: 8; 2011-07-20: 8; 2011-07-21: 8; 2011-07-22: 8; 2011-07-25: 8; 2011-07-26: 8
EC2360 | 1345006 | 8000 | BRINK | Landscape & Irrigation | 288 | 288 | 0% | 2012-11-06 | 2013-12-13 | 0 | 960 | At Completion Labor Units | 2012-11-06: 2; 2012-11-07: 5; 2012-11-08: 5; 2012-11-09: 5; 2012-11-12: 5; 2012-11-13: 5; 2012-11-14: 5; 2012-11-15: 5; 2012-11-16: 5; 2012-11-19: 5; 2012-11-20: 5; 2012-11-21: 5; 2012-11-23: 5; 2012-11-26: 5; 2012-11-27: 5; 2012-11-28: 5; 2012-11-29: 5; 2012-11-30: 5; 2012-12-03: 5; 2012-12-04: 5; 2012-12-05: 5; 2012-12-06: 5; 2012-12-07: 5; 2012-12-10: 5; 2012-12-11: 5; 2012-12-12: 5; 2012-12-13: 5; 2012-12-14: 5; 2012-12-17: 5; 2012-12-18: 5; 2012-12-19: 5; 2012-12-20: 5; 2012-12-21: 5; 2012-12-24: 5; 2012-12-26: 5; 2012-12-27: 5; 2012-12-28: 5; 2012-12-31: 5; 2013-01-02: 5; 2013-01-03: 5; 2013-01-04: 5; 2013-01-07: 5; 2013-01-08: 5; 2013-01-09: 5; 2013-01-10: 5; 2013-01-11: 5; 2013-01-14: 5; 2013-01-15: 5; 2013-01-16: 5; 2013-01-17: 5; 2013-01-18: 5; 2013-01-21: 5; 2013-01-22: 5; 2013-01-23: 5; 2013-01-24: 5; 2013-01-25: 5; 2013-01-28: 5; 2013-01-29: 5; 2013-01-30: 5; 2013-01-31: 5; 2013-02-01: 5; 2013-02-04: 5; 2013-02-05: 5; 2013-02-06: 5; 2013-02-07: 5; 2013-02-08: 5; 2013-02-11: 5; 2013-02-12: 5; 2013-02-13: 3; 2013-02-14: 3; 2013-02-15: 3; 2013-02-18: 3; 2013-02-19: 3; 2013-02-20: 3; 2013-02-21: 3; 2013-02-22: 3; 2013-02-25: 3; 2013-02-26: 3; 2013-02-27: 3; 2013-02-28: 3; 2013-03-01: 3; 2013-03-04: 3; 2013-03-05: 3; 2013-03-06: 3; 2013-03-07: 3; 2013-03-08: 3; 2013-03-11: 3; 2013-03-12: 3; 2013-03-13: 3; 2013-03-14: 3; 2013-03-15: 3; 2013-03-18: 3; 2013-03-19: 3; 2013-03-20: 3; 2013-03-21: 3; 2013-03-22: 3; 2013-03-25: 3; 2013-03-26: 3; 2013-03-27: 3; 2013-03-28: 3; 2013-03-29: 3; 2013-04-01: 3; 2013-04-02: 3; 2013-04-03: 3; 2013-04-04: 3; 2013-04-05: 3; 2013-04-08: 3; 2013-04-09: 3; 2013-04-10: 3; 2013-04-11: 3; 2013-04-12: 3; 2013-04-15: 3; 2013-04-16: 3; 2013-04-17: 3; 2013-04-18: 3; 2013-04-19: 3; 2013-04-22: 3; 2013-04-23: 3; 2013-04-24: 3; 2013-04-25: 3; 2013-04-26: 3; 2013-04-29: 3; 2013-04-30: 3; 2013-05-01: 3; 2013-05-02: 3; 2013-05-03: 3; 2013-05-06: 3; 2013-05-07: 3; 2013-05-08: 3; 2013-05-09: 3; 2013-05-10: 3; 2013-05-13: 3; 2013-05-14: 3; 2013-05-15: 3; 2013-05-16: 3; 2013-05-17: 3; 2013-05-20: 3; 2013-05-21: 3; 2013-05-22: 3; 2013-05-23: 3; 2013-05-24: 3; 2013-05-28: 3; 2013-05-29: 3; 2013-05-30: 3; 2013-05-31: 3; 2013-06-03: 3; 2013-06-04: 3; 2013-06-05: 3; 2013-06-06: 3; 2013-06-07: 3; 2013-06-10: 3; 2013-06-11: 3; 2013-06-12: 3; 2013-06-13: 3; 2013-06-14: 3; 2013-06-17: 3; 2013-06-18: 3; 2013-06-19: 3; 2013-06-20: 3; 2013-06-21: 3; 2013-06-24: 3; 2013-06-25: 3; 2013-06-26: 3; 2013-06-27: 3; 2013-06-28: 3; 2013-07-01: 3; 2013-07-02: 3; 2013-07-03: 3; 2013-07-05: 3; 2013-07-08: 3; 2013-07-09: 3; 2013-07-10: 3; 2013-07-11: 3; 2013-07-12: 3; 2013-07-15: 3; 2013-07-16: 3; 2013-07-17: 3; 2013-07-18: 3; 2013-07-19: 3; 2013-07-22: 3; 2013-07-23: 3; 2013-07-24: 3; 2013-07-25: 3; 2013-07-26: 3; 2013-07-29: 3; 2013-07-30: 3; 2013-07-31: 3; 2013-08-01: 3; 2013-08-02: 3; 2013-08-05: 3; 2013-08-06: 3; 2013-08-07: 3; 2013-08-08: 3; 2013-08-09: 3; 2013-08-12: 3; 2013-08-13: 3; 2013-08-14: 3; 2013-08-15: 3; 2013-08-16: 3; 2013-08-19: 3; 2013-08-20: 3; 2013-08-21: 3; 2013-08-22: 3; 2013-08-23: 3; 2013-08-26: 3; 2013-08-27: 3; 2013-08-28: 3; 2013-08-29: 3; 2013-08-30: 3; 2013-09-03: 3; 2013-09-04: 3; 2013-09-05: 3; 2013-09-06: 3; 2013-09-09: 3; 2013-09-10: 3; 2013-09-11: 3; 2013-09-12: 3; 2013-09-13: 3; 2013-09-16: 3; 2013-09-17: 3; 2013-09-18: 3; 2013-09-19: 3; 2013-09-20: 3; 2013-09-23: 3; 2013-09-24: 3; 2013-09-25: 3; 2013-09-26: 3; 2013-09-27: 3; 2013-09-30: 3; 2013-10-01: 3; 2013-10-02: 3; 2013-10-03: 3; 2013-10-04: 3; 2013-10-07: 3; 2013-10-08: 3; 2013-10-09: 3; 2013-10-10: 3; 2013-10-11: 3; 2013-10-14: 3; 2013-10-15: 3; 2013-10-16: 3; 2013-10-17: 3; 2013-10-18: 3; 2013-10-21: 3; 2013-10-22: 3; 2013-10-23: 3; 2013-10-24: 3; 2013-10-25: 3; 2013-10-28: 3; 2013-10-29: 3; 2013-10-30: 3; 2013-10-31: 3; 2013-11-01: 3; 2013-11-04: 3; 2013-11-05: 3; 2013-11-06: 3; 2013-11-07: 3; 2013-11-08: 3; 2013-11-11: 3; 2013-11-12: 3; 2013-11-13: 3; 2013-11-14: 3; 2013-11-15: 3; 2013-11-18: 3; 2013-11-19: 3; 2013-11-20: 3; 2013-11-21: 3; 2013-11-22: 3; 2013-11-25: 3; 2013-11-26: 3; 2013-11-27: 3; 2013-11-29: 3; 2013-12-02: 3; 2013-12-03: 3; 2013-12-04: 3; 2013-12-05: 3; 2013-12-06: 3; 2013-12-09: 3; 2013-12-10: 3; 2013-12-11: 3; 2013-12-12: 3; 2013-12-13: 3