## Sheet1
Activity ID | Project | Cost Code | Vendor | Activity Name | Original Duration | Remaining Duration | Schedule % Complete | Start | Finish | Total Float | At Completion Labor Units | Spreadsheet Field | time axis 2010-11-01 to 2013-12-13
EC2430 | 1345006 |  |  | Substantial Completion - All TCO | 0 | 0 | 0% |  | 2013-12-13 | 0 | 0 | At Completion Labor Units
EC1080 | 1345006 |  |  | Permits Received - Start Site Work | 0 | 0 | 0% | 2010-11-02 |  | 0 | 0 | At Completion Labor Units
EC1010 | 1345006 |  |  | Building Pad Delivered by Owner | 0 | 0 | 0% | 2010-11-01 |  | 0 | 0 | At Completion Labor Units
EC2440 | 1345006 |  |  | Complete Building 1 | 0 | 0 | 0% |  | 2013-12-13 | 0 | 0 | At Completion Labor Units
EC1650 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor 4 | 9.6 | 9.6 | 0% | 2011-11-09 | 2011-11-23 | 0 | 76.8 | At Completion Labor Units | 2011-11-09: 3.2; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 8; 2011-11-23: 1.6
EC1580 | 1345006 | 3000 | ACMEGC | Stucco Bands | 9.6 | 9.6 | 0% | 2011-11-09 | 2011-11-22 | 0 | 76.8 | At Completion Labor Units | 2011-11-09: 6.4; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 6.4
EC1660 | 1345006 | 3000 | ACMEGC | Stucco Grey | 19.2 | 19.2 | 0% | 2011-11-22 | 2011-12-19 | 0 | 153.6 | At Completion Labor Units | 2011-11-22: 1.6; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 8; 2011-11-29: 8; 2011-11-30: 8; 2011-12-01: 8; 2011-12-02: 8; 2011-12-05: 8; 2011-12-06: 8; 2011-12-07: 8; 2011-12-08: 8; 2011-12-09: 8; 2011-12-12: 8; 2011-12-13: 8; 2011-12-14: 8; 2011-12-15: 8; 2011-12-16: 8; 2011-12-19: 8; 2011-12-20: 8
EC1690 | 1345006 | 3000 | ACMEGC | Stucco Finish Coat | 24 | 24 | 0% | 2011-12-20 | 2012-01-20 | 0 | 192 | At Completion Labor Units | 2011-12-20: 8; 2011-12-21: 8; 2011-12-22: 8; 2011-12-23: 8; 2011-12-27: 8; 2011-12-28: 8; 2011-12-29: 8; 2011-12-30: 8; 2012-01-03: 8; 2012-01-04: 8; 2012-01-05: 8; 2012-01-06: 8; 2012-01-09: 8; 2012-01-10: 8; 2012-01-11: 8; 2012-01-12: 8; 2012-01-13: 8; 2012-01-16: 8; 2012-01-17: 8; 2012-01-18: 8; 2012-01-19: 8; 2012-01-20: 8; 2012-01-23: 8; 2012-01-24: 8
EC1840 | 1345006 | 3000 | ACMEGC | Caulk | 9.6 | 9.6 | 0% | 2012-01-23 | 2012-02-03 | 0 | 76.8 | At Completion Labor Units | 2012-01-23: 8; 2012-01-24: 8; 2012-01-25: 8; 2012-01-26: 8; 2012-01-27: 8; 2012-01-30: 8; 2012-01-31: 8; 2012-02-01: 8; 2012-02-02: 8; 2012-02-03: 4.8
EC1900 | 1345006 | 3000 | ACMEGC | Stucco Band Trim | 12 | 12 | 0% | 2012-02-03 | 2012-02-21 | 0 | 96 | At Completion Labor Units | 2012-02-03: 3.2; 2012-02-06: 8; 2012-02-07: 8; 2012-02-08: 8; 2012-02-09: 8; 2012-02-10: 8; 2012-02-13: 8; 2012-02-14: 8; 2012-02-15: 8; 2012-02-16: 8; 2012-02-17: 8; 2012-02-20: 8; 2012-02-21: 4.8
EC1980 | 1345006 | 3000 | ACMEGC | Paint Exterior | 12 | 12 | 0% | 2012-02-28 | 2012-03-15 | 0 | 96 | At Completion Labor Units | 2012-02-28: 3.2; 2012-02-29: 8; 2012-03-01: 8; 2012-03-02: 8; 2012-03-05: 8; 2012-03-06: 8; 2012-03-07: 8; 2012-03-08: 8; 2012-03-09: 8; 2012-03-12: 8; 2012-03-13: 8; 2012-03-14: 8; 2012-03-15: 4.8
EC2110 | 1345006 | 3000 | ACMEGC | Demobilize Scaffolding | 12 | 12 | 0% | 2012-03-15 | 2012-04-02 | 0 | 96 | At Completion Labor Units | 2012-03-15: 3.2; 2012-03-16: 8; 2012-03-19: 8; 2012-03-20: 8; 2012-03-21: 8; 2012-03-22: 8; 2012-03-23: 8; 2012-03-26: 8; 2012-03-27: 8; 2012-03-28: 8; 2012-03-29: 8; 2012-03-30: 8; 2012-04-02: 4.8
EC1360 | 1345006 | 3000 | ACMEGC | Mobilize Scaffolding | 12 | 12 | 0% | 2011-08-03 | 2011-08-19 | 31.4 | 96 | At Completion Labor Units | 2011-08-03: 1.6; 2011-08-04: 8; 2011-08-05: 8; 2011-08-08: 8; 2011-08-09: 8; 2011-08-10: 8; 2011-08-11: 8; 2011-08-12: 8; 2011-08-15: 8; 2011-08-16: 8; 2011-08-17: 8; 2011-08-18: 8; 2011-08-19: 6.4
EC2140 | 1345006 | 3000 |  | Shell Complete | 0 | 0 | 0% |  | 2012-04-18 | 144 | 0 | At Completion Labor Units
EC1990 | 1345006 | 3000 | ACMEGC | Install Railings | 36 | 36 | 0% | 2012-02-28 | 2012-04-18 | 144 | 288 | At Completion Labor Units | 2012-02-28: 3.2; 2012-02-29: 8; 2012-03-01: 8; 2012-03-02: 8; 2012-03-05: 8; 2012-03-06: 8; 2012-03-07: 8; 2012-03-08: 8; 2012-03-09: 8; 2012-03-12: 8; 2012-03-13: 8; 2012-03-14: 8; 2012-03-15: 8; 2012-03-16: 8; 2012-03-19: 8; 2012-03-20: 8; 2012-03-21: 8; 2012-03-22: 8; 2012-03-23: 8; 2012-03-26: 8; 2012-03-27: 8; 2012-03-28: 8; 2012-03-29: 8; 2012-03-30: 8; 2012-04-02: 8; 2012-04-03: 8; 2012-04-04: 8; 2012-04-05: 8; 2012-04-06: 8; 2012-04-09: 8; 2012-04-10: 8; 2012-04-11: 8; 2012-04-12: 8; 2012-04-13: 8; 2012-04-16: 8; 2012-04-17: 8; 2012-04-18: 4.8
EC1410 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 1 | 19.2 | 19.2 | 0% | 2011-08-19 | 2011-09-15 | 0 | 153.6 | At Completion Labor Units | 2011-08-19: 1.6; 2011-08-22: 8; 2011-08-23: 8; 2011-08-24: 8; 2011-08-25: 8; 2011-08-26: 8; 2011-08-29: 8; 2011-08-30: 8; 2011-08-31: 8; 2011-09-01: 8; 2011-09-02: 8; 2011-09-06: 8; 2011-09-07: 8; 2011-09-08: 8; 2011-09-09: 8; 2011-09-12: 8; 2011-09-13: 8; 2011-09-14: 8; 2011-09-15: 8; 2011-09-16: 8
EC1470 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 2 | 19.2 | 19.2 | 0% | 2011-09-09 | 2011-10-06 | 0 | 153.6 | At Completion Labor Units | 2011-09-09: 8; 2011-09-12: 8; 2011-09-13: 8; 2011-09-14: 8; 2011-09-15: 8; 2011-09-16: 8; 2011-09-19: 8; 2011-09-20: 8; 2011-09-21: 8; 2011-09-22: 8; 2011-09-23: 8; 2011-09-26: 8; 2011-09-27: 8; 2011-09-28: 8; 2011-09-29: 8; 2011-09-30: 8; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 1.6
EC1500 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 3 | 16.8 | 16.8 | 0% | 2011-09-29 | 2011-10-21 | 0 | 134.4 | At Completion Labor Units | 2011-09-29: 6.4; 2011-09-30: 8; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8
EC1520 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 4 | 21.6 | 21.6 | 0% | 2011-10-17 | 2011-11-15 | 0 | 172.8 | At Completion Labor Units | 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 8; 2011-10-28: 8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 4.8
EC1490 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor1 | 9.6 | 9.6 | 0% | 2011-09-12 | 2011-09-23 | 16.2 | 76.8 | At Completion Labor Units | 2011-09-12: 8; 2011-09-13: 8; 2011-09-14: 8; 2011-09-15: 8; 2011-09-16: 8; 2011-09-19: 8; 2011-09-20: 8; 2011-09-21: 8; 2011-09-22: 8; 2011-09-23: 4.8
EC1510 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor 2 | 9.6 | 9.6 | 0% | 2011-09-30 | 2011-10-13 | 11.6 | 76.8 | At Completion Labor Units | 2011-09-30: 6.4; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 6.4
EC1570 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor 3 | 7.2 | 7.2 | 0% | 2011-10-18 | 2011-10-27 | 9.4 | 57.6 | At Completion Labor Units | 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 1.6
EC2370 | 1345006 | 4000 | ACMEGC | Final Inspections and Punchlist | 33.6 | 33.6 | 0% | 2012-10-30 | 2012-12-17 | 259.4 | 528 | At Completion Labor Units | 2012-10-30: 6.86; 2012-10-31: 17.14; 2012-11-01: 17.14; 2012-11-02: 17.14; 2012-11-05: 17.14; 2012-11-06: 17.14; 2012-11-07: 17.14; 2012-11-08: 17.14; 2012-11-09: 17.14; 2012-11-12: 17.14; 2012-11-13: 17.14; 2012-11-14: 16.71; 2012-11-15: 15; 2012-11-16: 15; 2012-11-19: 15; 2012-11-20: 15; 2012-11-21: 15; 2012-11-23: 15; 2012-11-26: 15; 2012-11-27: 15; 2012-11-28: 15; 2012-11-29: 15; 2012-11-30: 15; 2012-12-03: 15; 2012-12-04: 15; 2012-12-05: 15; 2012-12-06: 15; 2012-12-07: 15; 2012-12-10: 15; 2012-12-11: 15; 2012-12-12: 15; 2012-12-13: 15; 2012-12-14: 15; 2012-12-17: 15; 2012-12-18: 3
EC1820 | 1345006 | 4000 | ACMEGC | Building 2 Elevators Complete | 69.6 | 69.6 | 0% | 2011-11-25 | 2012-03-01 | 374.6 | 768 | At Completion Labor Units | 2011-11-25: 6.62; 2011-11-28: 11.03; 2011-11-29: 11.03; 2011-11-30: 11.03; 2011-12-01: 11.03; 2011-12-02: 11.03; 2011-12-05: 11.03; 2011-12-06: 11.03; 2011-12-07: 11.03; 2011-12-08: 11.03; 2011-12-09: 11.03; 2011-12-12: 11.03; 2011-12-13: 11.03; 2011-12-14: 11.03; 2011-12-15: 11.03; 2011-12-16: 11.03; 2011-12-19: 11.03; 2011-12-20: 11.03; 2011-12-21: 11.03; 2011-12-22: 11.03; 2011-12-23: 11.03; 2011-12-27: 11.03; 2011-12-28: 11.03; 2011-12-29: 11.03; 2011-12-30: 11.03; 2012-01-03: 11.03; 2012-01-04: 11.03; 2012-01-05: 11.03; 2012-01-06: 11.03; 2012-01-09: 11.03; 2012-01-10: 11.03; 2012-01-11: 11.03; 2012-01-12: 11.03; 2012-01-13: 11.03; 2012-01-16: 11.03; 2012-01-17: 11.03; 2012-01-18: 11.03; 2012-01-19: 11.03; 2012-01-20: 11.03; 2012-01-23: 11.03; 2012-01-24: 11.03; 2012-01-25: 11.03; 2012-01-26: 11.03; 2012-01-27: 11.03; 2012-01-30: 11.03; 2012-01-31: 11.03; 2012-02-01: 11.03; 2012-02-02: 11.03; 2012-02-03: 11.03; 2012-02-06: 11.03; 2012-02-07: 11.03; 2012-02-08: 11.03; 2012-02-09: 11.03; 2012-02-10: 11.03; 2012-02-13: 11.03; 2012-02-14: 11.03; 2012-02-15: 11.03; 2012-02-16: 11.03; 2012-02-17: 11.03; 2012-02-20: 11.03; 2012-02-21: 11.03; 2012-02-22: 11.03; 2012-02-23: 11.03; 2012-02-24: 11.03; 2012-02-27: 11.03; 2012-02-28: 11.03; 2012-02-29: 11.03; 2012-03-01: 11.03; 2012-03-02: 11.03; 2012-03-05: 11.03
EC2240 | 1345006 | 4000 | ACMEGC | Tenant Finishes for Clubhouse Areas | 127.2 | 127.2 | 0% | 2012-06-21 | 2012-12-17 | 259.4 | 1760 | At Completion Labor Units | 2012-06-21: 15.09; 2012-06-22: 15.09; 2012-06-25: 15.09; 2012-06-26: 15.09; 2012-06-27: 15.09; 2012-06-28: 15.09; 2012-06-29: 15.09; 2012-07-02: 15.09; 2012-07-03: 15.09; 2012-07-05: 15.09; 2012-07-06: 15.09; 2012-07-09: 15.09; 2012-07-10: 15.09; 2012-07-11: 15.09; 2012-07-12: 15.09; 2012-07-13: 15.09; 2012-07-16: 15.09; 2012-07-17: 15.09; 2012-07-18: 15.09; 2012-07-19: 15.09; 2012-07-20: 15.09; 2012-07-23: 15.09; 2012-07-24: 15.09; 2012-07-25: 15.09; 2012-07-26: 15.09; 2012-07-27: 15.09; 2012-07-30: 15.09; 2012-07-31: 15.09; 2012-08-01: 15.09; 2012-08-02: 15.09; 2012-08-03: 15.09; 2012-08-06: 15.09; 2012-08-07: 15.09; 2012-08-08: 15.09; 2012-08-09: 15.09; 2012-08-10: 15.09; 2012-08-13: 15.09; 2012-08-14: 15.09; 2012-08-15: 15.09; 2012-08-16: 15.09; 2012-08-17: 15.09; 2012-08-20: 15.09; 2012-08-21: 13.96; 2012-08-22: 13.21; 2012-08-23: 13.21; 2012-08-24: 13.21; 2012-08-27: 13.21; 2012-08-28: 13.21; 2012-08-29: 13.21; 2012-08-30: 13.21; 2012-08-31: 13.21; 2012-09-04: 13.21; 2012-09-05: 13.21; 2012-09-06: 13.21; 2012-09-07: 13.21; 2012-09-10: 13.21; 2012-09-11: 13.21; 2012-09-12: 13.21; 2012-09-13: 13.21; 2012-09-14: 13.21; 2012-09-17: 13.21; 2012-09-18: 13.21; 2012-09-19: 13.21; 2012-09-20: 13.21; 2012-09-21: 13.21; 2012-09-24: 13.21; 2012-09-25: 13.21; 2012-09-26: 13.21; 2012-09-27: 13.21; 2012-09-28: 13.21; 2012-10-01: 13.21; 2012-10-02: 13.21; 2012-10-03: 13.21; 2012-10-04: 13.21; 2012-10-05: 13.21; 2012-10-08: 13.21; 2012-10-09: 13.21; 2012-10-10: 13.21; 2012-10-11: 13.21; 2012-10-12: 13.21; 2012-10-15: 13.21; 2012-10-16: 13.21; 2012-10-17: 13.21; 2012-10-18: 13.21; 2012-10-19: 13.21; 2012-10-22: 13.21; 2012-10-23: 13.21; 2012-10-24: 13.21; 2012-10-25: 13.21; 2012-10-26: 13.21; 2012-10-29: 13.21; 2012-10-30: 13.21; 2012-10-31: 13.21; 2012-11-01: 13.21; 2012-11-02: 13.21; 2012-11-05: 13.21; 2012-11-06: 13.21; 2012-11-07: 13.21; 2012-11-08: 13.21; 2012-11-09: 13.21; 2012-11-12: 13.21; 2012-11-13: 13.21; 2012-11-14: 13.21; 2012-11-15: 13.21; 2012-11-16: 13.21; 2012-11-19: 13.21; 2012-11-20: 13.21; 2012-11-21: 13.21; 2012-11-23: 13.21; 2012-11-26: 13.21; 2012-11-27: 13.21; 2012-11-28: 13.21; 2012-11-29: 13.21; 2012-11-30: 13.21; 2012-12-03: 13.21; 2012-12-04: 13.21; 2012-12-05: 13.21; 2012-12-06: 13.21; 2012-12-07: 13.21; 2012-12-10: 13.21; 2012-12-11: 13.21; 2012-12-12: 13.21; 2012-12-13: 13.21; 2012-12-14: 13.21; 2012-12-17: 13.21; 2012-12-18: 13.21; 2012-12-19: 13.21; 2012-12-20: 2.64
EC1550 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 1 | 196.8 | 196.8 | 0% | 2011-09-22 | 2012-06-25 | 259.4 | 901.53 | At Completion Labor Units | 2011-09-22: 0.97; 2011-09-23: 4.87; 2011-09-26: 4.87; 2011-09-27: 4.87; 2011-09-28: 4.87; 2011-09-29: 4.87; 2011-09-30: 4.87; 2011-10-03: 4.87; 2011-10-04: 4.87; 2011-10-05: 4.87; 2011-10-06: 4.87; 2011-10-07: 4.87; 2011-10-10: 4.87; 2011-10-11: 4.87; 2011-10-12: 4.87; 2011-10-13: 4.87; 2011-10-14: 4.87; 2011-10-17: 4.87; 2011-10-18: 4.87; 2011-10-19: 4.87; 2011-10-20: 4.87; 2011-10-21: 4.87; 2011-10-24: 4.87; 2011-10-25: 4.87; 2011-10-26: 4.87; 2011-10-27: 4.87; 2011-10-28: 4.87; 2011-10-31: 4.87; 2011-11-01: 4.87; 2011-11-02: 4.87; 2011-11-03: 4.87; 2011-11-04: 4.87; 2011-11-07: 4.87; 2011-11-08: 4.87; 2011-11-09: 4.87; 2011-11-10: 4.87; 2011-11-11: 4.87; 2011-11-14: 4.87; 2011-11-15: 4.87; 2011-11-16: 4.87; 2011-11-17: 4.87; 2011-11-18: 4.87; 2011-11-21: 4.87; 2011-11-22: 4.87; 2011-11-23: 4.87; 2011-11-25: 4.87; 2011-11-28: 4.87; 2011-11-29: 4.87; 2011-11-30: 4.87; 2011-12-01: 4.87; 2011-12-02: 4.87; 2011-12-05: 4.87; 2011-12-06: 4.87; 2011-12-07: 4.87; 2011-12-08: 4.87; 2011-12-09: 4.87; 2011-12-12: 4.87; 2011-12-13: 4.87; 2011-12-14: 4.87; 2011-12-15: 4.87; 2011-12-16: 4.87; 2011-12-19: 4.87; 2011-12-20: 4.87; 2011-12-21: 4.87; 2011-12-22: 4.87; 2011-12-23: 4.87; 2011-12-27: 4.61; 2011-12-28: 4.43; 2011-12-29: 4.43; 2011-12-30: 4.43; 2012-01-03: 4.43; 2012-01-04: 4.43; 2012-01-05: 4.43; 2012-01-06: 4.43; 2012-01-09: 4.43; 2012-01-10: 4.43; 2012-01-11: 4.43; 2012-01-12: 4.43; 2012-01-13: 4.43; 2012-01-16: 4.43; 2012-01-17: 4.43; 2012-01-18: 4.43; 2012-01-19: 4.43; 2012-01-20: 4.43; 2012-01-23: 4.43; 2012-01-24: 4.43; 2012-01-25: 4.43; 2012-01-26: 4.43; 2012-01-27: 4.43; 2012-01-30: 4.43; 2012-01-31: 4.43; 2012-02-01: 4.43; 2012-02-02: 4.43; 2012-02-03: 4.43; 2012-02-06: 4.43; 2012-02-07: 4.43; 2012-02-08: 4.43; 2012-02-09: 4.43; 2012-02-10: 4.43; 2012-02-13: 4.43; 2012-02-14: 4.43; 2012-02-15: 4.43; 2012-02-16: 4.43; 2012-02-17: 4.43; 2012-02-20: 4.43; 2012-02-21: 4.43; 2012-02-22: 4.43; 2012-02-23: 4.43; 2012-02-24: 4.43; 2012-02-27: 4.43; 2012-02-28: 4.43; 2012-02-29: 4.43; 2012-03-01: 4.43; 2012-03-02: 4.43; 2012-03-05: 4.43; 2012-03-06: 4.43; 2012-03-07: 4.43; 2012-03-08: 4.43; 2012-03-09: 4.43; 2012-03-12: 4.43; 2012-03-13: 4.43; 2012-03-14: 4.43; 2012-03-15: 4.43; 2012-03-16: 4.43; 2012-03-19: 4.43; 2012-03-20: 4.43; 2012-03-21: 4.43; 2012-03-22: 4.43; 2012-03-23: 4.43; 2012-03-26: 4.43; 2012-03-27: 4.43; 2012-03-28: 4.43; 2012-03-29: 4.43; 2012-03-30: 4.43; 2012-04-02: 4.43; 2012-04-03: 4.43; 2012-04-04: 4.43; 2012-04-05: 4.43; 2012-04-06: 4.43; 2012-04-09: 4.43; 2012-04-10: 4.43; 2012-04-11: 4.43; 2012-04-12: 4.43; 2012-04-13: 4.43; 2012-04-16: 4.43; 2012-04-17: 4.43; 2012-04-18: 4.43; 2012-04-19: 4.43; 2012-04-20: 4.43; 2012-04-23: 4.43; 2012-04-24: 4.43; 2012-04-25: 4.43; 2012-04-26: 4.43; 2012-04-27: 4.43; 2012-04-30: 4.43; 2012-05-01: 4.43; 2012-05-02: 4.43; 2012-05-03: 4.43; 2012-05-04: 4.43; 2012-05-07: 4.43; 2012-05-08: 4.43; 2012-05-09: 4.43; 2012-05-10: 4.43; 2012-05-11: 4.43; 2012-05-14: 4.43; 2012-05-15: 4.43; 2012-05-16: 4.43; 2012-05-17: 4.43; 2012-05-18: 4.43; 2012-05-21: 4.43; 2012-05-22: 4.43; 2012-05-23: 4.43; 2012-05-24: 4.43; 2012-05-25: 4.43; 2012-05-29: 4.43; 2012-05-30: 4.43; 2012-05-31: 4.43; 2012-06-01: 4.43; 2012-06-04: 4.43; 2012-06-05: 4.43; 2012-06-06: 4.43; 2012-06-07: 4.43; 2012-06-08: 4.43; 2012-06-11: 4.43; 2012-06-12: 4.43; 2012-06-13: 4.43; 2012-06-14: 4.43; 2012-06-15: 4.43; 2012-06-18: 4.43; 2012-06-19: 4.43; 2012-06-20: 4.43; 2012-06-21: 4.43; 2012-06-22: 4.43; 2012-06-25: 4.43; 2012-06-26: 4.43; 2012-06-27: 4.43; 2012-06-28: 4.43; 2012-06-29: 2.66
EC1630 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 1 | 199.2 | 199.2 | 0% | 2011-09-29 | 2012-07-04 | 259.4 | 901.53 | At Completion Labor Units | 2011-09-29: 0.96; 2011-09-30: 4.81; 2011-10-03: 4.81; 2011-10-04: 4.81; 2011-10-05: 4.81; 2011-10-06: 4.81; 2011-10-07: 4.81; 2011-10-10: 4.81; 2011-10-11: 4.81; 2011-10-12: 4.81; 2011-10-13: 4.81; 2011-10-14: 4.81; 2011-10-17: 4.81; 2011-10-18: 4.81; 2011-10-19: 4.81; 2011-10-20: 4.81; 2011-10-21: 4.81; 2011-10-24: 4.81; 2011-10-25: 4.81; 2011-10-26: 4.81; 2011-10-27: 4.81; 2011-10-28: 4.81; 2011-10-31: 4.81; 2011-11-01: 4.81; 2011-11-02: 4.81; 2011-11-03: 4.81; 2011-11-04: 4.81; 2011-11-07: 4.81; 2011-11-08: 4.81; 2011-11-09: 4.81; 2011-11-10: 4.81; 2011-11-11: 4.81; 2011-11-14: 4.81; 2011-11-15: 4.81; 2011-11-16: 4.81; 2011-11-17: 4.81; 2011-11-18: 4.81; 2011-11-21: 4.81; 2011-11-22: 4.81; 2011-11-23: 4.81; 2011-11-25: 4.81; 2011-11-28: 4.81; 2011-11-29: 4.81; 2011-11-30: 4.81; 2011-12-01: 4.81; 2011-12-02: 4.81; 2011-12-05: 4.81; 2011-12-06: 4.81; 2011-12-07: 4.81; 2011-12-08: 4.81; 2011-12-09: 4.81; 2011-12-12: 4.81; 2011-12-13: 4.81; 2011-12-14: 4.81; 2011-12-15: 4.81; 2011-12-16: 4.81; 2011-12-19: 4.81; 2011-12-20: 4.81; 2011-12-21: 4.81; 2011-12-22: 4.81; 2011-12-23: 4.81; 2011-12-27: 4.81; 2011-12-28: 4.81; 2011-12-29: 4.81; 2011-12-30: 4.81; 2012-01-03: 4.81; 2012-01-04: 4.81; 2012-01-05: 4.47; 2012-01-06: 4.38; 2012-01-09: 4.38; 2012-01-10: 4.38; 2012-01-11: 4.38; 2012-01-12: 4.38; 2012-01-13: 4.38; 2012-01-16: 4.38; 2012-01-17: 4.38; 2012-01-18: 4.38; 2012-01-19: 4.38; 2012-01-20: 4.38; 2012-01-23: 4.38; 2012-01-24: 4.38; 2012-01-25: 4.38; 2012-01-26: 4.38; 2012-01-27: 4.38; 2012-01-30: 4.38; 2012-01-31: 4.38; 2012-02-01: 4.38; 2012-02-02: 4.38; 2012-02-03: 4.38; 2012-02-06: 4.38; 2012-02-07: 4.38; 2012-02-08: 4.38; 2012-02-09: 4.38; 2012-02-10: 4.38; 2012-02-13: 4.38; 2012-02-14: 4.38; 2012-02-15: 4.38; 2012-02-16: 4.38; 2012-02-17: 4.38; 2012-02-20: 4.38; 2012-02-21: 4.38; 2012-02-22: 4.38; 2012-02-23: 4.38; 2012-02-24: 4.38; 2012-02-27: 4.38; 2012-02-28: 4.38; 2012-02-29: 4.38; 2012-03-01: 4.38; 2012-03-02: 4.38; 2012-03-05: 4.38; 2012-03-06: 4.38; 2012-03-07: 4.38; 2012-03-08: 4.38; 2012-03-09: 4.38; 2012-03-12: 4.38; 2012-03-13: 4.38; 2012-03-14: 4.38; 2012-03-15: 4.38; 2012-03-16: 4.38; 2012-03-19: 4.38; 2012-03-20: 4.38; 2012-03-21: 4.38; 2012-03-22: 4.38; 2012-03-23: 4.38; 2012-03-26: 4.38; 2012-03-27: 4.38; 2012-03-28: 4.38; 2012-03-29: 4.38; 2012-03-30: 4.38; 2012-04-02: 4.38; 2012-04-03: 4.38; 2012-04-04: 4.38; 2012-04-05: 4.38; 2012-04-06: 4.38; 2012-04-09: 4.38; 2012-04-10: 4.38; 2012-04-11: 4.38; 2012-04-12: 4.38; 2012-04-13: 4.38; 2012-04-16: 4.38; 2012-04-17: 4.38; 2012-04-18: 4.38; 2012-04-19: 4.38; 2012-04-20: 4.38; 2012-04-23: 4.38; 2012-04-24: 4.38; 2012-04-25: 4.38; 2012-04-26: 4.38; 2012-04-27: 4.38; 2012-04-30: 4.38; 2012-05-01: 4.38; 2012-05-02: 4.38; 2012-05-03: 4.38; 2012-05-04: 4.38; 2012-05-07: 4.38; 2012-05-08: 4.38; 2012-05-09: 4.38; 2012-05-10: 4.38; 2012-05-11: 4.38; 2012-05-14: 4.38; 2012-05-15: 4.38; 2012-05-16: 4.38; 2012-05-17: 4.38; 2012-05-18: 4.38; 2012-05-21: 4.38; 2012-05-22: 4.38; 2012-05-23: 4.38; 2012-05-24: 4.38; 2012-05-25: 4.38; 2012-05-29: 4.38; 2012-05-30: 4.38; 2012-05-31: 4.38; 2012-06-01: 4.38; 2012-06-04: 4.38; 2012-06-05: 4.38; 2012-06-06: 4.38; 2012-06-07: 4.38; 2012-06-08: 4.38; 2012-06-11: 4.38; 2012-06-12: 4.38; 2012-06-13: 4.38; 2012-06-14: 4.38; 2012-06-15: 4.38; 2012-06-18: 4.38; 2012-06-19: 4.38; 2012-06-20: 4.38; 2012-06-21: 4.38; 2012-06-22: 4.38; 2012-06-25: 4.38; 2012-06-26: 4.38; 2012-06-27: 4.38; 2012-06-28: 4.38; 2012-06-29: 4.38; 2012-07-02: 4.38; 2012-07-03: 4.38; 2012-07-05: 4.38; 2012-07-06: 4.38; 2012-07-09: 4.38; 2012-07-10: 4.38; 2012-07-11: 4.38
EC1670 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 2 | 199.2 | 199.2 | 0% | 2011-10-06 | 2012-07-11 | 310.6 | 901.53 | At Completion Labor Units | 2011-10-06: 0.96; 2011-10-07: 4.81; 2011-10-10: 4.81; 2011-10-11: 4.81; 2011-10-12: 4.81; 2011-10-13: 4.81; 2011-10-14: 4.81; 2011-10-17: 4.81; 2011-10-18: 4.81; 2011-10-19: 4.81; 2011-10-20: 4.81; 2011-10-21: 4.81; 2011-10-24: 4.81; 2011-10-25: 4.81; 2011-10-26: 4.81; 2011-10-27: 4.81; 2011-10-28: 4.81; 2011-10-31: 4.81; 2011-11-01: 4.81; 2011-11-02: 4.81; 2011-11-03: 4.81; 2011-11-04: 4.81; 2011-11-07: 4.81; 2011-11-08: 4.81; 2011-11-09: 4.81; 2011-11-10: 4.81; 2011-11-11: 4.81; 2011-11-14: 4.81; 2011-11-15: 4.81; 2011-11-16: 4.81; 2011-11-17: 4.81; 2011-11-18: 4.81; 2011-11-21: 4.81; 2011-11-22: 4.81; 2011-11-23: 4.81; 2011-11-25: 4.81; 2011-11-28: 4.81; 2011-11-29: 4.81; 2011-11-30: 4.81; 2011-12-01: 4.81; 2011-12-02: 4.81; 2011-12-05: 4.81; 2011-12-06: 4.81; 2011-12-07: 4.81; 2011-12-08: 4.81; 2011-12-09: 4.81; 2011-12-12: 4.81; 2011-12-13: 4.81; 2011-12-14: 4.81; 2011-12-15: 4.81; 2011-12-16: 4.81; 2011-12-19: 4.81; 2011-12-20: 4.81; 2011-12-21: 4.81; 2011-12-22: 4.81; 2011-12-23: 4.81; 2011-12-27: 4.81; 2011-12-28: 4.81; 2011-12-29: 4.81; 2011-12-30: 4.81; 2012-01-03: 4.81; 2012-01-04: 4.81; 2012-01-05: 4.81; 2012-01-06: 4.81; 2012-01-09: 4.81; 2012-01-10: 4.81; 2012-01-11: 4.81; 2012-01-12: 4.47; 2012-01-13: 4.38; 2012-01-16: 4.38; 2012-01-17: 4.38; 2012-01-18: 4.38; 2012-01-19: 4.38; 2012-01-20: 4.38; 2012-01-23: 4.38; 2012-01-24: 4.38; 2012-01-25: 4.38; 2012-01-26: 4.38; 2012-01-27: 4.38; 2012-01-30: 4.38; 2012-01-31: 4.38; 2012-02-01: 4.38; 2012-02-02: 4.38; 2012-02-03: 4.38; 2012-02-06: 4.38; 2012-02-07: 4.38; 2012-02-08: 4.38; 2012-02-09: 4.38; 2012-02-10: 4.38; 2012-02-13: 4.38; 2012-02-14: 4.38; 2012-02-15: 4.38; 2012-02-16: 4.38; 2012-02-17: 4.38; 2012-02-20: 4.38; 2012-02-21: 4.38; 2012-02-22: 4.38; 2012-02-23: 4.38; 2012-02-24: 4.38; 2012-02-27: 4.38; 2012-02-28: 4.38; 2012-02-29: 4.38; 2012-03-01: 4.38; 2012-03-02: 4.38; 2012-03-05: 4.38; 2012-03-06: 4.38; 2012-03-07: 4.38; 2012-03-08: 4.38; 2012-03-09: 4.38; 2012-03-12: 4.38; 2012-03-13: 4.38; 2012-03-14: 4.38; 2012-03-15: 4.38; 2012-03-16: 4.38; 2012-03-19: 4.38; 2012-03-20: 4.38; 2012-03-21: 4.38; 2012-03-22: 4.38; 2012-03-23: 4.38; 2012-03-26: 4.38; 2012-03-27: 4.38; 2012-03-28: 4.38; 2012-03-29: 4.38; 2012-03-30: 4.38; 2012-04-02: 4.38; 2012-04-03: 4.38; 2012-04-04: 4.38; 2012-04-05: 4.38; 2012-04-06: 4.38; 2012-04-09: 4.38; 2012-04-10: 4.38; 2012-04-11: 4.38; 2012-04-12: 4.38; 2012-04-13: 4.38; 2012-04-16: 4.38; 2012-04-17: 4.38; 2012-04-18: 4.38; 2012-04-19: 4.38; 2012-04-20: 4.38; 2012-04-23: 4.38; 2012-04-24: 4.38; 2012-04-25: 4.38; 2012-04-26: 4.38; 2012-04-27: 4.38; 2012-04-30: 4.38; 2012-05-01: 4.38; 2012-05-02: 4.38; 2012-05-03: 4.38; 2012-05-04: 4.38; 2012-05-07: 4.38; 2012-05-08: 4.38; 2012-05-09: 4.38; 2012-05-10: 4.38; 2012-05-11: 4.38; 2012-05-14: 4.38; 2012-05-15: 4.38; 2012-05-16: 4.38; 2012-05-17: 4.38; 2012-05-18: 4.38; 2012-05-21: 4.38; 2012-05-22: 4.38; 2012-05-23: 4.38; 2012-05-24: 4.38; 2012-05-25: 4.38; 2012-05-29: 4.38; 2012-05-30: 4.38; 2012-05-31: 4.38; 2012-06-01: 4.38; 2012-06-04: 4.38; 2012-06-05: 4.38; 2012-06-06: 4.38; 2012-06-07: 4.38; 2012-06-08: 4.38; 2012-06-11: 4.38; 2012-06-12: 4.38; 2012-06-13: 4.38; 2012-06-14: 4.38; 2012-06-15: 4.38; 2012-06-18: 4.38; 2012-06-19: 4.38; 2012-06-20: 4.38; 2012-06-21: 4.38; 2012-06-22: 4.38; 2012-06-25: 4.38; 2012-06-26: 4.38; 2012-06-27: 4.38; 2012-06-28: 4.38; 2012-06-29: 4.38; 2012-07-02: 4.38; 2012-07-03: 4.38; 2012-07-05: 4.38; 2012-07-06: 4.38; 2012-07-09: 4.38; 2012-07-10: 4.38; 2012-07-11: 4.38; 2012-07-12: 4.38; 2012-07-13: 4.38; 2012-07-16: 4.38; 2012-07-17: 4.38; 2012-07-18: 4.38
EC1700 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 2 | 199.2 | 199.2 | 0% | 2011-10-13 | 2012-07-18 | 310.6 | 901.53 | At Completion Labor Units | 2011-10-13: 0.96; 2011-10-14: 4.81; 2011-10-17: 4.81; 2011-10-18: 4.81; 2011-10-19: 4.81; 2011-10-20: 4.81; 2011-10-21: 4.81; 2011-10-24: 4.81; 2011-10-25: 4.81; 2011-10-26: 4.81; 2011-10-27: 4.81; 2011-10-28: 4.81; 2011-10-31: 4.81; 2011-11-01: 4.81; 2011-11-02: 4.81; 2011-11-03: 4.81; 2011-11-04: 4.81; 2011-11-07: 4.81; 2011-11-08: 4.81; 2011-11-09: 4.81; 2011-11-10: 4.81; 2011-11-11: 4.81; 2011-11-14: 4.81; 2011-11-15: 4.81; 2011-11-16: 4.81; 2011-11-17: 4.81; 2011-11-18: 4.81; 2011-11-21: 4.81; 2011-11-22: 4.81; 2011-11-23: 4.81; 2011-11-25: 4.81; 2011-11-28: 4.81; 2011-11-29: 4.81; 2011-11-30: 4.81; 2011-12-01: 4.81; 2011-12-02: 4.81; 2011-12-05: 4.81; 2011-12-06: 4.81; 2011-12-07: 4.81; 2011-12-08: 4.81; 2011-12-09: 4.81; 2011-12-12: 4.81; 2011-12-13: 4.81; 2011-12-14: 4.81; 2011-12-15: 4.81; 2011-12-16: 4.81; 2011-12-19: 4.81; 2011-12-20: 4.81; 2011-12-21: 4.81; 2011-12-22: 4.81; 2011-12-23: 4.81; 2011-12-27: 4.81; 2011-12-28: 4.81; 2011-12-29: 4.81; 2011-12-30: 4.81; 2012-01-03: 4.81; 2012-01-04: 4.81; 2012-01-05: 4.81; 2012-01-06: 4.81; 2012-01-09: 4.81; 2012-01-10: 4.81; 2012-01-11: 4.81; 2012-01-12: 4.81; 2012-01-13: 4.81; 2012-01-16: 4.81; 2012-01-17: 4.81; 2012-01-18: 4.81; 2012-01-19: 4.47; 2012-01-20: 4.38; 2012-01-23: 4.38; 2012-01-24: 4.38; 2012-01-25: 4.38; 2012-01-26: 4.38; 2012-01-27: 4.38; 2012-01-30: 4.38; 2012-01-31: 4.38; 2012-02-01: 4.38; 2012-02-02: 4.38; 2012-02-03: 4.38; 2012-02-06: 4.38; 2012-02-07: 4.38; 2012-02-08: 4.38; 2012-02-09: 4.38; 2012-02-10: 4.38; 2012-02-13: 4.38; 2012-02-14: 4.38; 2012-02-15: 4.38; 2012-02-16: 4.38; 2012-02-17: 4.38; 2012-02-20: 4.38; 2012-02-21: 4.38; 2012-02-22: 4.38; 2012-02-23: 4.38; 2012-02-24: 4.38; 2012-02-27: 4.38; 2012-02-28: 4.38; 2012-02-29: 4.38; 2012-03-01: 4.38; 2012-03-02: 4.38; 2012-03-05: 4.38; 2012-03-06: 4.38; 2012-03-07: 4.38; 2012-03-08: 4.38; 2012-03-09: 4.38; 2012-03-12: 4.38; 2012-03-13: 4.38; 2012-03-14: 4.38; 2012-03-15: 4.38; 2012-03-16: 4.38; 2012-03-19: 4.38; 2012-03-20: 4.38; 2012-03-21: 4.38; 2012-03-22: 4.38; 2012-03-23: 4.38; 2012-03-26: 4.38; 2012-03-27: 4.38; 2012-03-28: 4.38; 2012-03-29: 4.38; 2012-03-30: 4.38; 2012-04-02: 4.38; 2012-04-03: 4.38; 2012-04-04: 4.38; 2012-04-05: 4.38; 2012-04-06: 4.38; 2012-04-09: 4.38; 2012-04-10: 4.38; 2012-04-11: 4.38; 2012-04-12: 4.38; 2012-04-13: 4.38; 2012-04-16: 4.38; 2012-04-17: 4.38; 2012-04-18: 4.38; 2012-04-19: 4.38; 2012-04-20: 4.38; 2012-04-23: 4.38; 2012-04-24: 4.38; 2012-04-25: 4.38; 2012-04-26: 4.38; 2012-04-27: 4.38; 2012-04-30: 4.38; 2012-05-01: 4.38; 2012-05-02: 4.38; 2012-05-03: 4.38; 2012-05-04: 4.38; 2012-05-07: 4.38; 2012-05-08: 4.38; 2012-05-09: 4.38; 2012-05-10: 4.38; 2012-05-11: 4.38; 2012-05-14: 4.38; 2012-05-15: 4.38; 2012-05-16: 4.38; 2012-05-17: 4.38; 2012-05-18: 4.38; 2012-05-21: 4.38; 2012-05-22: 4.38; 2012-05-23: 4.38; 2012-05-24: 4.38; 2012-05-25: 4.38; 2012-05-29: 4.38; 2012-05-30: 4.38; 2012-05-31: 4.38; 2012-06-01: 4.38; 2012-06-04: 4.38; 2012-06-05: 4.38; 2012-06-06: 4.38; 2012-06-07: 4.38; 2012-06-08: 4.38; 2012-06-11: 4.38; 2012-06-12: 4.38; 2012-06-13: 4.38; 2012-06-14: 4.38; 2012-06-15: 4.38; 2012-06-18: 4.38; 2012-06-19: 4.38; 2012-06-20: 4.38; 2012-06-21: 4.38; 2012-06-22: 4.38; 2012-06-25: 4.38; 2012-06-26: 4.38; 2012-06-27: 4.38; 2012-06-28: 4.38; 2012-06-29: 4.38; 2012-07-02: 4.38; 2012-07-03: 4.38; 2012-07-05: 4.38; 2012-07-06: 4.38; 2012-07-09: 4.38; 2012-07-10: 4.38; 2012-07-11: 4.38; 2012-07-12: 4.38; 2012-07-13: 4.38; 2012-07-16: 4.38; 2012-07-17: 4.38; 2012-07-18: 4.38; 2012-07-19: 4.38; 2012-07-20: 4.38; 2012-07-23: 4.38; 2012-07-24: 4.38; 2012-07-25: 4.38
EC1790 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 3 | 199.2 | 199.2 | 0% | 2011-10-20 | 2012-07-25 | 310.6 | 901.53 | At Completion Labor Units | 2011-10-20: 0.96; 2011-10-21: 4.81; 2011-10-24: 4.81; 2011-10-25: 4.81; 2011-10-26: 4.81; 2011-10-27: 4.81; 2011-10-28: 4.81; 2011-10-31: 4.81; 2011-11-01: 4.81; 2011-11-02: 4.81; 2011-11-03: 4.81; 2011-11-04: 4.81; 2011-11-07: 4.81; 2011-11-08: 4.81; 2011-11-09: 4.81; 2011-11-10: 4.81; 2011-11-11: 4.81; 2011-11-14: 4.81; 2011-11-15: 4.81; 2011-11-16: 4.81; 2011-11-17: 4.81; 2011-11-18: 4.81; 2011-11-21: 4.81; 2011-11-22: 4.81; 2011-11-23: 4.81; 2011-11-25: 4.81; 2011-11-28: 4.81; 2011-11-29: 4.81; 2011-11-30: 4.81; 2011-12-01: 4.81; 2011-12-02: 4.81; 2011-12-05: 4.81; 2011-12-06: 4.81; 2011-12-07: 4.81; 2011-12-08: 4.81; 2011-12-09: 4.81; 2011-12-12: 4.81; 2011-12-13: 4.81; 2011-12-14: 4.81; 2011-12-15: 4.81; 2011-12-16: 4.81; 2011-12-19: 4.81; 2011-12-20: 4.81; 2011-12-21: 4.81; 2011-12-22: 4.81; 2011-12-23: 4.81; 2011-12-27: 4.81; 2011-12-28: 4.81; 2011-12-29: 4.81; 2011-12-30: 4.81; 2012-01-03: 4.81; 2012-01-04: 4.81; 2012-01-05: 4.81; 2012-01-06: 4.81; 2012-01-09: 4.81; 2012-01-10: 4.81; 2012-01-11: 4.81; 2012-01-12: 4.81; 2012-01-13: 4.81; 2012-01-16: 4.81; 2012-01-17: 4.81; 2012-01-18: 4.81; 2012-01-19: 4.81; 2012-01-20: 4.81; 2012-01-23: 4.81; 2012-01-24: 4.81; 2012-01-25: 4.81; 2012-01-26: 4.47; 2012-01-27: 4.38; 2012-01-30: 4.38; 2012-01-31: 4.38; 2012-02-01: 4.38; 2012-02-02: 4.38; 2012-02-03: 4.38; 2012-02-06: 4.38; 2012-02-07: 4.38; 2012-02-08: 4.38; 2012-02-09: 4.38; 2012-02-10: 4.38; 2012-02-13: 4.38; 2012-02-14: 4.38; 2012-02-15: 4.38; 2012-02-16: 4.38; 2012-02-17: 4.38; 2012-02-20: 4.38; 2012-02-21: 4.38; 2012-02-22: 4.38; 2012-02-23: 4.38; 2012-02-24: 4.38; 2012-02-27: 4.38; 2012-02-28: 4.38; 2012-02-29: 4.38; 2012-03-01: 4.38; 2012-03-02: 4.38; 2012-03-05: 4.38; 2012-03-06: 4.38; 2012-03-07: 4.38; 2012-03-08: 4.38; 2012-03-09: 4.38; 2012-03-12: 4.38; 2012-03-13: 4.38; 2012-03-14: 4.38; 2012-03-15: 4.38; 2012-03-16: 4.38; 2012-03-19: 4.38; 2012-03-20: 4.38; 2012-03-21: 4.38; 2012-03-22: 4.38; 2012-03-23: 4.38; 2012-03-26: 4.38; 2012-03-27: 4.38; 2012-03-28: 4.38; 2012-03-29: 4.38; 2012-03-30: 4.38; 2012-04-02: 4.38; 2012-04-03: 4.38; 2012-04-04: 4.38; 2012-04-05: 4.38; 2012-04-06: 4.38; 2012-04-09: 4.38; 2012-04-10: 4.38; 2012-04-11: 4.38; 2012-04-12: 4.38; 2012-04-13: 4.38; 2012-04-16: 4.38; 2012-04-17: 4.38; 2012-04-18: 4.38; 2012-04-19: 4.38; 2012-04-20: 4.38; 2012-04-23: 4.38; 2012-04-24: 4.38; 2012-04-25: 4.38; 2012-04-26: 4.38; 2012-04-27: 4.38; 2012-04-30: 4.38; 2012-05-01: 4.38; 2012-05-02: 4.38; 2012-05-03: 4.38; 2012-05-04: 4.38; 2012-05-07: 4.38; 2012-05-08: 4.38; 2012-05-09: 4.38; 2012-05-10: 4.38; 2012-05-11: 4.38; 2012-05-14: 4.38; 2012-05-15: 4.38; 2012-05-16: 4.38; 2012-05-17: 4.38; 2012-05-18: 4.38; 2012-05-21: 4.38; 2012-05-22: 4.38; 2012-05-23: 4.38; 2012-05-24: 4.38; 2012-05-25: 4.38; 2012-05-29: 4.38; 2012-05-30: 4.38; 2012-05-31: 4.38; 2012-06-01: 4.38; 2012-06-04: 4.38; 2012-06-05: 4.38; 2012-06-06: 4.38; 2012-06-07: 4.38; 2012-06-08: 4.38; 2012-06-11: 4.38; 2012-06-12: 4.38; 2012-06-13: 4.38; 2012-06-14: 4.38; 2012-06-15: 4.38; 2012-06-18: 4.38; 2012-06-19: 4.38; 2012-06-20: 4.38; 2012-06-21: 4.38; 2012-06-22: 4.38; 2012-06-25: 4.38; 2012-06-26: 4.38; 2012-06-27: 4.38; 2012-06-28: 4.38; 2012-06-29: 4.38; 2012-07-02: 4.38; 2012-07-03: 4.38; 2012-07-05: 4.38; 2012-07-06: 4.38; 2012-07-09: 4.38; 2012-07-10: 4.38; 2012-07-11: 4.38; 2012-07-12: 4.38; 2012-07-13: 4.38; 2012-07-16: 4.38; 2012-07-17: 4.38; 2012-07-18: 4.38; 2012-07-19: 4.38; 2012-07-20: 4.38; 2012-07-23: 4.38; 2012-07-24: 4.38; 2012-07-25: 4.38; 2012-07-26: 4.38; 2012-07-27: 4.38; 2012-07-30: 4.38; 2012-07-31: 4.38; 2012-08-01: 4.38
EC1850 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 3 | 199.2 | 199.2 | 0% | 2011-10-27 | 2012-08-01 | 310.6 | 901.53 | At Completion Labor Units | 2011-10-27: 0.96; 2011-10-28: 4.81; 2011-10-31: 4.81; 2011-11-01: 4.81; 2011-11-02: 4.81; 2011-11-03: 4.81; 2011-11-04: 4.81; 2011-11-07: 4.81; 2011-11-08: 4.81; 2011-11-09: 4.81; 2011-11-10: 4.81; 2011-11-11: 4.81; 2011-11-14: 4.81; 2011-11-15: 4.81; 2011-11-16: 4.81; 2011-11-17: 4.81; 2011-11-18: 4.81; 2011-11-21: 4.81; 2011-11-22: 4.81; 2011-11-23: 4.81; 2011-11-25: 4.81; 2011-11-28: 4.81; 2011-11-29: 4.81; 2011-11-30: 4.81; 2011-12-01: 4.81; 2011-12-02: 4.81; 2011-12-05: 4.81; 2011-12-06: 4.81; 2011-12-07: 4.81; 2011-12-08: 4.81; 2011-12-09: 4.81; 2011-12-12: 4.81; 2011-12-13: 4.81; 2011-12-14: 4.81; 2011-12-15: 4.81; 2011-12-16: 4.81; 2011-12-19: 4.81; 2011-12-20: 4.81; 2011-12-21: 4.81; 2011-12-22: 4.81; 2011-12-23: 4.81; 2011-12-27: 4.81; 2011-12-28: 4.81; 2011-12-29: 4.81; 2011-12-30: 4.81; 2012-01-03: 4.81; 2012-01-04: 4.81; 2012-01-05: 4.81; 2012-01-06: 4.81; 2012-01-09: 4.81; 2012-01-10: 4.81; 2012-01-11: 4.81; 2012-01-12: 4.81; 2012-01-13: 4.81; 2012-01-16: 4.81; 2012-01-17: 4.81; 2012-01-18: 4.81; 2012-01-19: 4.81; 2012-01-20: 4.81; 2012-01-23: 4.81; 2012-01-24: 4.81; 2012-01-25: 4.81; 2012-01-26: 4.81; 2012-01-27: 4.81; 2012-01-30: 4.81; 2012-01-31: 4.81; 2012-02-01: 4.81; 2012-02-02: 4.47; 2012-02-03: 4.38; 2012-02-06: 4.38; 2012-02-07: 4.38; 2012-02-08: 4.38; 2012-02-09: 4.38; 2012-02-10: 4.38; 2012-02-13: 4.38; 2012-02-14: 4.38; 2012-02-15: 4.38; 2012-02-16: 4.38; 2012-02-17: 4.38; 2012-02-20: 4.38; 2012-02-21: 4.38; 2012-02-22: 4.38; 2012-02-23: 4.38; 2012-02-24: 4.38; 2012-02-27: 4.38; 2012-02-28: 4.38; 2012-02-29: 4.38; 2012-03-01: 4.38; 2012-03-02: 4.38; 2012-03-05: 4.38; 2012-03-06: 4.38; 2012-03-07: 4.38; 2012-03-08: 4.38; 2012-03-09: 4.38; 2012-03-12: 4.38; 2012-03-13: 4.38; 2012-03-14: 4.38; 2012-03-15: 4.38; 2012-03-16: 4.38; 2012-03-19: 4.38; 2012-03-20: 4.38; 2012-03-21: 4.38; 2012-03-22: 4.38; 2012-03-23: 4.38; 2012-03-26: 4.38; 2012-03-27: 4.38; 2012-03-28: 4.38; 2012-03-29: 4.38; 2012-03-30: 4.38; 2012-04-02: 4.38; 2012-04-03: 4.38; 2012-04-04: 4.38; 2012-04-05: 4.38; 2012-04-06: 4.38; 2012-04-09: 4.38; 2012-04-10: 4.38; 2012-04-11: 4.38; 2012-04-12: 4.38; 2012-04-13: 4.38; 2012-04-16: 4.38; 2012-04-17: 4.38; 2012-04-18: 4.38; 2012-04-19: 4.38; 2012-04-20: 4.38; 2012-04-23: 4.38; 2012-04-24: 4.38; 2012-04-25: 4.38; 2012-04-26: 4.38; 2012-04-27: 4.38; 2012-04-30: 4.38; 2012-05-01: 4.38; 2012-05-02: 4.38; 2012-05-03: 4.38; 2012-05-04: 4.38; 2012-05-07: 4.38; 2012-05-08: 4.38; 2012-05-09: 4.38; 2012-05-10: 4.38; 2012-05-11: 4.38; 2012-05-14: 4.38; 2012-05-15: 4.38; 2012-05-16: 4.38; 2012-05-17: 4.38; 2012-05-18: 4.38; 2012-05-21: 4.38; 2012-05-22: 4.38; 2012-05-23: 4.38; 2012-05-24: 4.38; 2012-05-25: 4.38; 2012-05-29: 4.38; 2012-05-30: 4.38; 2012-05-31: 4.38; 2012-06-01: 4.38; 2012-06-04: 4.38; 2012-06-05: 4.38; 2012-06-06: 4.38; 2012-06-07: 4.38; 2012-06-08: 4.38; 2012-06-11: 4.38; 2012-06-12: 4.38; 2012-06-13: 4.38; 2012-06-14: 4.38; 2012-06-15: 4.38; 2012-06-18: 4.38; 2012-06-19: 4.38; 2012-06-20: 4.38; 2012-06-21: 4.38; 2012-06-22: 4.38; 2012-06-25: 4.38; 2012-06-26: 4.38; 2012-06-27: 4.38; 2012-06-28: 4.38; 2012-06-29: 4.38; 2012-07-02: 4.38; 2012-07-03: 4.38; 2012-07-05: 4.38; 2012-07-06: 4.38; 2012-07-09: 4.38; 2012-07-10: 4.38; 2012-07-11: 4.38; 2012-07-12: 4.38; 2012-07-13: 4.38; 2012-07-16: 4.38; 2012-07-17: 4.38; 2012-07-18: 4.38; 2012-07-19: 4.38; 2012-07-20: 4.38; 2012-07-23: 4.38; 2012-07-24: 4.38; 2012-07-25: 4.38; 2012-07-26: 4.38; 2012-07-27: 4.38; 2012-07-30: 4.38; 2012-07-31: 4.38; 2012-08-01: 4.38; 2012-08-02: 4.38; 2012-08-03: 4.38; 2012-08-06: 4.38; 2012-08-07: 4.38; 2012-08-08: 4.38
EC1910 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 4 | 201.6 | 201.6 | 0% | 2011-11-03 | 2012-08-13 | 310.6 | 901.53 | At Completion Labor Units | 2011-11-03: 0.95; 2011-11-04: 4.76; 2011-11-07: 4.76; 2011-11-08: 4.76; 2011-11-09: 4.76; 2011-11-10: 4.76; 2011-11-11: 4.76; 2011-11-14: 4.76; 2011-11-15: 4.76; 2011-11-16: 4.76; 2011-11-17: 4.76; 2011-11-18: 4.76; 2011-11-21: 4.76; 2011-11-22: 4.76; 2011-11-23: 4.76; 2011-11-25: 4.76; 2011-11-28: 4.76; 2011-11-29: 4.76; 2011-11-30: 4.76; 2011-12-01: 4.76; 2011-12-02: 4.76; 2011-12-05: 4.76; 2011-12-06: 4.76; 2011-12-07: 4.76; 2011-12-08: 4.76; 2011-12-09: 4.76; 2011-12-12: 4.76; 2011-12-13: 4.76; 2011-12-14: 4.76; 2011-12-15: 4.76; 2011-12-16: 4.76; 2011-12-19: 4.76; 2011-12-20: 4.76; 2011-12-21: 4.76; 2011-12-22: 4.76; 2011-12-23: 4.76; 2011-12-27: 4.76; 2011-12-28: 4.76; 2011-12-29: 4.76; 2011-12-30: 4.76; 2012-01-03: 4.76; 2012-01-04: 4.76; 2012-01-05: 4.76; 2012-01-06: 4.76; 2012-01-09: 4.76; 2012-01-10: 4.76; 2012-01-11: 4.76; 2012-01-12: 4.76; 2012-01-13: 4.76; 2012-01-16: 4.76; 2012-01-17: 4.76; 2012-01-18: 4.76; 2012-01-19: 4.76; 2012-01-20: 4.76; 2012-01-23: 4.76; 2012-01-24: 4.76; 2012-01-25: 4.76; 2012-01-26: 4.76; 2012-01-27: 4.76; 2012-01-30: 4.76; 2012-01-31: 4.76; 2012-02-01: 4.76; 2012-02-02: 4.76; 2012-02-03: 4.76; 2012-02-06: 4.76; 2012-02-07: 4.76; 2012-02-08: 4.76; 2012-02-09: 4.76; 2012-02-10: 4.33; 2012-02-13: 4.33; 2012-02-14: 4.33; 2012-02-15: 4.33; 2012-02-16: 4.33; 2012-02-17: 4.33; 2012-02-20: 4.33; 2012-02-21: 4.33; 2012-02-22: 4.33; 2012-02-23: 4.33; 2012-02-24: 4.33; 2012-02-27: 4.33; 2012-02-28: 4.33; 2012-02-29: 4.33; 2012-03-01: 4.33; 2012-03-02: 4.33; 2012-03-05: 4.33; 2012-03-06: 4.33; 2012-03-07: 4.33; 2012-03-08: 4.33; 2012-03-09: 4.33; 2012-03-12: 4.33; 2012-03-13: 4.33; 2012-03-14: 4.33; 2012-03-15: 4.33; 2012-03-16: 4.33; 2012-03-19: 4.33; 2012-03-20: 4.33; 2012-03-21: 4.33; 2012-03-22: 4.33; 2012-03-23: 4.33; 2012-03-26: 4.33; 2012-03-27: 4.33; 2012-03-28: 4.33; 2012-03-29: 4.33; 2012-03-30: 4.33; 2012-04-02: 4.33; 2012-04-03: 4.33; 2012-04-04: 4.33; 2012-04-05: 4.33; 2012-04-06: 4.33; 2012-04-09: 4.33; 2012-04-10: 4.33; 2012-04-11: 4.33; 2012-04-12: 4.33; 2012-04-13: 4.33; 2012-04-16: 4.33; 2012-04-17: 4.33; 2012-04-18: 4.33; 2012-04-19: 4.33; 2012-04-20: 4.33; 2012-04-23: 4.33; 2012-04-24: 4.33; 2012-04-25: 4.33; 2012-04-26: 4.33; 2012-04-27: 4.33; 2012-04-30: 4.33; 2012-05-01: 4.33; 2012-05-02: 4.33; 2012-05-03: 4.33; 2012-05-04: 4.33; 2012-05-07: 4.33; 2012-05-08: 4.33; 2012-05-09: 4.33; 2012-05-10: 4.33; 2012-05-11: 4.33; 2012-05-14: 4.33; 2012-05-15: 4.33; 2012-05-16: 4.33; 2012-05-17: 4.33; 2012-05-18: 4.33; 2012-05-21: 4.33; 2012-05-22: 4.33; 2012-05-23: 4.33; 2012-05-24: 4.33; 2012-05-25: 4.33; 2012-05-29: 4.33; 2012-05-30: 4.33; 2012-05-31: 4.33; 2012-06-01: 4.33; 2012-06-04: 4.33; 2012-06-05: 4.33; 2012-06-06: 4.33; 2012-06-07: 4.33; 2012-06-08: 4.33; 2012-06-11: 4.33; 2012-06-12: 4.33; 2012-06-13: 4.33; 2012-06-14: 4.33; 2012-06-15: 4.33; 2012-06-18: 4.33; 2012-06-19: 4.33; 2012-06-20: 4.33; 2012-06-21: 4.33; 2012-06-22: 4.33; 2012-06-25: 4.33; 2012-06-26: 4.33; 2012-06-27: 4.33; 2012-06-28: 4.33; 2012-06-29: 4.33; 2012-07-02: 4.33; 2012-07-03: 4.33; 2012-07-05: 4.33; 2012-07-06: 4.33; 2012-07-09: 4.33; 2012-07-10: 4.33; 2012-07-11: 4.33; 2012-07-12: 4.33; 2012-07-13: 4.33; 2012-07-16: 4.33; 2012-07-17: 4.33; 2012-07-18: 4.33; 2012-07-19: 4.33; 2012-07-20: 4.33; 2012-07-23: 4.33; 2012-07-24: 4.33; 2012-07-25: 4.33; 2012-07-26: 4.33; 2012-07-27: 4.33; 2012-07-30: 4.33; 2012-07-31: 4.33; 2012-08-01: 4.33; 2012-08-02: 4.33; 2012-08-03: 4.33; 2012-08-06: 4.33; 2012-08-07: 4.33; 2012-08-08: 4.33; 2012-08-09: 4.33; 2012-08-10: 4.33; 2012-08-13: 4.33; 2012-08-14: 4.33; 2012-08-15: 4.33; 2012-08-16: 4.33; 2012-08-17: 4.33; 2012-08-20: 1.73
EC1950 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 4 | 201.6 | 201.6 | 0% | 2011-11-10 | 2012-08-20 | 310.6 | 901.53 | At Completion Labor Units | 2011-11-10: 0.95; 2011-11-11: 4.76; 2011-11-14: 4.76; 2011-11-15: 4.76; 2011-11-16: 4.76; 2011-11-17: 4.76; 2011-11-18: 4.76; 2011-11-21: 4.76; 2011-11-22: 4.76; 2011-11-23: 4.76; 2011-11-25: 4.76; 2011-11-28: 4.76; 2011-11-29: 4.76; 2011-11-30: 4.76; 2011-12-01: 4.76; 2011-12-02: 4.76; 2011-12-05: 4.76; 2011-12-06: 4.76; 2011-12-07: 4.76; 2011-12-08: 4.76; 2011-12-09: 4.76; 2011-12-12: 4.76; 2011-12-13: 4.76; 2011-12-14: 4.76; 2011-12-15: 4.76; 2011-12-16: 4.76; 2011-12-19: 4.76; 2011-12-20: 4.76; 2011-12-21: 4.76; 2011-12-22: 4.76; 2011-12-23: 4.76; 2011-12-27: 4.76; 2011-12-28: 4.76; 2011-12-29: 4.76; 2011-12-30: 4.76; 2012-01-03: 4.76; 2012-01-04: 4.76; 2012-01-05: 4.76; 2012-01-06: 4.76; 2012-01-09: 4.76; 2012-01-10: 4.76; 2012-01-11: 4.76; 2012-01-12: 4.76; 2012-01-13: 4.76; 2012-01-16: 4.76; 2012-01-17: 4.76; 2012-01-18: 4.76; 2012-01-19: 4.76; 2012-01-20: 4.76; 2012-01-23: 4.76; 2012-01-24: 4.76; 2012-01-25: 4.76; 2012-01-26: 4.76; 2012-01-27: 4.76; 2012-01-30: 4.76; 2012-01-31: 4.76; 2012-02-01: 4.76; 2012-02-02: 4.76; 2012-02-03: 4.76; 2012-02-06: 4.76; 2012-02-07: 4.76; 2012-02-08: 4.76; 2012-02-09: 4.76; 2012-02-10: 4.76; 2012-02-13: 4.76; 2012-02-14: 4.76; 2012-02-15: 4.76; 2012-02-16: 4.76; 2012-02-17: 4.33; 2012-02-20: 4.33; 2012-02-21: 4.33; 2012-02-22: 4.33; 2012-02-23: 4.33; 2012-02-24: 4.33; 2012-02-27: 4.33; 2012-02-28: 4.33; 2012-02-29: 4.33; 2012-03-01: 4.33; 2012-03-02: 4.33; 2012-03-05: 4.33; 2012-03-06: 4.33; 2012-03-07: 4.33; 2012-03-08: 4.33; 2012-03-09: 4.33; 2012-03-12: 4.33; 2012-03-13: 4.33; 2012-03-14: 4.33; 2012-03-15: 4.33; 2012-03-16: 4.33; 2012-03-19: 4.33; 2012-03-20: 4.33; 2012-03-21: 4.33; 2012-03-22: 4.33; 2012-03-23: 4.33; 2012-03-26: 4.33; 2012-03-27: 4.33; 2012-03-28: 4.33; 2012-03-29: 4.33; 2012-03-30: 4.33; 2012-04-02: 4.33; 2012-04-03: 4.33; 2012-04-04: 4.33; 2012-04-05: 4.33; 2012-04-06: 4.33; 2012-04-09: 4.33; 2012-04-10: 4.33; 2012-04-11: 4.33; 2012-04-12: 4.33; 2012-04-13: 4.33; 2012-04-16: 4.33; 2012-04-17: 4.33; 2012-04-18: 4.33; 2012-04-19: 4.33; 2012-04-20: 4.33; 2012-04-23: 4.33; 2012-04-24: 4.33; 2012-04-25: 4.33; 2012-04-26: 4.33; 2012-04-27: 4.33; 2012-04-30: 4.33; 2012-05-01: 4.33; 2012-05-02: 4.33; 2012-05-03: 4.33; 2012-05-04: 4.33; 2012-05-07: 4.33; 2012-05-08: 4.33; 2012-05-09: 4.33; 2012-05-10: 4.33; 2012-05-11: 4.33; 2012-05-14: 4.33; 2012-05-15: 4.33; 2012-05-16: 4.33; 2012-05-17: 4.33; 2012-05-18: 4.33; 2012-05-21: 4.33; 2012-05-22: 4.33; 2012-05-23: 4.33; 2012-05-24: 4.33; 2012-05-25: 4.33; 2012-05-29: 4.33; 2012-05-30: 4.33; 2012-05-31: 4.33; 2012-06-01: 4.33; 2012-06-04: 4.33; 2012-06-05: 4.33; 2012-06-06: 4.33; 2012-06-07: 4.33; 2012-06-08: 4.33; 2012-06-11: 4.33; 2012-06-12: 4.33; 2012-06-13: 4.33; 2012-06-14: 4.33; 2012-06-15: 4.33; 2012-06-18: 4.33; 2012-06-19: 4.33; 2012-06-20: 4.33; 2012-06-21: 4.33; 2012-06-22: 4.33; 2012-06-25: 4.33; 2012-06-26: 4.33; 2012-06-27: 4.33; 2012-06-28: 4.33; 2012-06-29: 4.33; 2012-07-02: 4.33; 2012-07-03: 4.33; 2012-07-05: 4.33; 2012-07-06: 4.33; 2012-07-09: 4.33; 2012-07-10: 4.33; 2012-07-11: 4.33; 2012-07-12: 4.33; 2012-07-13: 4.33; 2012-07-16: 4.33; 2012-07-17: 4.33; 2012-07-18: 4.33; 2012-07-19: 4.33; 2012-07-20: 4.33; 2012-07-23: 4.33; 2012-07-24: 4.33; 2012-07-25: 4.33; 2012-07-26: 4.33; 2012-07-27: 4.33; 2012-07-30: 4.33; 2012-07-31: 4.33; 2012-08-01: 4.33; 2012-08-02: 4.33; 2012-08-03: 4.33; 2012-08-06: 4.33; 2012-08-07: 4.33; 2012-08-08: 4.33; 2012-08-09: 4.33; 2012-08-10: 4.33; 2012-08-13: 4.33; 2012-08-14: 4.33; 2012-08-15: 4.33; 2012-08-16: 4.33; 2012-08-17: 4.33; 2012-08-20: 4.33; 2012-08-21: 4.33; 2012-08-22: 4.33; 2012-08-23: 4.33; 2012-08-24: 4.33; 2012-08-27: 1.73
EC2080 | 1345006 | 5000 | ACMEGC | Pool & Deck | 141.6 | 141.6 | 0% | 2012-03-19 | 2012-10-03 | 0 | 672 | At Completion Labor Units | 2012-03-19: 1.9; 2012-03-20: 4.75; 2012-03-21: 4.75; 2012-03-22: 4.75; 2012-03-23: 4.75; 2012-03-26: 4.75; 2012-03-27: 4.75; 2012-03-28: 4.75; 2012-03-29: 4.75; 2012-03-30: 4.75; 2012-04-02: 4.75; 2012-04-03: 4.75; 2012-04-04: 4.75; 2012-04-05: 4.75; 2012-04-06: 4.75; 2012-04-09: 4.75; 2012-04-10: 4.75; 2012-04-11: 4.75; 2012-04-12: 4.75; 2012-04-13: 4.75; 2012-04-16: 4.75; 2012-04-17: 4.75; 2012-04-18: 4.75; 2012-04-19: 4.75; 2012-04-20: 4.75; 2012-04-23: 4.75; 2012-04-24: 4.75; 2012-04-25: 4.75; 2012-04-26: 4.75; 2012-04-27: 4.75; 2012-04-30: 4.75; 2012-05-01: 4.75; 2012-05-02: 4.75; 2012-05-03: 4.75; 2012-05-04: 4.75; 2012-05-07: 4.75; 2012-05-08: 4.75; 2012-05-09: 4.75; 2012-05-10: 4.75; 2012-05-11: 4.75; 2012-05-14: 4.75; 2012-05-15: 4.75; 2012-05-16: 4.75; 2012-05-17: 4.75; 2012-05-18: 4.75; 2012-05-21: 4.75; 2012-05-22: 4.75; 2012-05-23: 4.75; 2012-05-24: 4.75; 2012-05-25: 4.75; 2012-05-29: 4.75; 2012-05-30: 4.75; 2012-05-31: 4.75; 2012-06-01: 4.75; 2012-06-04: 4.75; 2012-06-05: 4.75; 2012-06-06: 4.75; 2012-06-07: 4.75; 2012-06-08: 4.75; 2012-06-11: 4.75; 2012-06-12: 4.75; 2012-06-13: 4.75; 2012-06-14: 4.75; 2012-06-15: 4.75; 2012-06-18: 4.75; 2012-06-19: 4.75; 2012-06-20: 4.75; 2012-06-21: 4.75; 2012-06-22: 4.75; 2012-06-25: 4.75; 2012-06-26: 4.75; 2012-06-27: 4.75; 2012-06-28: 4.75; 2012-06-29: 4.75; 2012-07-02: 4.75; 2012-07-03: 4.75; 2012-07-05: 4.75; 2012-07-06: 4.75; 2012-07-09: 4.75; 2012-07-10: 4.75; 2012-07-11: 4.75; 2012-07-12: 4.75; 2012-07-13: 4.75; 2012-07-16: 4.75; 2012-07-17: 4.75; 2012-07-18: 4.75; 2012-07-19: 4.75; 2012-07-20: 4.75; 2012-07-23: 4.75; 2012-07-24: 4.75; 2012-07-25: 4.75; 2012-07-26: 4.75; 2012-07-27: 4.75; 2012-07-30: 4.75; 2012-07-31: 4.75; 2012-08-01: 4.75; 2012-08-02: 4.75; 2012-08-03: 4.75; 2012-08-06: 4.75; 2012-08-07: 4.75; 2012-08-08: 4.75; 2012-08-09: 4.75; 2012-08-10: 4.75; 2012-08-13: 4.75; 2012-08-14: 4.75; 2012-08-15: 4.75; 2012-08-16: 4.75; 2012-08-17: 4.75; 2012-08-20: 4.75; 2012-08-21: 4.75; 2012-08-22: 4.75; 2012-08-23: 4.75; 2012-08-24: 4.75; 2012-08-27: 4.75; 2012-08-28: 4.75; 2012-08-29: 4.75; 2012-08-30: 4.75; 2012-08-31: 4.75; 2012-09-04: 4.75; 2012-09-05: 4.75; 2012-09-06: 4.75; 2012-09-07: 4.75; 2012-09-10: 4.75; 2012-09-11: 4.75; 2012-09-12: 4.75; 2012-09-13: 4.75; 2012-09-14: 4.75; 2012-09-17: 4.75; 2012-09-18: 4.75; 2012-09-19: 4.75; 2012-09-20: 4.75; 2012-09-21: 4.75; 2012-09-24: 4.75; 2012-09-25: 4.75; 2012-09-26: 4.75; 2012-09-27: 4.75; 2012-09-28: 4.75; 2012-10-01: 4.75; 2012-10-02: 4.75; 2012-10-03: 4.75; 2012-10-04: 4.75; 2012-10-05: 4.75; 2012-10-08: 0.95
EC2270 | 1345006 | 5000 | ACMEGC | Pergola and Amenities | 50.4 | 50.4 | 0% | 2012-09-05 | 2012-11-14 | 0 | 403.2 | At Completion Labor Units | 2012-09-05: 6.4; 2012-09-06: 8; 2012-09-07: 8; 2012-09-10: 8; 2012-09-11: 8; 2012-09-12: 8; 2012-09-13: 8; 2012-09-14: 8; 2012-09-17: 8; 2012-09-18: 8; 2012-09-19: 8; 2012-09-20: 8; 2012-09-21: 8; 2012-09-24: 8; 2012-09-25: 8; 2012-09-26: 8; 2012-09-27: 8; 2012-09-28: 8; 2012-10-01: 8; 2012-10-02: 8; 2012-10-03: 8; 2012-10-04: 8; 2012-10-05: 8; 2012-10-08: 8; 2012-10-09: 8; 2012-10-10: 8; 2012-10-11: 8; 2012-10-12: 8; 2012-10-15: 8; 2012-10-16: 8; 2012-10-17: 8; 2012-10-18: 8; 2012-10-19: 8; 2012-10-22: 8; 2012-10-23: 8; 2012-10-24: 8; 2012-10-25: 8; 2012-10-26: 8; 2012-10-29: 8; 2012-10-30: 8; 2012-10-31: 8; 2012-11-01: 8; 2012-11-02: 8; 2012-11-05: 8; 2012-11-06: 8; 2012-11-07: 8; 2012-11-08: 8; 2012-11-09: 8; 2012-11-12: 8; 2012-11-13: 8; 2012-11-14: 4.8
EC1090 | 1345006 | 1000 | ACMEGC | Building Pad Including UG Utils | 48 | 48 | 0% | 2010-11-02 | 2011-01-06 | 0 | 384 | At Completion Labor Units | 2010-11-02: 8; 2010-11-03: 8; 2010-11-04: 8; 2010-11-05: 8; 2010-11-08: 8; 2010-11-09: 8; 2010-11-10: 8; 2010-11-11: 8; 2010-11-12: 8; 2010-11-15: 8; 2010-11-16: 8; 2010-11-17: 8; 2010-11-18: 8; 2010-11-19: 8; 2010-11-22: 8; 2010-11-23: 8; 2010-11-24: 8; 2010-11-26: 8; 2010-11-29: 8; 2010-11-30: 8; 2010-12-01: 8; 2010-12-02: 8; 2010-12-03: 8; 2010-12-06: 8; 2010-12-07: 8; 2010-12-08: 8; 2010-12-09: 8; 2010-12-10: 8; 2010-12-13: 8; 2010-12-14: 8; 2010-12-15: 8; 2010-12-16: 8; 2010-12-17: 8; 2010-12-20: 8; 2010-12-21: 8; 2010-12-22: 8; 2010-12-23: 8; 2010-12-27: 8; 2010-12-28: 8; 2010-12-29: 8; 2010-12-30: 8; 2011-01-03: 8; 2011-01-04: 8; 2011-01-05: 8; 2011-01-06: 8; 2011-01-07: 8; 2011-01-10: 8; 2011-01-11: 8
EC1140 | 1345006 | 1000 | MASON | First Floor Masonry Structure | 12 | 12 | 0% | 2011-01-07 | 2011-01-24 | 0 | 96 | At Completion Labor Units | 2011-01-07: 8; 2011-01-10: 8; 2011-01-11: 8; 2011-01-12: 8; 2011-01-13: 8; 2011-01-14: 8; 2011-01-17: 8; 2011-01-18: 8; 2011-01-19: 8; 2011-01-20: 8; 2011-01-21: 8; 2011-01-24: 8
EC1170 | 1345006 | 1000 | STDPAV | Second Floor Slab & Collar Beam | 24 | 24 | 0% | 2011-01-25 | 2011-02-25 | 0 | 192 | At Completion Labor Units | 2011-01-25: 8; 2011-01-26: 8; 2011-01-27: 8; 2011-01-28: 8; 2011-01-31: 8; 2011-02-01: 8; 2011-02-02: 8; 2011-02-03: 8; 2011-02-04: 8; 2011-02-07: 8; 2011-02-08: 8; 2011-02-09: 8; 2011-02-10: 8; 2011-02-11: 8; 2011-02-14: 8; 2011-02-15: 8; 2011-02-16: 8; 2011-02-17: 8; 2011-02-18: 8; 2011-02-21: 8; 2011-02-22: 8; 2011-02-23: 8; 2011-02-24: 8; 2011-02-25: 8
EC1190 | 1345006 | 1000 | MASON | Second Floor Masonry Structure | 12 | 12 | 0% | 2011-02-28 | 2011-03-15 | 0 | 96 | At Completion Labor Units | 2011-02-28: 8; 2011-03-01: 8; 2011-03-02: 8; 2011-03-03: 8; 2011-03-04: 8; 2011-03-07: 8; 2011-03-08: 8; 2011-03-09: 8; 2011-03-10: 8; 2011-03-11: 8; 2011-03-14: 8; 2011-03-15: 8
EC1210 | 1345006 | 1000 | STDPAV | Third Floor Slab & Collar Beam | 24 | 24 | 0% | 2011-03-16 | 2011-04-18 | 0 | 192 | At Completion Labor Units | 2011-03-16: 8; 2011-03-17: 8; 2011-03-18: 8; 2011-03-21: 8; 2011-03-22: 8; 2011-03-23: 8; 2011-03-24: 8; 2011-03-25: 8; 2011-03-28: 8; 2011-03-29: 8; 2011-03-30: 8; 2011-03-31: 8; 2011-04-01: 8; 2011-04-04: 8; 2011-04-05: 8; 2011-04-06: 8; 2011-04-07: 8; 2011-04-08: 8; 2011-04-11: 8; 2011-04-12: 8; 2011-04-13: 8; 2011-04-14: 8; 2011-04-15: 8; 2011-04-18: 8
EC1240 | 1345006 | 1000 | MASON | Third Floor Masonry Structure | 12 | 12 | 0% | 2011-04-19 | 2011-05-04 | 0 | 96 | At Completion Labor Units | 2011-04-19: 8; 2011-04-20: 8; 2011-04-21: 8; 2011-04-22: 8; 2011-04-25: 8; 2011-04-26: 8; 2011-04-27: 8; 2011-04-28: 8; 2011-04-29: 8; 2011-05-02: 8; 2011-05-03: 8; 2011-05-04: 8
EC1250 | 1345006 | 1000 | STDPAV | Fourth Floor Slab & Collar Beam | 24 | 24 | 0% | 2011-05-05 | 2011-06-07 | 0 | 192 | At Completion Labor Units | 2011-05-05: 8; 2011-05-06: 8; 2011-05-09: 8; 2011-05-10: 8; 2011-05-11: 8; 2011-05-12: 8; 2011-05-13: 8; 2011-05-16: 8; 2011-05-17: 8; 2011-05-18: 8; 2011-05-19: 8; 2011-05-20: 8; 2011-05-23: 8; 2011-05-24: 8; 2011-05-25: 8; 2011-05-26: 8; 2011-05-27: 8; 2011-05-31: 8; 2011-06-01: 8; 2011-06-02: 8; 2011-06-03: 8; 2011-06-06: 8; 2011-06-07: 8; 2011-06-08: 8
EC1300 | 1345006 | 1000 | MASON | Fourth Floor Masonry Structure | 12 | 12 | 0% | 2011-06-08 | 2011-06-23 | 0 | 96 | At Completion Labor Units | 2011-06-08: 8; 2011-06-09: 8; 2011-06-10: 8; 2011-06-13: 8; 2011-06-14: 8; 2011-06-15: 8; 2011-06-16: 8; 2011-06-17: 8; 2011-06-20: 8; 2011-06-21: 8; 2011-06-22: 8; 2011-06-23: 8
EC1310 | 1345006 | 1000 | STDPAV | Roof Slab | 24 | 24 | 0% | 2011-06-24 | 2011-07-27 | 0 | 192 | At Completion Labor Units | 2011-06-24: 8; 2011-06-27: 8; 2011-06-28: 8; 2011-06-29: 8; 2011-06-30: 8; 2011-07-01: 8; 2011-07-05: 8; 2011-07-06: 8; 2011-07-07: 8; 2011-07-08: 8; 2011-07-11: 8; 2011-07-12: 8; 2011-07-13: 8; 2011-07-14: 8; 2011-07-15: 8; 2011-07-18: 8; 2011-07-19: 8; 2011-07-20: 8; 2011-07-21: 8; 2011-07-22: 8; 2011-07-25: 8; 2011-07-26: 8; 2011-07-27: 8; 2011-07-28: 8
EC1340 | 1345006 | 1000 | MASON | Stair and Elevator Masonry Structure | 4.8 | 4.8 | 0% | 2011-07-28 | 2011-08-03 | 0 | 38.4 | At Completion Labor Units | 2011-07-28: 8; 2011-07-29: 8; 2011-08-01: 8; 2011-08-02: 8; 2011-08-03: 6.4
EC1350 | 1345006 | 1000 | STDPAV | Roof Slab/Collar Beam | 12 | 12 | 0% | 2011-08-03 | 2011-08-19 | 0 | 96 | At Completion Labor Units | 2011-08-03: 1.6; 2011-08-04: 8; 2011-08-05: 8; 2011-08-08: 8; 2011-08-09: 8; 2011-08-10: 8; 2011-08-11: 8; 2011-08-12: 8; 2011-08-15: 8; 2011-08-16: 8; 2011-08-17: 8; 2011-08-18: 8; 2011-08-19: 6.4
EC1390 | 1345006 | 2000 | ACMEGC | Place Roof Trusses and Sheathing | 24 | 24 | 0% | 2011-08-19 | 2011-09-22 | 81.2 | 384 | At Completion Labor Units | 2011-08-19: 3.2; 2011-08-22: 16; 2011-08-23: 16; 2011-08-24: 16; 2011-08-25: 16; 2011-08-26: 16; 2011-08-29: 16; 2011-08-30: 16; 2011-08-31: 16; 2011-09-01: 16; 2011-09-02: 16; 2011-09-06: 16; 2011-09-07: 16; 2011-09-08: 16; 2011-09-09: 16; 2011-09-12: 16; 2011-09-13: 16; 2011-09-14: 16; 2011-09-15: 16; 2011-09-16: 16; 2011-09-19: 16; 2011-09-20: 16; 2011-09-21: 16; 2011-09-22: 16; 2011-09-23: 12.8
EC1400 | 1345006 | 2000 | MECH | Place Mechanical Equipment Supports | 24 | 24 | 0% | 2011-08-19 | 2011-09-22 | 259.4 | 192 | At Completion Labor Units | 2011-08-19: 1.6; 2011-08-22: 8; 2011-08-23: 8; 2011-08-24: 8; 2011-08-25: 8; 2011-08-26: 8; 2011-08-29: 8; 2011-08-30: 8; 2011-08-31: 8; 2011-09-01: 8; 2011-09-02: 8; 2011-09-06: 8; 2011-09-07: 8; 2011-09-08: 8; 2011-09-09: 8; 2011-09-12: 8; 2011-09-13: 8; 2011-09-14: 8; 2011-09-15: 8; 2011-09-16: 8; 2011-09-19: 8; 2011-09-20: 8; 2011-09-21: 8; 2011-09-22: 8; 2011-09-23: 6.4
EC1540 | 1345006 | 2000 | ACMEGC | Felt and Tile Roofing | 45.6 | 45.6 | 0% | 2011-09-22 | 2011-11-25 | 81.2 | 364.8 | At Completion Labor Units | 2011-09-22: 1.6; 2011-09-23: 8; 2011-09-26: 8; 2011-09-27: 8; 2011-09-28: 8; 2011-09-29: 8; 2011-09-30: 8; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 8; 2011-10-28: 8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 8; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 3.2
EC1780 | 1345006 | 2000 |  | Roof Complete | 0 | 0 | 0% |  | 2011-11-25 | 374.6 | 0 | At Completion Labor Units
EC1530 | 1345006 | 2000 | ACMEGC | Built-Up Asphalt Roofing | 33.6 | 33.6 | 0% | 2011-09-22 | 2011-11-09 | 259.4 | 268.8 | At Completion Labor Units | 2011-09-22: 1.6; 2011-09-23: 8; 2011-09-26: 8; 2011-09-27: 8; 2011-09-28: 8; 2011-09-29: 8; 2011-09-30: 8; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 8; 2011-10-28: 8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 3.2
EC1420 | 1345006 | 6000 |  | Start Garage | 0 | 0 | 0% | 2011-06-27 |  | 116.6 | 0 | At Completion Labor Units
EC1430 | 1345006 | 6000 | STEEL | Shop Drawings, Review & Approval | 72 | 72 | 0% | 2011-06-27 | 2011-10-04 | 116.6 | 614.4 | At Completion Labor Units | 2011-06-27: 8.68; 2011-06-28: 8.68; 2011-06-29: 8.68; 2011-06-30: 8.68; 2011-07-01: 8.68; 2011-07-05: 8.68; 2011-07-06: 8.68; 2011-07-07: 8.68; 2011-07-08: 8.68; 2011-07-11: 8.68; 2011-07-12: 8.68; 2011-07-13: 8.68; 2011-07-14: 8.68; 2011-07-15: 8.68; 2011-07-18: 8.68; 2011-07-19: 8.68; 2011-07-20: 8.68; 2011-07-21: 8.68; 2011-07-22: 8.68; 2011-07-25: 8.68; 2011-07-26: 8.68; 2011-07-27: 8.68; 2011-07-28: 8.68; 2011-07-29: 8.68; 2011-08-01: 8.68; 2011-08-02: 8.68; 2011-08-03: 8.68; 2011-08-04: 8.68; 2011-08-05: 8.68; 2011-08-08: 8.68; 2011-08-09: 8.68; 2011-08-10: 8.68; 2011-08-11: 8.68; 2011-08-12: 8.68; 2011-08-15: 8.68; 2011-08-16: 8.68; 2011-08-17: 8.68; 2011-08-18: 8.68; 2011-08-19: 8.68; 2011-08-22: 8.68; 2011-08-23: 8.68; 2011-08-24: 8.68; 2011-08-25: 8.68; 2011-08-26: 8.68; 2011-08-29: 8.68; 2011-08-30: 8.68; 2011-08-31: 8.68; 2011-09-01: 8.68; 2011-09-02: 8.68; 2011-09-06: 8.68; 2011-09-07: 8.68; 2011-09-08: 8.68; 2011-09-09: 8.68; 2011-09-12: 8.68; 2011-09-13: 8.68; 2011-09-14: 8.68; 2011-09-15: 8.68; 2011-09-16: 8.68; 2011-09-19: 8.68; 2011-09-20: 8.68; 2011-09-21: 8.68; 2011-09-22: 8.68; 2011-09-23: 8.68; 2011-09-26: 8.68; 2011-09-27: 8.68; 2011-09-28: 8.68; 2011-09-29: 8.68; 2011-09-30: 8.68; 2011-10-03: 8.68; 2011-10-04: 6.94; 2011-10-05: 4.34; 2011-10-06: 4.34
EC1810 | 1345006 | 6000 | STEEL | Fab & Delivery | 72 | 72 | 0% | 2011-10-05 | 2012-01-12 | 116.6 | 460.8 | At Completion Labor Units | 2011-10-05: 6.51; 2011-10-06: 6.51; 2011-10-07: 6.51; 2011-10-10: 6.51; 2011-10-11: 6.51; 2011-10-12: 6.51; 2011-10-13: 6.51; 2011-10-14: 6.51; 2011-10-17: 6.51; 2011-10-18: 6.51; 2011-10-19: 6.51; 2011-10-20: 6.51; 2011-10-21: 6.51; 2011-10-24: 6.51; 2011-10-25: 6.51; 2011-10-26: 6.51; 2011-10-27: 6.51; 2011-10-28: 6.51; 2011-10-31: 6.51; 2011-11-01: 6.51; 2011-11-02: 6.51; 2011-11-03: 6.51; 2011-11-04: 6.51; 2011-11-07: 6.51; 2011-11-08: 6.51; 2011-11-09: 6.51; 2011-11-10: 6.51; 2011-11-11: 6.51; 2011-11-14: 6.51; 2011-11-15: 6.51; 2011-11-16: 6.51; 2011-11-17: 6.51; 2011-11-18: 6.51; 2011-11-21: 6.51; 2011-11-22: 6.51; 2011-11-23: 6.51; 2011-11-25: 6.51; 2011-11-28: 6.51; 2011-11-29: 6.51; 2011-11-30: 6.51; 2011-12-01: 6.51; 2011-12-02: 6.51; 2011-12-05: 6.51; 2011-12-06: 6.51; 2011-12-07: 6.51; 2011-12-08: 6.51; 2011-12-09: 6.51; 2011-12-12: 6.51; 2011-12-13: 6.51; 2011-12-14: 6.51; 2011-12-15: 6.51; 2011-12-16: 6.51; 2011-12-19: 6.51; 2011-12-20: 6.51; 2011-12-21: 6.51; 2011-12-22: 6.51; 2011-12-23: 6.51; 2011-12-27: 6.51; 2011-12-28: 6.51; 2011-12-29: 6.51; 2011-12-30: 6.51; 2012-01-03: 6.51; 2012-01-04: 6.51; 2012-01-05: 6.51; 2012-01-06: 6.51; 2012-01-09: 6.51; 2012-01-10: 6.51; 2012-01-11: 6.51; 2012-01-12: 6.51; 2012-01-13: 5.21; 2012-01-16: 3.25; 2012-01-17: 3.25
EC2090 | 1345006 | 6000 | STEEL | Erect Precast Structure | 96 | 96 | 0% | 2012-01-13 | 2012-05-25 | 116.6 | 576 | At Completion Labor Units | 2012-01-13: 6.09; 2012-01-16: 6.09; 2012-01-17: 6.09; 2012-01-18: 6.09; 2012-01-19: 6.09; 2012-01-20: 6.09; 2012-01-23: 6.09; 2012-01-24: 6.09; 2012-01-25: 6.09; 2012-01-26: 6.09; 2012-01-27: 6.09; 2012-01-30: 6.09; 2012-01-31: 6.09; 2012-02-01: 6.09; 2012-02-02: 6.09; 2012-02-03: 6.09; 2012-02-06: 6.09; 2012-02-07: 6.09; 2012-02-08: 6.09; 2012-02-09: 6.09; 2012-02-10: 6.09; 2012-02-13: 6.09; 2012-02-14: 6.09; 2012-02-15: 6.09; 2012-02-16: 6.09; 2012-02-17: 6.09; 2012-02-20: 6.09; 2012-02-21: 6.09; 2012-02-22: 6.09; 2012-02-23: 6.09; 2012-02-24: 6.09; 2012-02-27: 6.09; 2012-02-28: 6.09; 2012-02-29: 6.09; 2012-03-01: 6.09; 2012-03-02: 6.09; 2012-03-05: 6.09; 2012-03-06: 6.09; 2012-03-07: 6.09; 2012-03-08: 6.09; 2012-03-09: 6.09; 2012-03-12: 6.09; 2012-03-13: 6.09; 2012-03-14: 6.09; 2012-03-15: 6.09; 2012-03-16: 6.09; 2012-03-19: 6.09; 2012-03-20: 6.09; 2012-03-21: 6.09; 2012-03-22: 6.09; 2012-03-23: 6.09; 2012-03-26: 6.09; 2012-03-27: 6.09; 2012-03-28: 6.09; 2012-03-29: 6.09; 2012-03-30: 6.09; 2012-04-02: 6.09; 2012-04-03: 6.09; 2012-04-04: 6.09; 2012-04-05: 6.09; 2012-04-06: 6.09; 2012-04-09: 6.09; 2012-04-10: 6.09; 2012-04-11: 6.09; 2012-04-12: 6.09; 2012-04-13: 6.09; 2012-04-16: 6.09; 2012-04-17: 6.09; 2012-04-18: 6.09; 2012-04-19: 6.09; 2012-04-20: 6.09; 2012-04-23: 6.09; 2012-04-24: 6.09; 2012-04-25: 6.09; 2012-04-26: 6.09; 2012-04-27: 6.09; 2012-04-30: 6.09; 2012-05-01: 6.09; 2012-05-02: 6.09; 2012-05-03: 6.09; 2012-05-04: 6.09; 2012-05-07: 6.09; 2012-05-08: 6.09; 2012-05-09: 6.09; 2012-05-10: 6.09; 2012-05-11: 6.09; 2012-05-14: 6.09; 2012-05-15: 6.09; 2012-05-16: 6.09; 2012-05-17: 6.09; 2012-05-18: 6.09; 2012-05-21: 6.09; 2012-05-22: 6.09; 2012-05-23: 4.59; 2012-05-24: 2.33; 2012-05-25: 2.33
EC2280 | 1345006 | 6000 | STEEL | Fire Protection and Lighting | 72 | 72 | 0% | 2012-05-28 | 2012-09-04 | 266.2 | 480 | At Completion Labor Units | 2012-05-29: 6.67; 2012-05-30: 6.67; 2012-05-31: 6.67; 2012-06-01: 6.67; 2012-06-04: 6.67; 2012-06-05: 6.67; 2012-06-06: 6.67; 2012-06-07: 6.67; 2012-06-08: 6.67; 2012-06-11: 6.67; 2012-06-12: 6.67; 2012-06-13: 6.67; 2012-06-14: 6.67; 2012-06-15: 6.67; 2012-06-18: 6.67; 2012-06-19: 6.67; 2012-06-20: 6.67; 2012-06-21: 6.67; 2012-06-22: 6.67; 2012-06-25: 6.67; 2012-06-26: 6.67; 2012-06-27: 6.67; 2012-06-28: 6.67; 2012-06-29: 6.67; 2012-07-02: 6.67; 2012-07-03: 6.67; 2012-07-05: 6.67; 2012-07-06: 6.67; 2012-07-09: 6.67; 2012-07-10: 6.67; 2012-07-11: 6.67; 2012-07-12: 6.67; 2012-07-13: 6.67; 2012-07-16: 6.67; 2012-07-17: 6.67; 2012-07-18: 6.67; 2012-07-19: 6.67; 2012-07-20: 6.67; 2012-07-23: 6.67; 2012-07-24: 6.67; 2012-07-25: 6.67; 2012-07-26: 6.67; 2012-07-27: 6.67; 2012-07-30: 6.67; 2012-07-31: 6.67; 2012-08-01: 6.67; 2012-08-02: 6.67; 2012-08-03: 6.67; 2012-08-06: 6.67; 2012-08-07: 6.67; 2012-08-08: 6.67; 2012-08-09: 6.67; 2012-08-10: 6.67; 2012-08-13: 6.67; 2012-08-14: 6.67; 2012-08-15: 6.67; 2012-08-16: 6.67; 2012-08-17: 6.67; 2012-08-20: 6.67; 2012-08-21: 6.67; 2012-08-22: 6.67; 2012-08-23: 6.67; 2012-08-24: 6.67; 2012-08-27: 6.67; 2012-08-28: 6.67; 2012-08-29: 6.67; 2012-08-30: 6.67; 2012-08-31: 6.67; 2012-09-04: 6.67; 2012-09-05: 6.67; 2012-09-06: 6.67; 2012-09-07: 6.67
EC2310 | 1345006 | 6000 | STEEL | Finishes, Barrier Cables & Striping | 72 | 72 | 0% | 2012-08-08 | 2012-11-15 | 266.2 | 768 | At Completion Labor Units | 2012-08-08: 10.67; 2012-08-09: 10.67; 2012-08-10: 10.67; 2012-08-13: 10.67; 2012-08-14: 10.67; 2012-08-15: 10.67; 2012-08-16: 10.67; 2012-08-17: 10.67; 2012-08-20: 10.67; 2012-08-21: 10.67; 2012-08-22: 10.67; 2012-08-23: 10.67; 2012-08-24: 10.67; 2012-08-27: 10.67; 2012-08-28: 10.67; 2012-08-29: 10.67; 2012-08-30: 10.67; 2012-08-31: 10.67; 2012-09-04: 10.67; 2012-09-05: 10.67; 2012-09-06: 10.67; 2012-09-07: 10.67; 2012-09-10: 10.67; 2012-09-11: 10.67; 2012-09-12: 10.67; 2012-09-13: 10.67; 2012-09-14: 10.67; 2012-09-17: 10.67; 2012-09-18: 10.67; 2012-09-19: 10.67; 2012-09-20: 10.67; 2012-09-21: 10.67; 2012-09-24: 10.67; 2012-09-25: 10.67; 2012-09-26: 10.67; 2012-09-27: 10.67; 2012-09-28: 10.67; 2012-10-01: 10.67; 2012-10-02: 10.67; 2012-10-03: 10.67; 2012-10-04: 10.67; 2012-10-05: 10.67; 2012-10-08: 10.67; 2012-10-09: 10.67; 2012-10-10: 10.67; 2012-10-11: 10.67; 2012-10-12: 10.67; 2012-10-15: 10.67; 2012-10-16: 10.67; 2012-10-17: 10.67; 2012-10-18: 10.67; 2012-10-19: 10.67; 2012-10-22: 10.67; 2012-10-23: 10.67; 2012-10-24: 10.67; 2012-10-25: 10.67; 2012-10-26: 10.67; 2012-10-29: 10.67; 2012-10-30: 10.67; 2012-10-31: 10.67; 2012-11-01: 10.67; 2012-11-02: 10.67; 2012-11-05: 10.67; 2012-11-06: 10.67; 2012-11-07: 10.67; 2012-11-08: 10.67; 2012-11-09: 10.67; 2012-11-12: 10.67; 2012-11-13: 10.67; 2012-11-14: 10.67; 2012-11-15: 10.67; 2012-11-16: 10.67
EC2400 | 1345006 | 6000 |  | Complete Garage | 0 | 0 | 0% |  | 2012-12-06 | 266.2 | 0 | At Completion Labor Units
EC2380 | 1345006 | 6000 | STEEL | Punchlist Garage | 14.4 | 14.4 | 0% | 2012-11-16 | 2012-12-06 | 266.2 | 192 | At Completion Labor Units | 2012-11-16: 16; 2012-11-19: 16; 2012-11-20: 16; 2012-11-21: 16; 2012-11-23: 16; 2012-11-26: 16; 2012-11-27: 16; 2012-11-28: 16; 2012-11-29: 16; 2012-11-30: 12.8; 2012-12-03: 8; 2012-12-04: 8; 2012-12-05: 8; 2012-12-06: 8; 2012-12-07: 3.2
EC2390 | 1345006 | 6000 |  | Complete Garage 1 | 0 | 0 | 0% |  | 2012-12-06 | 266.2 | 0 | At Completion Labor Units
EC2420 | 1345006 |  |  | Complete Building 2 | 0 | 0 | 0% |  | 2013-02-25 | 209.2 | 0 | At Completion Labor Units
EC1640 | 1345006 | 1000 | STDPAV | Roof Slab/Collar Beam | 24 | 24 | 0% | 2011-08-29 | 2011-09-30 | 116.6 | 192 | At Completion Labor Units | 2011-08-29: 4.8; 2011-08-30: 8; 2011-08-31: 8; 2011-09-01: 8; 2011-09-02: 8; 2011-09-06: 8; 2011-09-07: 8; 2011-09-08: 8; 2011-09-09: 8; 2011-09-12: 8; 2011-09-13: 8; 2011-09-14: 8; 2011-09-15: 8; 2011-09-16: 8; 2011-09-19: 8; 2011-09-20: 8; 2011-09-21: 8; 2011-09-22: 8; 2011-09-23: 8; 2011-09-26: 8; 2011-09-27: 8; 2011-09-28: 8; 2011-09-29: 8; 2011-09-30: 8; 2011-10-03: 3.2
EC1150 | 1345006 | 1000 | STDPAV | Building Slab Incl. UG Utils | 48 | 48 | 0% | 2010-11-30 | 2011-02-03 | 116.6 | 768 | At Completion Labor Units | 2010-11-30: 16; 2010-12-01: 16; 2010-12-02: 16; 2010-12-03: 16; 2010-12-06: 16; 2010-12-07: 16; 2010-12-08: 16; 2010-12-09: 16; 2010-12-10: 16; 2010-12-13: 16; 2010-12-14: 16; 2010-12-15: 16; 2010-12-16: 16; 2010-12-17: 16; 2010-12-20: 16; 2010-12-21: 16; 2010-12-22: 16; 2010-12-23: 16; 2010-12-27: 16; 2010-12-28: 16; 2010-12-29: 16; 2010-12-30: 16; 2011-01-03: 16; 2011-01-04: 16; 2011-01-05: 16; 2011-01-06: 16; 2011-01-07: 16; 2011-01-10: 16; 2011-01-11: 16; 2011-01-12: 16; 2011-01-13: 16; 2011-01-14: 16; 2011-01-17: 16; 2011-01-18: 16; 2011-01-19: 16; 2011-01-20: 16; 2011-01-21: 16; 2011-01-24: 16; 2011-01-25: 16; 2011-01-26: 16; 2011-01-27: 16; 2011-01-28: 16; 2011-01-31: 16; 2011-02-01: 16; 2011-02-02: 16; 2011-02-03: 16; 2011-02-04: 16; 2011-02-07: 16
EC1220 | 1345006 | 1000 | MASON | First Floor Masonry Structure | 12 | 12 | 0% | 2011-02-04 | 2011-02-21 | 116.6 | 96 | At Completion Labor Units | 2011-02-04: 8; 2011-02-07: 8; 2011-02-08: 8; 2011-02-09: 8; 2011-02-10: 8; 2011-02-11: 8; 2011-02-14: 8; 2011-02-15: 8; 2011-02-16: 8; 2011-02-17: 8; 2011-02-18: 8; 2011-02-21: 8
EC1230 | 1345006 | 1000 | STDPAV | Second Floor Slab & Collar Beam | 24 | 24 | 0% | 2011-02-22 | 2011-03-25 | 116.6 | 192 | At Completion Labor Units | 2011-02-22: 8; 2011-02-23: 8; 2011-02-24: 8; 2011-02-25: 8; 2011-02-28: 8; 2011-03-01: 8; 2011-03-02: 8; 2011-03-03: 8; 2011-03-04: 8; 2011-03-07: 8; 2011-03-08: 8; 2011-03-09: 8; 2011-03-10: 8; 2011-03-11: 8; 2011-03-14: 8; 2011-03-15: 8; 2011-03-16: 8; 2011-03-17: 8; 2011-03-18: 8; 2011-03-21: 8; 2011-03-22: 8; 2011-03-23: 8; 2011-03-24: 8; 2011-03-25: 8
EC1260 | 1345006 | 1000 | MASON | Second Floor Masonry Structure | 12 | 12 | 0% | 2011-03-28 | 2011-04-12 | 116.6 | 96 | At Completion Labor Units | 2011-03-28: 8; 2011-03-29: 8; 2011-03-30: 8; 2011-03-31: 8; 2011-04-01: 8; 2011-04-04: 8; 2011-04-05: 8; 2011-04-06: 8; 2011-04-07: 8; 2011-04-08: 8; 2011-04-11: 8; 2011-04-12: 8
EC1290 | 1345006 | 1000 | STDPAV | Third Floor Slab & Collar Beam | 24 | 24 | 0% | 2011-04-13 | 2011-05-16 | 116.6 | 192 | At Completion Labor Units | 2011-04-13: 8; 2011-04-14: 8; 2011-04-15: 8; 2011-04-18: 8; 2011-04-19: 8; 2011-04-20: 8; 2011-04-21: 8; 2011-04-22: 8; 2011-04-25: 8; 2011-04-26: 8; 2011-04-27: 8; 2011-04-28: 8; 2011-04-29: 8; 2011-05-02: 8; 2011-05-03: 8; 2011-05-04: 8; 2011-05-05: 8; 2011-05-06: 8; 2011-05-09: 8; 2011-05-10: 8; 2011-05-11: 8; 2011-05-12: 8; 2011-05-13: 8; 2011-05-16: 8
EC1320 | 1345006 | 1000 | MASON | Third Floor Masonry Structure | 12 | 12 | 0% | 2011-05-17 | 2011-06-01 | 116.6 | 96 | At Completion Labor Units | 2011-05-17: 8; 2011-05-18: 8; 2011-05-19: 8; 2011-05-20: 8; 2011-05-23: 8; 2011-05-24: 8; 2011-05-25: 8; 2011-05-26: 8; 2011-05-27: 8; 2011-05-31: 8; 2011-06-01: 8; 2011-06-02: 8
EC1330 | 1345006 | 1000 | STDPAV | Fourth Floor Slab & Collar Beam | 24 | 24 | 0% | 2011-06-02 | 2011-07-05 | 116.6 | 192 | At Completion Labor Units | 2011-06-02: 8; 2011-06-03: 8; 2011-06-06: 8; 2011-06-07: 8; 2011-06-08: 8; 2011-06-09: 8; 2011-06-10: 8; 2011-06-13: 8; 2011-06-14: 8; 2011-06-15: 8; 2011-06-16: 8; 2011-06-17: 8; 2011-06-20: 8; 2011-06-21: 8; 2011-06-22: 8; 2011-06-23: 8; 2011-06-24: 8; 2011-06-27: 8; 2011-06-28: 8; 2011-06-29: 8; 2011-06-30: 8; 2011-07-01: 8; 2011-07-05: 8; 2011-07-06: 8
EC1380 | 1345006 | 1000 | MASON | Fourth Floor Masonry Structure | 12 | 12 | 0% | 2011-07-06 | 2011-07-21 | 116.6 | 96 | At Completion Labor Units | 2011-07-06: 8; 2011-07-07: 8; 2011-07-08: 8; 2011-07-11: 8; 2011-07-12: 8; 2011-07-13: 8; 2011-07-14: 8; 2011-07-15: 8; 2011-07-18: 8; 2011-07-19: 8; 2011-07-20: 8; 2011-07-21: 8
EC1480 | 1345006 | 1000 | STDPAV | Roof Slab | 21.6 | 21.6 | 0% | 2011-07-22 | 2011-08-22 | 116.6 | 172.8 | At Completion Labor Units | 2011-07-22: 8; 2011-07-25: 8; 2011-07-26: 8; 2011-07-27: 8; 2011-07-28: 8; 2011-07-29: 8; 2011-08-01: 8; 2011-08-02: 8; 2011-08-03: 8; 2011-08-04: 8; 2011-08-05: 8; 2011-08-08: 8; 2011-08-09: 8; 2011-08-10: 8; 2011-08-11: 8; 2011-08-12: 8; 2011-08-15: 8; 2011-08-16: 8; 2011-08-17: 8; 2011-08-18: 8; 2011-08-19: 8; 2011-08-22: 4.8
EC1620 | 1345006 | 1000 | MASON | Stair and Elevator Masonry Structure | 4.8 | 4.8 | 0% | 2011-08-22 | 2011-08-29 | 116.6 | 38.4 | At Completion Labor Units | 2011-08-22: 3.2; 2011-08-23: 8; 2011-08-24: 8; 2011-08-25: 8; 2011-08-26: 8; 2011-08-29: 3.2
EC1710 | 1345006 | 2000 | ACMEGC | Place Roof Trusses and Sheathing | 24 | 24 | 0% | 2011-09-30 | 2011-11-03 | 116.6 | 384 | At Completion Labor Units | 2011-09-30: 9.6; 2011-10-03: 16; 2011-10-04: 16; 2011-10-05: 16; 2011-10-06: 16; 2011-10-07: 16; 2011-10-10: 16; 2011-10-11: 16; 2011-10-12: 16; 2011-10-13: 16; 2011-10-14: 16; 2011-10-17: 16; 2011-10-18: 16; 2011-10-19: 16; 2011-10-20: 16; 2011-10-21: 16; 2011-10-24: 16; 2011-10-25: 16; 2011-10-26: 16; 2011-10-27: 16; 2011-10-28: 16; 2011-10-31: 16; 2011-11-01: 16; 2011-11-02: 16; 2011-11-03: 6.4
EC1720 | 1345006 | 2000 | MECH | Place Mechanical Equipment Supports | 24 | 24 | 0% | 2011-09-30 | 2011-11-03 | 128.6 | 192 | At Completion Labor Units | 2011-09-30: 4.8; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 8; 2011-10-28: 8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 3.2
EC1860 | 1345006 | 2000 | ACMEGC | Built-Up Asphalt Roofing | 33.6 | 33.6 | 0% | 2011-11-03 | 2011-12-20 | 128.6 | 268.8 | At Completion Labor Units | 2011-11-03: 4.8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 8; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 8; 2011-11-29: 8; 2011-11-30: 8; 2011-12-01: 8; 2011-12-02: 8; 2011-12-05: 8; 2011-12-06: 8; 2011-12-07: 8; 2011-12-08: 8; 2011-12-09: 8; 2011-12-12: 8; 2011-12-13: 8; 2011-12-14: 8; 2011-12-15: 8; 2011-12-16: 8; 2011-12-19: 8; 2011-12-20: 8; 2011-12-21: 8
EC1870 | 1345006 | 2000 | ACMEGC | Felt and Tile Roofing | 45.6 | 45.6 | 0% | 2011-11-03 | 2012-01-05 | 116.6 | 364.8 | At Completion Labor Units | 2011-11-03: 4.8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 8; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 8; 2011-11-29: 8; 2011-11-30: 8; 2011-12-01: 8; 2011-12-02: 8; 2011-12-05: 8; 2011-12-06: 8; 2011-12-07: 8; 2011-12-08: 8; 2011-12-09: 8; 2011-12-12: 8; 2011-12-13: 8; 2011-12-14: 8; 2011-12-15: 8; 2011-12-16: 8; 2011-12-19: 8; 2011-12-20: 8; 2011-12-21: 8; 2011-12-22: 8; 2011-12-23: 8; 2011-12-27: 8; 2011-12-28: 8; 2011-12-29: 8; 2011-12-30: 8; 2012-01-03: 8; 2012-01-04: 8; 2012-01-05: 8; 2012-01-06: 8; 2012-01-09: 8; 2012-01-10: 8
EC2020 | 1345006 | 2000 |  | Roof Complete | 0 | 0 | 0% |  | 2012-01-05 | 116.6 | 0 | At Completion Labor Units
EC1730 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 1 | 24 | 24 | 0% | 2011-09-30 | 2011-11-03 | 248.8 | 384 | At Completion Labor Units | 2011-09-30: 9.6; 2011-10-03: 16; 2011-10-04: 16; 2011-10-05: 16; 2011-10-06: 16; 2011-10-07: 16; 2011-10-10: 16; 2011-10-11: 16; 2011-10-12: 16; 2011-10-13: 16; 2011-10-14: 16; 2011-10-17: 16; 2011-10-18: 16; 2011-10-19: 16; 2011-10-20: 16; 2011-10-21: 16; 2011-10-24: 16; 2011-10-25: 16; 2011-10-26: 16; 2011-10-27: 16; 2011-10-28: 16; 2011-10-31: 16; 2011-11-01: 16; 2011-11-02: 16; 2011-11-03: 6.4
EC1800 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 2 | 21.6 | 21.6 | 0% | 2011-10-27 | 2011-11-25 | 248.8 | 345.6 | At Completion Labor Units | 2011-10-27: 9.6; 2011-10-28: 16; 2011-10-31: 16; 2011-11-01: 16; 2011-11-02: 16; 2011-11-03: 16; 2011-11-04: 16; 2011-11-07: 16; 2011-11-08: 16; 2011-11-09: 16; 2011-11-10: 16; 2011-11-11: 16; 2011-11-14: 16; 2011-11-15: 16; 2011-11-16: 16; 2011-11-17: 16; 2011-11-18: 16; 2011-11-21: 16; 2011-11-22: 16; 2011-11-23: 16; 2011-11-25: 16; 2011-11-28: 16
EC1880 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 3 | 21.6 | 21.6 | 0% | 2011-11-21 | 2011-12-20 | 248.8 | 345.6 | At Completion Labor Units | 2011-11-21: 16; 2011-11-22: 16; 2011-11-23: 16; 2011-11-25: 16; 2011-11-28: 16; 2011-11-29: 16; 2011-11-30: 16; 2011-12-01: 16; 2011-12-02: 16; 2011-12-05: 16; 2011-12-06: 16; 2011-12-07: 16; 2011-12-08: 16; 2011-12-09: 16; 2011-12-12: 16; 2011-12-13: 16; 2011-12-14: 16; 2011-12-15: 16; 2011-12-16: 16; 2011-12-19: 16; 2011-12-20: 16; 2011-12-21: 9.6
EC1920 | 1345006 | 3000 | ACMEGC | Install Exterior Windows and Sliding Glass Doors Floor 4 | 24 | 24 | 0% | 2011-12-13 | 2012-01-16 | 248.8 | 384 | At Completion Labor Units | 2011-12-13: 6.4; 2011-12-14: 16; 2011-12-15: 16; 2011-12-16: 16; 2011-12-19: 16; 2011-12-20: 16; 2011-12-21: 16; 2011-12-22: 16; 2011-12-23: 16; 2011-12-27: 16; 2011-12-28: 16; 2011-12-29: 16; 2011-12-30: 16; 2012-01-03: 16; 2012-01-04: 16; 2012-01-05: 16; 2012-01-06: 16; 2012-01-09: 16; 2012-01-10: 16; 2012-01-11: 16; 2012-01-12: 16; 2012-01-13: 16; 2012-01-16: 16; 2012-01-17: 16; 2012-01-18: 9.6
EC1830 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor1 | 12 | 12 | 0% | 2011-10-28 | 2011-11-15 | 267.4 | 96 | At Completion Labor Units | 2011-10-28: 4.8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 3.2
EC1890 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor 2 | 9.6 | 9.6 | 0% | 2011-11-22 | 2011-12-05 | 262.8 | 76.8 | At Completion Labor Units | 2011-11-22: 8; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 8; 2011-11-29: 8; 2011-11-30: 8; 2011-12-01: 8; 2011-12-02: 8; 2011-12-05: 8; 2011-12-06: 4.8
EC1930 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor 3 | 12 | 12 | 0% | 2011-12-14 | 2011-12-30 | 255.8 | 96 | At Completion Labor Units | 2011-12-14: 3.2; 2011-12-15: 8; 2011-12-16: 8; 2011-12-19: 8; 2011-12-20: 8; 2011-12-21: 8; 2011-12-22: 8; 2011-12-23: 8; 2011-12-27: 8; 2011-12-28: 8; 2011-12-29: 8; 2011-12-30: 8; 2012-01-03: 4.8
EC1960 | 1345006 | 3000 | ACMEGC | Install Backing & Cauld Windows Floor 4 | 12 | 12 | 0% | 2012-01-10 | 2012-01-26 | 248.8 | 96 | At Completion Labor Units | 2012-01-10: 3.2; 2012-01-11: 8; 2012-01-12: 8; 2012-01-13: 8; 2012-01-16: 8; 2012-01-17: 8; 2012-01-18: 8; 2012-01-19: 8; 2012-01-20: 8; 2012-01-23: 8; 2012-01-24: 8; 2012-01-25: 8; 2012-01-26: 4.8
EC1940 | 1345006 | 3000 | ACMEGC | Stucco Bands | 12 | 12 | 0% | 2012-01-12 | 2012-01-30 | 248.8 | 96 | At Completion Labor Units | 2012-01-12: 3.2; 2012-01-13: 8; 2012-01-16: 8; 2012-01-17: 8; 2012-01-18: 8; 2012-01-19: 8; 2012-01-20: 8; 2012-01-23: 8; 2012-01-24: 8; 2012-01-25: 8; 2012-01-26: 8; 2012-01-27: 8; 2012-01-30: 4.8
EC1970 | 1345006 | 3000 | ACMEGC | Stucco Grey | 24 | 24 | 0% | 2012-01-30 | 2012-03-02 | 248.8 | 192 | At Completion Labor Units | 2012-01-30: 3.2; 2012-01-31: 8; 2012-02-01: 8; 2012-02-02: 8; 2012-02-03: 8; 2012-02-06: 8; 2012-02-07: 8; 2012-02-08: 8; 2012-02-09: 8; 2012-02-10: 8; 2012-02-13: 8; 2012-02-14: 8; 2012-02-15: 8; 2012-02-16: 8; 2012-02-17: 8; 2012-02-20: 8; 2012-02-21: 8; 2012-02-22: 8; 2012-02-23: 8; 2012-02-24: 8; 2012-02-27: 8; 2012-02-28: 8; 2012-02-29: 8; 2012-03-01: 8; 2012-03-02: 4.8
EC2050 | 1345006 | 3000 | ACMEGC | Stucco Finish Coat | 24 | 24 | 0% | 2012-03-02 | 2012-04-05 | 248.8 | 192 | At Completion Labor Units | 2012-03-02: 3.2; 2012-03-05: 8; 2012-03-06: 8; 2012-03-07: 8; 2012-03-08: 8; 2012-03-09: 8; 2012-03-12: 8; 2012-03-13: 8; 2012-03-14: 8; 2012-03-15: 8; 2012-03-16: 8; 2012-03-19: 8; 2012-03-20: 8; 2012-03-21: 8; 2012-03-22: 8; 2012-03-23: 8; 2012-03-26: 8; 2012-03-27: 8; 2012-03-28: 8; 2012-03-29: 8; 2012-03-30: 8; 2012-04-02: 8; 2012-04-03: 8; 2012-04-04: 8; 2012-04-05: 4.8
EC2130 | 1345006 | 3000 | ACMEGC | Caulk | 12 | 12 | 0% | 2012-04-05 | 2012-04-23 | 248.8 | 96 | At Completion Labor Units | 2012-04-05: 3.2; 2012-04-06: 8; 2012-04-09: 8; 2012-04-10: 8; 2012-04-11: 8; 2012-04-12: 8; 2012-04-13: 8; 2012-04-16: 8; 2012-04-17: 8; 2012-04-18: 8; 2012-04-19: 8; 2012-04-20: 8; 2012-04-23: 4.8
EC2160 | 1345006 | 3000 | ACMEGC | Stucco Band Trim | 24 | 24 | 0% | 2012-04-23 | 2012-05-25 | 248.8 | 192 | At Completion Labor Units | 2012-04-23: 3.2; 2012-04-24: 8; 2012-04-25: 8; 2012-04-26: 8; 2012-04-27: 8; 2012-04-30: 8; 2012-05-01: 8; 2012-05-02: 8; 2012-05-03: 8; 2012-05-04: 8; 2012-05-07: 8; 2012-05-08: 8; 2012-05-09: 8; 2012-05-10: 8; 2012-05-11: 8; 2012-05-14: 8; 2012-05-15: 8; 2012-05-16: 8; 2012-05-17: 8; 2012-05-18: 8; 2012-05-21: 8; 2012-05-22: 8; 2012-05-23: 8; 2012-05-24: 8; 2012-05-25: 4.8
EC2220 | 1345006 | 3000 | ACMEGC | Paint Exterior | 48 | 48 | 0% | 2012-06-01 | 2012-08-08 | 248.8 | 384 | At Completion Labor Units | 2012-06-01: 3.2; 2012-06-04: 8; 2012-06-05: 8; 2012-06-06: 8; 2012-06-07: 8; 2012-06-08: 8; 2012-06-11: 8; 2012-06-12: 8; 2012-06-13: 8; 2012-06-14: 8; 2012-06-15: 8; 2012-06-18: 8; 2012-06-19: 8; 2012-06-20: 8; 2012-06-21: 8; 2012-06-22: 8; 2012-06-25: 8; 2012-06-26: 8; 2012-06-27: 8; 2012-06-28: 8; 2012-06-29: 8; 2012-07-02: 8; 2012-07-03: 8; 2012-07-05: 8; 2012-07-06: 8; 2012-07-09: 8; 2012-07-10: 8; 2012-07-11: 8; 2012-07-12: 8; 2012-07-13: 8; 2012-07-16: 8; 2012-07-17: 8; 2012-07-18: 8; 2012-07-19: 8; 2012-07-20: 8; 2012-07-23: 8; 2012-07-24: 8; 2012-07-25: 8; 2012-07-26: 8; 2012-07-27: 8; 2012-07-30: 8; 2012-07-31: 8; 2012-08-01: 8; 2012-08-02: 8; 2012-08-03: 8; 2012-08-06: 8; 2012-08-07: 8; 2012-08-08: 8; 2012-08-09: 4.8
EC2300 | 1345006 | 3000 | ACMEGC | Demobilize Scaffolding | 12 | 12 | 0% | 2012-08-08 | 2012-08-24 | 248.8 | 96 | At Completion Labor Units | 2012-08-08: 3.2; 2012-08-09: 8; 2012-08-10: 8; 2012-08-13: 8; 2012-08-14: 8; 2012-08-15: 8; 2012-08-16: 8; 2012-08-17: 8; 2012-08-20: 8; 2012-08-21: 8; 2012-08-22: 8; 2012-08-23: 8; 2012-08-24: 4.8
EC1740 | 1345006 | 3000 | ACMEGC | Mobilize Scaffolding | 12 | 12 | 0% | 2011-09-30 | 2011-10-18 | 275.4 | 96 | At Completion Labor Units | 2011-09-30: 4.8; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 3.2
EC2320 | 1345006 | 3000 |  | Shell Complete | 0 | 0 | 0% |  | 2012-08-24 | 260.8 | 0 | At Completion Labor Units
EC2230 | 1345006 | 3000 | ACMEGC | Install Railings | 36 | 36 | 0% | 2012-06-01 | 2012-07-23 | 284.8 | 288 | At Completion Labor Units | 2012-06-01: 3.2; 2012-06-04: 8; 2012-06-05: 8; 2012-06-06: 8; 2012-06-07: 8; 2012-06-08: 8; 2012-06-11: 8; 2012-06-12: 8; 2012-06-13: 8; 2012-06-14: 8; 2012-06-15: 8; 2012-06-18: 8; 2012-06-19: 8; 2012-06-20: 8; 2012-06-21: 8; 2012-06-22: 8; 2012-06-25: 8; 2012-06-26: 8; 2012-06-27: 8; 2012-06-28: 8; 2012-06-29: 8; 2012-07-02: 8; 2012-07-03: 8; 2012-07-05: 8; 2012-07-06: 8; 2012-07-09: 8; 2012-07-10: 8; 2012-07-11: 8; 2012-07-12: 8; 2012-07-13: 8; 2012-07-16: 8; 2012-07-17: 8; 2012-07-18: 8; 2012-07-19: 8; 2012-07-20: 8; 2012-07-23: 8; 2012-07-24: 4.8
EC2150 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 3 | 196.8 | 196.8 | 0% | 2012-01-27 | 2012-10-29 | 209.2 | 896 | At Completion Labor Units | 2012-01-27: 4.88; 2012-01-30: 4.88; 2012-01-31: 4.88; 2012-02-01: 4.88; 2012-02-02: 4.88; 2012-02-03: 4.88; 2012-02-06: 4.88; 2012-02-07: 4.88; 2012-02-08: 4.88; 2012-02-09: 4.88; 2012-02-10: 4.88; 2012-02-13: 4.88; 2012-02-14: 4.88; 2012-02-15: 4.88; 2012-02-16: 4.88; 2012-02-17: 4.88; 2012-02-20: 4.88; 2012-02-21: 4.88; 2012-02-22: 4.88; 2012-02-23: 4.88; 2012-02-24: 4.88; 2012-02-27: 4.88; 2012-02-28: 4.88; 2012-02-29: 4.88; 2012-03-01: 4.88; 2012-03-02: 4.88; 2012-03-05: 4.88; 2012-03-06: 4.88; 2012-03-07: 4.88; 2012-03-08: 4.88; 2012-03-09: 4.88; 2012-03-12: 4.88; 2012-03-13: 4.88; 2012-03-14: 4.88; 2012-03-15: 4.88; 2012-03-16: 4.88; 2012-03-19: 4.88; 2012-03-20: 4.88; 2012-03-21: 4.88; 2012-03-22: 4.88; 2012-03-23: 4.88; 2012-03-26: 4.88; 2012-03-27: 4.88; 2012-03-28: 4.88; 2012-03-29: 4.88; 2012-03-30: 4.88; 2012-04-02: 4.88; 2012-04-03: 4.88; 2012-04-04: 4.88; 2012-04-05: 4.88; 2012-04-06: 4.88; 2012-04-09: 4.88; 2012-04-10: 4.88; 2012-04-11: 4.88; 2012-04-12: 4.88; 2012-04-13: 4.88; 2012-04-16: 4.88; 2012-04-17: 4.88; 2012-04-18: 4.88; 2012-04-19: 4.88; 2012-04-20: 4.88; 2012-04-23: 4.88; 2012-04-24: 4.88; 2012-04-25: 4.88; 2012-04-26: 4.88; 2012-04-27: 4.68; 2012-04-30: 4.39; 2012-05-01: 4.39; 2012-05-02: 4.39; 2012-05-03: 4.39; 2012-05-04: 4.39; 2012-05-07: 4.39; 2012-05-08: 4.39; 2012-05-09: 4.39; 2012-05-10: 4.39; 2012-05-11: 4.39; 2012-05-14: 4.39; 2012-05-15: 4.39; 2012-05-16: 4.39; 2012-05-17: 4.39; 2012-05-18: 4.39; 2012-05-21: 4.39; 2012-05-22: 4.39; 2012-05-23: 4.39; 2012-05-24: 4.39; 2012-05-25: 4.39; 2012-05-29: 4.39; 2012-05-30: 4.39; 2012-05-31: 4.39; 2012-06-01: 4.39; 2012-06-04: 4.39; 2012-06-05: 4.39; 2012-06-06: 4.39; 2012-06-07: 4.39; 2012-06-08: 4.39; 2012-06-11: 4.39; 2012-06-12: 4.39; 2012-06-13: 4.39; 2012-06-14: 4.39; 2012-06-15: 4.39; 2012-06-18: 4.39; 2012-06-19: 4.39; 2012-06-20: 4.39; 2012-06-21: 4.39; 2012-06-22: 4.39; 2012-06-25: 4.39; 2012-06-26: 4.39; 2012-06-27: 4.39; 2012-06-28: 4.39; 2012-06-29: 4.39; 2012-07-02: 4.39; 2012-07-03: 4.39; 2012-07-05: 4.39; 2012-07-06: 4.39; 2012-07-09: 4.39; 2012-07-10: 4.39; 2012-07-11: 4.39; 2012-07-12: 4.39; 2012-07-13: 4.39; 2012-07-16: 4.39; 2012-07-17: 4.39; 2012-07-18: 4.39; 2012-07-19: 4.39; 2012-07-20: 4.39; 2012-07-23: 4.39; 2012-07-24: 4.39; 2012-07-25: 4.39; 2012-07-26: 4.39; 2012-07-27: 4.39; 2012-07-30: 4.39; 2012-07-31: 4.39; 2012-08-01: 4.39; 2012-08-02: 4.39; 2012-08-03: 4.39; 2012-08-06: 4.39; 2012-08-07: 4.39; 2012-08-08: 4.39; 2012-08-09: 4.39; 2012-08-10: 4.39; 2012-08-13: 4.39; 2012-08-14: 4.39; 2012-08-15: 4.39; 2012-08-16: 4.39; 2012-08-17: 4.39; 2012-08-20: 4.39; 2012-08-21: 4.39; 2012-08-22: 4.39; 2012-08-23: 4.39; 2012-08-24: 4.39; 2012-08-27: 4.39; 2012-08-28: 4.39; 2012-08-29: 4.39; 2012-08-30: 4.39; 2012-08-31: 4.39; 2012-09-04: 4.39; 2012-09-05: 4.39; 2012-09-06: 4.39; 2012-09-07: 4.39; 2012-09-10: 4.39; 2012-09-11: 4.39; 2012-09-12: 4.39; 2012-09-13: 4.39; 2012-09-14: 4.39; 2012-09-17: 4.39; 2012-09-18: 4.39; 2012-09-19: 4.39; 2012-09-20: 4.39; 2012-09-21: 4.39; 2012-09-24: 4.39; 2012-09-25: 4.39; 2012-09-26: 4.39; 2012-09-27: 4.39; 2012-09-28: 4.39; 2012-10-01: 4.39; 2012-10-02: 4.39; 2012-10-03: 4.39; 2012-10-04: 4.39; 2012-10-05: 4.39; 2012-10-08: 4.39; 2012-10-09: 4.39; 2012-10-10: 4.39; 2012-10-11: 4.39; 2012-10-12: 4.39; 2012-10-15: 4.39; 2012-10-16: 4.39; 2012-10-17: 4.39; 2012-10-18: 4.39; 2012-10-19: 4.39; 2012-10-22: 4.39; 2012-10-23: 4.39; 2012-10-24: 4.39; 2012-10-25: 4.39; 2012-10-26: 4.39; 2012-10-29: 4.39; 2012-10-30: 4.39; 2012-10-31: 4.39; 2012-11-01: 3.51
EC2170 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 3 | 196.8 | 196.8 | 0% | 2012-02-03 | 2012-11-05 | 209.2 | 896 | At Completion Labor Units | 2012-02-03: 4.88; 2012-02-06: 4.88; 2012-02-07: 4.88; 2012-02-08: 4.88; 2012-02-09: 4.88; 2012-02-10: 4.88; 2012-02-13: 4.88; 2012-02-14: 4.88; 2012-02-15: 4.88; 2012-02-16: 4.88; 2012-02-17: 4.88; 2012-02-20: 4.88; 2012-02-21: 4.88; 2012-02-22: 4.88; 2012-02-23: 4.88; 2012-02-24: 4.88; 2012-02-27: 4.88; 2012-02-28: 4.88; 2012-02-29: 4.88; 2012-03-01: 4.88; 2012-03-02: 4.88; 2012-03-05: 4.88; 2012-03-06: 4.88; 2012-03-07: 4.88; 2012-03-08: 4.88; 2012-03-09: 4.88; 2012-03-12: 4.88; 2012-03-13: 4.88; 2012-03-14: 4.88; 2012-03-15: 4.88; 2012-03-16: 4.88; 2012-03-19: 4.88; 2012-03-20: 4.88; 2012-03-21: 4.88; 2012-03-22: 4.88; 2012-03-23: 4.88; 2012-03-26: 4.88; 2012-03-27: 4.88; 2012-03-28: 4.88; 2012-03-29: 4.88; 2012-03-30: 4.88; 2012-04-02: 4.88; 2012-04-03: 4.88; 2012-04-04: 4.88; 2012-04-05: 4.88; 2012-04-06: 4.88; 2012-04-09: 4.88; 2012-04-10: 4.88; 2012-04-11: 4.88; 2012-04-12: 4.88; 2012-04-13: 4.88; 2012-04-16: 4.88; 2012-04-17: 4.88; 2012-04-18: 4.88; 2012-04-19: 4.88; 2012-04-20: 4.88; 2012-04-23: 4.88; 2012-04-24: 4.88; 2012-04-25: 4.88; 2012-04-26: 4.88; 2012-04-27: 4.88; 2012-04-30: 4.88; 2012-05-01: 4.88; 2012-05-02: 4.88; 2012-05-03: 4.88; 2012-05-04: 4.68; 2012-05-07: 4.39; 2012-05-08: 4.39; 2012-05-09: 4.39; 2012-05-10: 4.39; 2012-05-11: 4.39; 2012-05-14: 4.39; 2012-05-15: 4.39; 2012-05-16: 4.39; 2012-05-17: 4.39; 2012-05-18: 4.39; 2012-05-21: 4.39; 2012-05-22: 4.39; 2012-05-23: 4.39; 2012-05-24: 4.39; 2012-05-25: 4.39; 2012-05-29: 4.39; 2012-05-30: 4.39; 2012-05-31: 4.39; 2012-06-01: 4.39; 2012-06-04: 4.39; 2012-06-05: 4.39; 2012-06-06: 4.39; 2012-06-07: 4.39; 2012-06-08: 4.39; 2012-06-11: 4.39; 2012-06-12: 4.39; 2012-06-13: 4.39; 2012-06-14: 4.39; 2012-06-15: 4.39; 2012-06-18: 4.39; 2012-06-19: 4.39; 2012-06-20: 4.39; 2012-06-21: 4.39; 2012-06-22: 4.39; 2012-06-25: 4.39; 2012-06-26: 4.39; 2012-06-27: 4.39; 2012-06-28: 4.39; 2012-06-29: 4.39; 2012-07-02: 4.39; 2012-07-03: 4.39; 2012-07-05: 4.39; 2012-07-06: 4.39; 2012-07-09: 4.39; 2012-07-10: 4.39; 2012-07-11: 4.39; 2012-07-12: 4.39; 2012-07-13: 4.39; 2012-07-16: 4.39; 2012-07-17: 4.39; 2012-07-18: 4.39; 2012-07-19: 4.39; 2012-07-20: 4.39; 2012-07-23: 4.39; 2012-07-24: 4.39; 2012-07-25: 4.39; 2012-07-26: 4.39; 2012-07-27: 4.39; 2012-07-30: 4.39; 2012-07-31: 4.39; 2012-08-01: 4.39; 2012-08-02: 4.39; 2012-08-03: 4.39; 2012-08-06: 4.39; 2012-08-07: 4.39; 2012-08-08: 4.39; 2012-08-09: 4.39; 2012-08-10: 4.39; 2012-08-13: 4.39; 2012-08-14: 4.39; 2012-08-15: 4.39; 2012-08-16: 4.39; 2012-08-17: 4.39; 2012-08-20: 4.39; 2012-08-21: 4.39; 2012-08-22: 4.39; 2012-08-23: 4.39; 2012-08-24: 4.39; 2012-08-27: 4.39; 2012-08-28: 4.39; 2012-08-29: 4.39; 2012-08-30: 4.39; 2012-08-31: 4.39; 2012-09-04: 4.39; 2012-09-05: 4.39; 2012-09-06: 4.39; 2012-09-07: 4.39; 2012-09-10: 4.39; 2012-09-11: 4.39; 2012-09-12: 4.39; 2012-09-13: 4.39; 2012-09-14: 4.39; 2012-09-17: 4.39; 2012-09-18: 4.39; 2012-09-19: 4.39; 2012-09-20: 4.39; 2012-09-21: 4.39; 2012-09-24: 4.39; 2012-09-25: 4.39; 2012-09-26: 4.39; 2012-09-27: 4.39; 2012-09-28: 4.39; 2012-10-01: 4.39; 2012-10-02: 4.39; 2012-10-03: 4.39; 2012-10-04: 4.39; 2012-10-05: 4.39; 2012-10-08: 4.39; 2012-10-09: 4.39; 2012-10-10: 4.39; 2012-10-11: 4.39; 2012-10-12: 4.39; 2012-10-15: 4.39; 2012-10-16: 4.39; 2012-10-17: 4.39; 2012-10-18: 4.39; 2012-10-19: 4.39; 2012-10-22: 4.39; 2012-10-23: 4.39; 2012-10-24: 4.39; 2012-10-25: 4.39; 2012-10-26: 4.39; 2012-10-29: 4.39; 2012-10-30: 4.39; 2012-10-31: 4.39; 2012-11-01: 4.39; 2012-11-02: 4.39; 2012-11-05: 4.39; 2012-11-06: 4.39; 2012-11-07: 4.39; 2012-11-08: 3.51
EC2200 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 4 | 194.4 | 194.4 | 0% | 2012-02-10 | 2012-11-08 | 209.2 | 896 | At Completion Labor Units | 2012-02-10: 4.94; 2012-02-13: 4.94; 2012-02-14: 4.94; 2012-02-15: 4.94; 2012-02-16: 4.94; 2012-02-17: 4.94; 2012-02-20: 4.94; 2012-02-21: 4.94; 2012-02-22: 4.94; 2012-02-23: 4.94; 2012-02-24: 4.94; 2012-02-27: 4.94; 2012-02-28: 4.94; 2012-02-29: 4.94; 2012-03-01: 4.94; 2012-03-02: 4.94; 2012-03-05: 4.94; 2012-03-06: 4.94; 2012-03-07: 4.94; 2012-03-08: 4.94; 2012-03-09: 4.94; 2012-03-12: 4.94; 2012-03-13: 4.94; 2012-03-14: 4.94; 2012-03-15: 4.94; 2012-03-16: 4.94; 2012-03-19: 4.94; 2012-03-20: 4.94; 2012-03-21: 4.94; 2012-03-22: 4.94; 2012-03-23: 4.94; 2012-03-26: 4.94; 2012-03-27: 4.94; 2012-03-28: 4.94; 2012-03-29: 4.94; 2012-03-30: 4.94; 2012-04-02: 4.94; 2012-04-03: 4.94; 2012-04-04: 4.94; 2012-04-05: 4.94; 2012-04-06: 4.94; 2012-04-09: 4.94; 2012-04-10: 4.94; 2012-04-11: 4.94; 2012-04-12: 4.94; 2012-04-13: 4.94; 2012-04-16: 4.94; 2012-04-17: 4.94; 2012-04-18: 4.94; 2012-04-19: 4.94; 2012-04-20: 4.94; 2012-04-23: 4.94; 2012-04-24: 4.94; 2012-04-25: 4.94; 2012-04-26: 4.94; 2012-04-27: 4.94; 2012-04-30: 4.94; 2012-05-01: 4.94; 2012-05-02: 4.94; 2012-05-03: 4.94; 2012-05-04: 4.94; 2012-05-07: 4.94; 2012-05-08: 4.94; 2012-05-09: 4.94; 2012-05-10: 4.84; 2012-05-11: 4.44; 2012-05-14: 4.44; 2012-05-15: 4.44; 2012-05-16: 4.44; 2012-05-17: 4.44; 2012-05-18: 4.44; 2012-05-21: 4.44; 2012-05-22: 4.44; 2012-05-23: 4.44; 2012-05-24: 4.44; 2012-05-25: 4.44; 2012-05-29: 4.44; 2012-05-30: 4.44; 2012-05-31: 4.44; 2012-06-01: 4.44; 2012-06-04: 4.44; 2012-06-05: 4.44; 2012-06-06: 4.44; 2012-06-07: 4.44; 2012-06-08: 4.44; 2012-06-11: 4.44; 2012-06-12: 4.44; 2012-06-13: 4.44; 2012-06-14: 4.44; 2012-06-15: 4.44; 2012-06-18: 4.44; 2012-06-19: 4.44; 2012-06-20: 4.44; 2012-06-21: 4.44; 2012-06-22: 4.44; 2012-06-25: 4.44; 2012-06-26: 4.44; 2012-06-27: 4.44; 2012-06-28: 4.44; 2012-06-29: 4.44; 2012-07-02: 4.44; 2012-07-03: 4.44; 2012-07-05: 4.44; 2012-07-06: 4.44; 2012-07-09: 4.44; 2012-07-10: 4.44; 2012-07-11: 4.44; 2012-07-12: 4.44; 2012-07-13: 4.44; 2012-07-16: 4.44; 2012-07-17: 4.44; 2012-07-18: 4.44; 2012-07-19: 4.44; 2012-07-20: 4.44; 2012-07-23: 4.44; 2012-07-24: 4.44; 2012-07-25: 4.44; 2012-07-26: 4.44; 2012-07-27: 4.44; 2012-07-30: 4.44; 2012-07-31: 4.44; 2012-08-01: 4.44; 2012-08-02: 4.44; 2012-08-03: 4.44; 2012-08-06: 4.44; 2012-08-07: 4.44; 2012-08-08: 4.44; 2012-08-09: 4.44; 2012-08-10: 4.44; 2012-08-13: 4.44; 2012-08-14: 4.44; 2012-08-15: 4.44; 2012-08-16: 4.44; 2012-08-17: 4.44; 2012-08-20: 4.44; 2012-08-21: 4.44; 2012-08-22: 4.44; 2012-08-23: 4.44; 2012-08-24: 4.44; 2012-08-27: 4.44; 2012-08-28: 4.44; 2012-08-29: 4.44; 2012-08-30: 4.44; 2012-08-31: 4.44; 2012-09-04: 4.44; 2012-09-05: 4.44; 2012-09-06: 4.44; 2012-09-07: 4.44; 2012-09-10: 4.44; 2012-09-11: 4.44; 2012-09-12: 4.44; 2012-09-13: 4.44; 2012-09-14: 4.44; 2012-09-17: 4.44; 2012-09-18: 4.44; 2012-09-19: 4.44; 2012-09-20: 4.44; 2012-09-21: 4.44; 2012-09-24: 4.44; 2012-09-25: 4.44; 2012-09-26: 4.44; 2012-09-27: 4.44; 2012-09-28: 4.44; 2012-10-01: 4.44; 2012-10-02: 4.44; 2012-10-03: 4.44; 2012-10-04: 4.44; 2012-10-05: 4.44; 2012-10-08: 4.44; 2012-10-09: 4.44; 2012-10-10: 4.44; 2012-10-11: 4.44; 2012-10-12: 4.44; 2012-10-15: 4.44; 2012-10-16: 4.44; 2012-10-17: 4.44; 2012-10-18: 4.44; 2012-10-19: 4.44; 2012-10-22: 4.44; 2012-10-23: 4.44; 2012-10-24: 4.44; 2012-10-25: 4.44; 2012-10-26: 4.44; 2012-10-29: 4.44; 2012-10-30: 4.44; 2012-10-31: 4.44; 2012-11-01: 4.44; 2012-11-02: 4.44; 2012-11-05: 4.44; 2012-11-06: 4.44; 2012-11-07: 4.44; 2012-11-08: 4.44; 2012-11-09: 4.44; 2012-11-12: 4.44; 2012-11-13: 1.78
EC2210 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 4 | 194.4 | 194.4 | 0% | 2012-02-17 | 2012-11-15 | 209.2 | 896 | At Completion Labor Units | 2012-02-17: 4.94; 2012-02-20: 4.94; 2012-02-21: 4.94; 2012-02-22: 4.94; 2012-02-23: 4.94; 2012-02-24: 4.94; 2012-02-27: 4.94; 2012-02-28: 4.94; 2012-02-29: 4.94; 2012-03-01: 4.94; 2012-03-02: 4.94; 2012-03-05: 4.94; 2012-03-06: 4.94; 2012-03-07: 4.94; 2012-03-08: 4.94; 2012-03-09: 4.94; 2012-03-12: 4.94; 2012-03-13: 4.94; 2012-03-14: 4.94; 2012-03-15: 4.94; 2012-03-16: 4.94; 2012-03-19: 4.94; 2012-03-20: 4.94; 2012-03-21: 4.94; 2012-03-22: 4.94; 2012-03-23: 4.94; 2012-03-26: 4.94; 2012-03-27: 4.94; 2012-03-28: 4.94; 2012-03-29: 4.94; 2012-03-30: 4.94; 2012-04-02: 4.94; 2012-04-03: 4.94; 2012-04-04: 4.94; 2012-04-05: 4.94; 2012-04-06: 4.94; 2012-04-09: 4.94; 2012-04-10: 4.94; 2012-04-11: 4.94; 2012-04-12: 4.94; 2012-04-13: 4.94; 2012-04-16: 4.94; 2012-04-17: 4.94; 2012-04-18: 4.94; 2012-04-19: 4.94; 2012-04-20: 4.94; 2012-04-23: 4.94; 2012-04-24: 4.94; 2012-04-25: 4.94; 2012-04-26: 4.94; 2012-04-27: 4.94; 2012-04-30: 4.94; 2012-05-01: 4.94; 2012-05-02: 4.94; 2012-05-03: 4.94; 2012-05-04: 4.94; 2012-05-07: 4.94; 2012-05-08: 4.94; 2012-05-09: 4.94; 2012-05-10: 4.94; 2012-05-11: 4.94; 2012-05-14: 4.94; 2012-05-15: 4.94; 2012-05-16: 4.94; 2012-05-17: 4.84; 2012-05-18: 4.44; 2012-05-21: 4.44; 2012-05-22: 4.44; 2012-05-23: 4.44; 2012-05-24: 4.44; 2012-05-25: 4.44; 2012-05-29: 4.44; 2012-05-30: 4.44; 2012-05-31: 4.44; 2012-06-01: 4.44; 2012-06-04: 4.44; 2012-06-05: 4.44; 2012-06-06: 4.44; 2012-06-07: 4.44; 2012-06-08: 4.44; 2012-06-11: 4.44; 2012-06-12: 4.44; 2012-06-13: 4.44; 2012-06-14: 4.44; 2012-06-15: 4.44; 2012-06-18: 4.44; 2012-06-19: 4.44; 2012-06-20: 4.44; 2012-06-21: 4.44; 2012-06-22: 4.44; 2012-06-25: 4.44; 2012-06-26: 4.44; 2012-06-27: 4.44; 2012-06-28: 4.44; 2012-06-29: 4.44; 2012-07-02: 4.44; 2012-07-03: 4.44; 2012-07-05: 4.44; 2012-07-06: 4.44; 2012-07-09: 4.44; 2012-07-10: 4.44; 2012-07-11: 4.44; 2012-07-12: 4.44; 2012-07-13: 4.44; 2012-07-16: 4.44; 2012-07-17: 4.44; 2012-07-18: 4.44; 2012-07-19: 4.44; 2012-07-20: 4.44; 2012-07-23: 4.44; 2012-07-24: 4.44; 2012-07-25: 4.44; 2012-07-26: 4.44; 2012-07-27: 4.44; 2012-07-30: 4.44; 2012-07-31: 4.44; 2012-08-01: 4.44; 2012-08-02: 4.44; 2012-08-03: 4.44; 2012-08-06: 4.44; 2012-08-07: 4.44; 2012-08-08: 4.44; 2012-08-09: 4.44; 2012-08-10: 4.44; 2012-08-13: 4.44; 2012-08-14: 4.44; 2012-08-15: 4.44; 2012-08-16: 4.44; 2012-08-17: 4.44; 2012-08-20: 4.44; 2012-08-21: 4.44; 2012-08-22: 4.44; 2012-08-23: 4.44; 2012-08-24: 4.44; 2012-08-27: 4.44; 2012-08-28: 4.44; 2012-08-29: 4.44; 2012-08-30: 4.44; 2012-08-31: 4.44; 2012-09-04: 4.44; 2012-09-05: 4.44; 2012-09-06: 4.44; 2012-09-07: 4.44; 2012-09-10: 4.44; 2012-09-11: 4.44; 2012-09-12: 4.44; 2012-09-13: 4.44; 2012-09-14: 4.44; 2012-09-17: 4.44; 2012-09-18: 4.44; 2012-09-19: 4.44; 2012-09-20: 4.44; 2012-09-21: 4.44; 2012-09-24: 4.44; 2012-09-25: 4.44; 2012-09-26: 4.44; 2012-09-27: 4.44; 2012-09-28: 4.44; 2012-10-01: 4.44; 2012-10-02: 4.44; 2012-10-03: 4.44; 2012-10-04: 4.44; 2012-10-05: 4.44; 2012-10-08: 4.44; 2012-10-09: 4.44; 2012-10-10: 4.44; 2012-10-11: 4.44; 2012-10-12: 4.44; 2012-10-15: 4.44; 2012-10-16: 4.44; 2012-10-17: 4.44; 2012-10-18: 4.44; 2012-10-19: 4.44; 2012-10-22: 4.44; 2012-10-23: 4.44; 2012-10-24: 4.44; 2012-10-25: 4.44; 2012-10-26: 4.44; 2012-10-29: 4.44; 2012-10-30: 4.44; 2012-10-31: 4.44; 2012-11-01: 4.44; 2012-11-02: 4.44; 2012-11-05: 4.44; 2012-11-06: 4.44; 2012-11-07: 4.44; 2012-11-08: 4.44; 2012-11-09: 4.44; 2012-11-12: 4.44; 2012-11-13: 4.44; 2012-11-14: 4.44; 2012-11-15: 4.44; 2012-11-16: 4.44; 2012-11-19: 4.44; 2012-11-20: 1.78
EC2410 | 1345006 | 4000 | ACMEGC | Final Inspections and Punchlist | 72 | 72 | 0% | 2012-11-15 | 2013-02-25 | 209.2 | 456 | At Completion Labor Units | 2012-11-15: 4.2; 2012-11-16: 7; 2012-11-19: 7; 2012-11-20: 7; 2012-11-21: 7; 2012-11-23: 7; 2012-11-26: 7; 2012-11-27: 7; 2012-11-28: 7; 2012-11-29: 7; 2012-11-30: 7; 2012-12-03: 7; 2012-12-04: 7; 2012-12-05: 7; 2012-12-06: 7; 2012-12-07: 7; 2012-12-10: 7; 2012-12-11: 7; 2012-12-12: 7; 2012-12-13: 7; 2012-12-14: 7; 2012-12-17: 7; 2012-12-18: 7; 2012-12-19: 7; 2012-12-20: 6.4; 2012-12-21: 6; 2012-12-24: 6; 2012-12-26: 6; 2012-12-27: 6; 2012-12-28: 6; 2012-12-31: 6; 2013-01-02: 6; 2013-01-03: 6; 2013-01-04: 6; 2013-01-07: 6; 2013-01-08: 6; 2013-01-09: 6; 2013-01-10: 6; 2013-01-11: 6; 2013-01-14: 6; 2013-01-15: 6; 2013-01-16: 6; 2013-01-17: 6; 2013-01-18: 6; 2013-01-21: 6; 2013-01-22: 6; 2013-01-23: 6; 2013-01-24: 6; 2013-01-25: 6; 2013-01-28: 6; 2013-01-29: 6; 2013-01-30: 6; 2013-01-31: 6; 2013-02-01: 6; 2013-02-04: 6; 2013-02-05: 6; 2013-02-06: 6; 2013-02-07: 6; 2013-02-08: 6; 2013-02-11: 6; 2013-02-12: 6; 2013-02-13: 6; 2013-02-14: 6; 2013-02-15: 6; 2013-02-18: 6; 2013-02-19: 6; 2013-02-20: 6; 2013-02-21: 6; 2013-02-22: 6; 2013-02-25: 6; 2013-02-26: 6; 2013-02-27: 6; 2013-02-28: 2.4
EC2040 | 1345006 | 4000 | ACMEGC | Building 1 Elevators Complete | 69.6 | 69.6 | 0% | 2012-01-06 | 2012-04-12 | 311.4 | 768 | At Completion Labor Units | 2012-01-06: 11.03; 2012-01-09: 11.03; 2012-01-10: 11.03; 2012-01-11: 11.03; 2012-01-12: 11.03; 2012-01-13: 11.03; 2012-01-16: 11.03; 2012-01-17: 11.03; 2012-01-18: 11.03; 2012-01-19: 11.03; 2012-01-20: 11.03; 2012-01-23: 11.03; 2012-01-24: 11.03; 2012-01-25: 11.03; 2012-01-26: 11.03; 2012-01-27: 11.03; 2012-01-30: 11.03; 2012-01-31: 11.03; 2012-02-01: 11.03; 2012-02-02: 11.03; 2012-02-03: 11.03; 2012-02-06: 11.03; 2012-02-07: 11.03; 2012-02-08: 11.03; 2012-02-09: 11.03; 2012-02-10: 11.03; 2012-02-13: 11.03; 2012-02-14: 11.03; 2012-02-15: 11.03; 2012-02-16: 11.03; 2012-02-17: 11.03; 2012-02-20: 11.03; 2012-02-21: 11.03; 2012-02-22: 11.03; 2012-02-23: 11.03; 2012-02-24: 11.03; 2012-02-27: 11.03; 2012-02-28: 11.03; 2012-02-29: 11.03; 2012-03-01: 11.03; 2012-03-02: 11.03; 2012-03-05: 11.03; 2012-03-06: 11.03; 2012-03-07: 11.03; 2012-03-08: 11.03; 2012-03-09: 11.03; 2012-03-12: 11.03; 2012-03-13: 11.03; 2012-03-14: 11.03; 2012-03-15: 11.03; 2012-03-16: 11.03; 2012-03-19: 11.03; 2012-03-20: 11.03; 2012-03-21: 11.03; 2012-03-22: 11.03; 2012-03-23: 11.03; 2012-03-26: 11.03; 2012-03-27: 11.03; 2012-03-28: 11.03; 2012-03-29: 11.03; 2012-03-30: 11.03; 2012-04-02: 11.03; 2012-04-03: 11.03; 2012-04-04: 11.03; 2012-04-05: 11.03; 2012-04-06: 11.03; 2012-04-09: 11.03; 2012-04-10: 11.03; 2012-04-11: 11.03; 2012-04-12: 6.62
EC2070 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 2 | 196.8 | 196.8 | 0% | 2012-01-13 | 2012-10-15 | 209.2 | 896 | At Completion Labor Units | 2012-01-13: 4.88; 2012-01-16: 4.88; 2012-01-17: 4.88; 2012-01-18: 4.88; 2012-01-19: 4.88; 2012-01-20: 4.88; 2012-01-23: 4.88; 2012-01-24: 4.88; 2012-01-25: 4.88; 2012-01-26: 4.88; 2012-01-27: 4.88; 2012-01-30: 4.88; 2012-01-31: 4.88; 2012-02-01: 4.88; 2012-02-02: 4.88; 2012-02-03: 4.88; 2012-02-06: 4.88; 2012-02-07: 4.88; 2012-02-08: 4.88; 2012-02-09: 4.88; 2012-02-10: 4.88; 2012-02-13: 4.88; 2012-02-14: 4.88; 2012-02-15: 4.88; 2012-02-16: 4.88; 2012-02-17: 4.88; 2012-02-20: 4.88; 2012-02-21: 4.88; 2012-02-22: 4.88; 2012-02-23: 4.88; 2012-02-24: 4.88; 2012-02-27: 4.88; 2012-02-28: 4.88; 2012-02-29: 4.88; 2012-03-01: 4.88; 2012-03-02: 4.88; 2012-03-05: 4.88; 2012-03-06: 4.88; 2012-03-07: 4.88; 2012-03-08: 4.88; 2012-03-09: 4.88; 2012-03-12: 4.88; 2012-03-13: 4.88; 2012-03-14: 4.88; 2012-03-15: 4.88; 2012-03-16: 4.88; 2012-03-19: 4.88; 2012-03-20: 4.88; 2012-03-21: 4.88; 2012-03-22: 4.88; 2012-03-23: 4.88; 2012-03-26: 4.88; 2012-03-27: 4.88; 2012-03-28: 4.88; 2012-03-29: 4.88; 2012-03-30: 4.88; 2012-04-02: 4.88; 2012-04-03: 4.88; 2012-04-04: 4.88; 2012-04-05: 4.88; 2012-04-06: 4.88; 2012-04-09: 4.88; 2012-04-10: 4.88; 2012-04-11: 4.88; 2012-04-12: 4.88; 2012-04-13: 4.68; 2012-04-16: 4.39; 2012-04-17: 4.39; 2012-04-18: 4.39; 2012-04-19: 4.39; 2012-04-20: 4.39; 2012-04-23: 4.39; 2012-04-24: 4.39; 2012-04-25: 4.39; 2012-04-26: 4.39; 2012-04-27: 4.39; 2012-04-30: 4.39; 2012-05-01: 4.39; 2012-05-02: 4.39; 2012-05-03: 4.39; 2012-05-04: 4.39; 2012-05-07: 4.39; 2012-05-08: 4.39; 2012-05-09: 4.39; 2012-05-10: 4.39; 2012-05-11: 4.39; 2012-05-14: 4.39; 2012-05-15: 4.39; 2012-05-16: 4.39; 2012-05-17: 4.39; 2012-05-18: 4.39; 2012-05-21: 4.39; 2012-05-22: 4.39; 2012-05-23: 4.39; 2012-05-24: 4.39; 2012-05-25: 4.39; 2012-05-29: 4.39; 2012-05-30: 4.39; 2012-05-31: 4.39; 2012-06-01: 4.39; 2012-06-04: 4.39; 2012-06-05: 4.39; 2012-06-06: 4.39; 2012-06-07: 4.39; 2012-06-08: 4.39; 2012-06-11: 4.39; 2012-06-12: 4.39; 2012-06-13: 4.39; 2012-06-14: 4.39; 2012-06-15: 4.39; 2012-06-18: 4.39; 2012-06-19: 4.39; 2012-06-20: 4.39; 2012-06-21: 4.39; 2012-06-22: 4.39; 2012-06-25: 4.39; 2012-06-26: 4.39; 2012-06-27: 4.39; 2012-06-28: 4.39; 2012-06-29: 4.39; 2012-07-02: 4.39; 2012-07-03: 4.39; 2012-07-05: 4.39; 2012-07-06: 4.39; 2012-07-09: 4.39; 2012-07-10: 4.39; 2012-07-11: 4.39; 2012-07-12: 4.39; 2012-07-13: 4.39; 2012-07-16: 4.39; 2012-07-17: 4.39; 2012-07-18: 4.39; 2012-07-19: 4.39; 2012-07-20: 4.39; 2012-07-23: 4.39; 2012-07-24: 4.39; 2012-07-25: 4.39; 2012-07-26: 4.39; 2012-07-27: 4.39; 2012-07-30: 4.39; 2012-07-31: 4.39; 2012-08-01: 4.39; 2012-08-02: 4.39; 2012-08-03: 4.39; 2012-08-06: 4.39; 2012-08-07: 4.39; 2012-08-08: 4.39; 2012-08-09: 4.39; 2012-08-10: 4.39; 2012-08-13: 4.39; 2012-08-14: 4.39; 2012-08-15: 4.39; 2012-08-16: 4.39; 2012-08-17: 4.39; 2012-08-20: 4.39; 2012-08-21: 4.39; 2012-08-22: 4.39; 2012-08-23: 4.39; 2012-08-24: 4.39; 2012-08-27: 4.39; 2012-08-28: 4.39; 2012-08-29: 4.39; 2012-08-30: 4.39; 2012-08-31: 4.39; 2012-09-04: 4.39; 2012-09-05: 4.39; 2012-09-06: 4.39; 2012-09-07: 4.39; 2012-09-10: 4.39; 2012-09-11: 4.39; 2012-09-12: 4.39; 2012-09-13: 4.39; 2012-09-14: 4.39; 2012-09-17: 4.39; 2012-09-18: 4.39; 2012-09-19: 4.39; 2012-09-20: 4.39; 2012-09-21: 4.39; 2012-09-24: 4.39; 2012-09-25: 4.39; 2012-09-26: 4.39; 2012-09-27: 4.39; 2012-09-28: 4.39; 2012-10-01: 4.39; 2012-10-02: 4.39; 2012-10-03: 4.39; 2012-10-04: 4.39; 2012-10-05: 4.39; 2012-10-08: 4.39; 2012-10-09: 4.39; 2012-10-10: 4.39; 2012-10-11: 4.39; 2012-10-12: 4.39; 2012-10-15: 4.39; 2012-10-16: 4.39; 2012-10-17: 4.39; 2012-10-18: 3.51
EC2120 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 2 | 196.8 | 196.8 | 0% | 2012-01-20 | 2012-10-22 | 209.2 | 896 | At Completion Labor Units | 2012-01-20: 4.88; 2012-01-23: 4.88; 2012-01-24: 4.88; 2012-01-25: 4.88; 2012-01-26: 4.88; 2012-01-27: 4.88; 2012-01-30: 4.88; 2012-01-31: 4.88; 2012-02-01: 4.88; 2012-02-02: 4.88; 2012-02-03: 4.88; 2012-02-06: 4.88; 2012-02-07: 4.88; 2012-02-08: 4.88; 2012-02-09: 4.88; 2012-02-10: 4.88; 2012-02-13: 4.88; 2012-02-14: 4.88; 2012-02-15: 4.88; 2012-02-16: 4.88; 2012-02-17: 4.88; 2012-02-20: 4.88; 2012-02-21: 4.88; 2012-02-22: 4.88; 2012-02-23: 4.88; 2012-02-24: 4.88; 2012-02-27: 4.88; 2012-02-28: 4.88; 2012-02-29: 4.88; 2012-03-01: 4.88; 2012-03-02: 4.88; 2012-03-05: 4.88; 2012-03-06: 4.88; 2012-03-07: 4.88; 2012-03-08: 4.88; 2012-03-09: 4.88; 2012-03-12: 4.88; 2012-03-13: 4.88; 2012-03-14: 4.88; 2012-03-15: 4.88; 2012-03-16: 4.88; 2012-03-19: 4.88; 2012-03-20: 4.88; 2012-03-21: 4.88; 2012-03-22: 4.88; 2012-03-23: 4.88; 2012-03-26: 4.88; 2012-03-27: 4.88; 2012-03-28: 4.88; 2012-03-29: 4.88; 2012-03-30: 4.88; 2012-04-02: 4.88; 2012-04-03: 4.88; 2012-04-04: 4.88; 2012-04-05: 4.88; 2012-04-06: 4.88; 2012-04-09: 4.88; 2012-04-10: 4.88; 2012-04-11: 4.88; 2012-04-12: 4.88; 2012-04-13: 4.88; 2012-04-16: 4.88; 2012-04-17: 4.88; 2012-04-18: 4.88; 2012-04-19: 4.88; 2012-04-20: 4.68; 2012-04-23: 4.39; 2012-04-24: 4.39; 2012-04-25: 4.39; 2012-04-26: 4.39; 2012-04-27: 4.39; 2012-04-30: 4.39; 2012-05-01: 4.39; 2012-05-02: 4.39; 2012-05-03: 4.39; 2012-05-04: 4.39; 2012-05-07: 4.39; 2012-05-08: 4.39; 2012-05-09: 4.39; 2012-05-10: 4.39; 2012-05-11: 4.39; 2012-05-14: 4.39; 2012-05-15: 4.39; 2012-05-16: 4.39; 2012-05-17: 4.39; 2012-05-18: 4.39; 2012-05-21: 4.39; 2012-05-22: 4.39; 2012-05-23: 4.39; 2012-05-24: 4.39; 2012-05-25: 4.39; 2012-05-29: 4.39; 2012-05-30: 4.39; 2012-05-31: 4.39; 2012-06-01: 4.39; 2012-06-04: 4.39; 2012-06-05: 4.39; 2012-06-06: 4.39; 2012-06-07: 4.39; 2012-06-08: 4.39; 2012-06-11: 4.39; 2012-06-12: 4.39; 2012-06-13: 4.39; 2012-06-14: 4.39; 2012-06-15: 4.39; 2012-06-18: 4.39; 2012-06-19: 4.39; 2012-06-20: 4.39; 2012-06-21: 4.39; 2012-06-22: 4.39; 2012-06-25: 4.39; 2012-06-26: 4.39; 2012-06-27: 4.39; 2012-06-28: 4.39; 2012-06-29: 4.39; 2012-07-02: 4.39; 2012-07-03: 4.39; 2012-07-05: 4.39; 2012-07-06: 4.39; 2012-07-09: 4.39; 2012-07-10: 4.39; 2012-07-11: 4.39; 2012-07-12: 4.39; 2012-07-13: 4.39; 2012-07-16: 4.39; 2012-07-17: 4.39; 2012-07-18: 4.39; 2012-07-19: 4.39; 2012-07-20: 4.39; 2012-07-23: 4.39; 2012-07-24: 4.39; 2012-07-25: 4.39; 2012-07-26: 4.39; 2012-07-27: 4.39; 2012-07-30: 4.39; 2012-07-31: 4.39; 2012-08-01: 4.39; 2012-08-02: 4.39; 2012-08-03: 4.39; 2012-08-06: 4.39; 2012-08-07: 4.39; 2012-08-08: 4.39; 2012-08-09: 4.39; 2012-08-10: 4.39; 2012-08-13: 4.39; 2012-08-14: 4.39; 2012-08-15: 4.39; 2012-08-16: 4.39; 2012-08-17: 4.39; 2012-08-20: 4.39; 2012-08-21: 4.39; 2012-08-22: 4.39; 2012-08-23: 4.39; 2012-08-24: 4.39; 2012-08-27: 4.39; 2012-08-28: 4.39; 2012-08-29: 4.39; 2012-08-30: 4.39; 2012-08-31: 4.39; 2012-09-04: 4.39; 2012-09-05: 4.39; 2012-09-06: 4.39; 2012-09-07: 4.39; 2012-09-10: 4.39; 2012-09-11: 4.39; 2012-09-12: 4.39; 2012-09-13: 4.39; 2012-09-14: 4.39; 2012-09-17: 4.39; 2012-09-18: 4.39; 2012-09-19: 4.39; 2012-09-20: 4.39; 2012-09-21: 4.39; 2012-09-24: 4.39; 2012-09-25: 4.39; 2012-09-26: 4.39; 2012-09-27: 4.39; 2012-09-28: 4.39; 2012-10-01: 4.39; 2012-10-02: 4.39; 2012-10-03: 4.39; 2012-10-04: 4.39; 2012-10-05: 4.39; 2012-10-08: 4.39; 2012-10-09: 4.39; 2012-10-10: 4.39; 2012-10-11: 4.39; 2012-10-12: 4.39; 2012-10-15: 4.39; 2012-10-16: 4.39; 2012-10-17: 4.39; 2012-10-18: 4.39; 2012-10-19: 4.39; 2012-10-22: 4.39; 2012-10-23: 4.39; 2012-10-24: 4.39; 2012-10-25: 3.51
EC2000 | 1345006 | 4000 | ACMEGC | Unit Finishes Building North - Floor 1 | 201.6 | 201.6 | 0% | 2011-12-30 | 2012-10-08 | 209.2 | 896 | At Completion Labor Units | 2011-12-30: 4.76; 2012-01-03: 4.76; 2012-01-04: 4.76; 2012-01-05: 4.76; 2012-01-06: 4.76; 2012-01-09: 4.76; 2012-01-10: 4.76; 2012-01-11: 4.76; 2012-01-12: 4.76; 2012-01-13: 4.76; 2012-01-16: 4.76; 2012-01-17: 4.76; 2012-01-18: 4.76; 2012-01-19: 4.76; 2012-01-20: 4.76; 2012-01-23: 4.76; 2012-01-24: 4.76; 2012-01-25: 4.76; 2012-01-26: 4.76; 2012-01-27: 4.76; 2012-01-30: 4.76; 2012-01-31: 4.76; 2012-02-01: 4.76; 2012-02-02: 4.76; 2012-02-03: 4.76; 2012-02-06: 4.76; 2012-02-07: 4.76; 2012-02-08: 4.76; 2012-02-09: 4.76; 2012-02-10: 4.76; 2012-02-13: 4.76; 2012-02-14: 4.76; 2012-02-15: 4.76; 2012-02-16: 4.76; 2012-02-17: 4.76; 2012-02-20: 4.76; 2012-02-21: 4.76; 2012-02-22: 4.76; 2012-02-23: 4.76; 2012-02-24: 4.76; 2012-02-27: 4.76; 2012-02-28: 4.76; 2012-02-29: 4.76; 2012-03-01: 4.76; 2012-03-02: 4.76; 2012-03-05: 4.76; 2012-03-06: 4.76; 2012-03-07: 4.76; 2012-03-08: 4.76; 2012-03-09: 4.76; 2012-03-12: 4.76; 2012-03-13: 4.76; 2012-03-14: 4.76; 2012-03-15: 4.76; 2012-03-16: 4.76; 2012-03-19: 4.76; 2012-03-20: 4.76; 2012-03-21: 4.76; 2012-03-22: 4.76; 2012-03-23: 4.76; 2012-03-26: 4.76; 2012-03-27: 4.76; 2012-03-28: 4.76; 2012-03-29: 4.76; 2012-03-30: 4.76; 2012-04-02: 4.76; 2012-04-03: 4.76; 2012-04-04: 4.38; 2012-04-05: 4.29; 2012-04-06: 4.29; 2012-04-09: 4.29; 2012-04-10: 4.29; 2012-04-11: 4.29; 2012-04-12: 4.29; 2012-04-13: 4.29; 2012-04-16: 4.29; 2012-04-17: 4.29; 2012-04-18: 4.29; 2012-04-19: 4.29; 2012-04-20: 4.29; 2012-04-23: 4.29; 2012-04-24: 4.29; 2012-04-25: 4.29; 2012-04-26: 4.29; 2012-04-27: 4.29; 2012-04-30: 4.29; 2012-05-01: 4.29; 2012-05-02: 4.29; 2012-05-03: 4.29; 2012-05-04: 4.29; 2012-05-07: 4.29; 2012-05-08: 4.29; 2012-05-09: 4.29; 2012-05-10: 4.29; 2012-05-11: 4.29; 2012-05-14: 4.29; 2012-05-15: 4.29; 2012-05-16: 4.29; 2012-05-17: 4.29; 2012-05-18: 4.29; 2012-05-21: 4.29; 2012-05-22: 4.29; 2012-05-23: 4.29; 2012-05-24: 4.29; 2012-05-25: 4.29; 2012-05-29: 4.29; 2012-05-30: 4.29; 2012-05-31: 4.29; 2012-06-01: 4.29; 2012-06-04: 4.29; 2012-06-05: 4.29; 2012-06-06: 4.29; 2012-06-07: 4.29; 2012-06-08: 4.29; 2012-06-11: 4.29; 2012-06-12: 4.29; 2012-06-13: 4.29; 2012-06-14: 4.29; 2012-06-15: 4.29; 2012-06-18: 4.29; 2012-06-19: 4.29; 2012-06-20: 4.29; 2012-06-21: 4.29; 2012-06-22: 4.29; 2012-06-25: 4.29; 2012-06-26: 4.29; 2012-06-27: 4.29; 2012-06-28: 4.29; 2012-06-29: 4.29; 2012-07-02: 4.29; 2012-07-03: 4.29; 2012-07-05: 4.29; 2012-07-06: 4.29; 2012-07-09: 4.29; 2012-07-10: 4.29; 2012-07-11: 4.29; 2012-07-12: 4.29; 2012-07-13: 4.29; 2012-07-16: 4.29; 2012-07-17: 4.29; 2012-07-18: 4.29; 2012-07-19: 4.29; 2012-07-20: 4.29; 2012-07-23: 4.29; 2012-07-24: 4.29; 2012-07-25: 4.29; 2012-07-26: 4.29; 2012-07-27: 4.29; 2012-07-30: 4.29; 2012-07-31: 4.29; 2012-08-01: 4.29; 2012-08-02: 4.29; 2012-08-03: 4.29; 2012-08-06: 4.29; 2012-08-07: 4.29; 2012-08-08: 4.29; 2012-08-09: 4.29; 2012-08-10: 4.29; 2012-08-13: 4.29; 2012-08-14: 4.29; 2012-08-15: 4.29; 2012-08-16: 4.29; 2012-08-17: 4.29; 2012-08-20: 4.29; 2012-08-21: 4.29; 2012-08-22: 4.29; 2012-08-23: 4.29; 2012-08-24: 4.29; 2012-08-27: 4.29; 2012-08-28: 4.29; 2012-08-29: 4.29; 2012-08-30: 4.29; 2012-08-31: 4.29; 2012-09-04: 4.29; 2012-09-05: 4.29; 2012-09-06: 4.29; 2012-09-07: 4.29; 2012-09-10: 4.29; 2012-09-11: 4.29; 2012-09-12: 4.29; 2012-09-13: 4.29; 2012-09-14: 4.29; 2012-09-17: 4.29; 2012-09-18: 4.29; 2012-09-19: 4.29; 2012-09-20: 4.29; 2012-09-21: 4.29; 2012-09-24: 4.29; 2012-09-25: 4.29; 2012-09-26: 4.29; 2012-09-27: 4.29; 2012-09-28: 4.29; 2012-10-01: 4.29; 2012-10-02: 4.29; 2012-10-03: 4.29; 2012-10-04: 4.29; 2012-10-05: 4.29; 2012-10-08: 4.29; 2012-10-09: 4.29; 2012-10-10: 4.29; 2012-10-11: 4.29; 2012-10-12: 2.57
EC2030 | 1345006 | 4000 | ACMEGC | Unit Finishes Building South - Floor 1 | 201.6 | 201.6 | 0% | 2012-01-06 | 2012-10-15 | 209.2 | 896 | At Completion Labor Units | 2012-01-06: 4.76; 2012-01-09: 4.76; 2012-01-10: 4.76; 2012-01-11: 4.76; 2012-01-12: 4.76; 2012-01-13: 4.76; 2012-01-16: 4.76; 2012-01-17: 4.76; 2012-01-18: 4.76; 2012-01-19: 4.76; 2012-01-20: 4.76; 2012-01-23: 4.76; 2012-01-24: 4.76; 2012-01-25: 4.76; 2012-01-26: 4.76; 2012-01-27: 4.76; 2012-01-30: 4.76; 2012-01-31: 4.76; 2012-02-01: 4.76; 2012-02-02: 4.76; 2012-02-03: 4.76; 2012-02-06: 4.76; 2012-02-07: 4.76; 2012-02-08: 4.76; 2012-02-09: 4.76; 2012-02-10: 4.76; 2012-02-13: 4.76; 2012-02-14: 4.76; 2012-02-15: 4.76; 2012-02-16: 4.76; 2012-02-17: 4.76; 2012-02-20: 4.76; 2012-02-21: 4.76; 2012-02-22: 4.76; 2012-02-23: 4.76; 2012-02-24: 4.76; 2012-02-27: 4.76; 2012-02-28: 4.76; 2012-02-29: 4.76; 2012-03-01: 4.76; 2012-03-02: 4.76; 2012-03-05: 4.76; 2012-03-06: 4.76; 2012-03-07: 4.76; 2012-03-08: 4.76; 2012-03-09: 4.76; 2012-03-12: 4.76; 2012-03-13: 4.76; 2012-03-14: 4.76; 2012-03-15: 4.76; 2012-03-16: 4.76; 2012-03-19: 4.76; 2012-03-20: 4.76; 2012-03-21: 4.76; 2012-03-22: 4.76; 2012-03-23: 4.76; 2012-03-26: 4.76; 2012-03-27: 4.76; 2012-03-28: 4.76; 2012-03-29: 4.76; 2012-03-30: 4.76; 2012-04-02: 4.76; 2012-04-03: 4.76; 2012-04-04: 4.76; 2012-04-05: 4.76; 2012-04-06: 4.76; 2012-04-09: 4.76; 2012-04-10: 4.38; 2012-04-11: 4.29; 2012-04-12: 4.29; 2012-04-13: 4.29; 2012-04-16: 4.29; 2012-04-17: 4.29; 2012-04-18: 4.29; 2012-04-19: 4.29; 2012-04-20: 4.29; 2012-04-23: 4.29; 2012-04-24: 4.29; 2012-04-25: 4.29; 2012-04-26: 4.29; 2012-04-27: 4.29; 2012-04-30: 4.29; 2012-05-01: 4.29; 2012-05-02: 4.29; 2012-05-03: 4.29; 2012-05-04: 4.29; 2012-05-07: 4.29; 2012-05-08: 4.29; 2012-05-09: 4.29; 2012-05-10: 4.29; 2012-05-11: 4.29; 2012-05-14: 4.29; 2012-05-15: 4.29; 2012-05-16: 4.29; 2012-05-17: 4.29; 2012-05-18: 4.29; 2012-05-21: 4.29; 2012-05-22: 4.29; 2012-05-23: 4.29; 2012-05-24: 4.29; 2012-05-25: 4.29; 2012-05-29: 4.29; 2012-05-30: 4.29; 2012-05-31: 4.29; 2012-06-01: 4.29; 2012-06-04: 4.29; 2012-06-05: 4.29; 2012-06-06: 4.29; 2012-06-07: 4.29; 2012-06-08: 4.29; 2012-06-11: 4.29; 2012-06-12: 4.29; 2012-06-13: 4.29; 2012-06-14: 4.29; 2012-06-15: 4.29; 2012-06-18: 4.29; 2012-06-19: 4.29; 2012-06-20: 4.29; 2012-06-21: 4.29; 2012-06-22: 4.29; 2012-06-25: 4.29; 2012-06-26: 4.29; 2012-06-27: 4.29; 2012-06-28: 4.29; 2012-06-29: 4.29; 2012-07-02: 4.29; 2012-07-03: 4.29; 2012-07-05: 4.29; 2012-07-06: 4.29; 2012-07-09: 4.29; 2012-07-10: 4.29; 2012-07-11: 4.29; 2012-07-12: 4.29; 2012-07-13: 4.29; 2012-07-16: 4.29; 2012-07-17: 4.29; 2012-07-18: 4.29; 2012-07-19: 4.29; 2012-07-20: 4.29; 2012-07-23: 4.29; 2012-07-24: 4.29; 2012-07-25: 4.29; 2012-07-26: 4.29; 2012-07-27: 4.29; 2012-07-30: 4.29; 2012-07-31: 4.29; 2012-08-01: 4.29; 2012-08-02: 4.29; 2012-08-03: 4.29; 2012-08-06: 4.29; 2012-08-07: 4.29; 2012-08-08: 4.29; 2012-08-09: 4.29; 2012-08-10: 4.29; 2012-08-13: 4.29; 2012-08-14: 4.29; 2012-08-15: 4.29; 2012-08-16: 4.29; 2012-08-17: 4.29; 2012-08-20: 4.29; 2012-08-21: 4.29; 2012-08-22: 4.29; 2012-08-23: 4.29; 2012-08-24: 4.29; 2012-08-27: 4.29; 2012-08-28: 4.29; 2012-08-29: 4.29; 2012-08-30: 4.29; 2012-08-31: 4.29; 2012-09-04: 4.29; 2012-09-05: 4.29; 2012-09-06: 4.29; 2012-09-07: 4.29; 2012-09-10: 4.29; 2012-09-11: 4.29; 2012-09-12: 4.29; 2012-09-13: 4.29; 2012-09-14: 4.29; 2012-09-17: 4.29; 2012-09-18: 4.29; 2012-09-19: 4.29; 2012-09-20: 4.29; 2012-09-21: 4.29; 2012-09-24: 4.29; 2012-09-25: 4.29; 2012-09-26: 4.29; 2012-09-27: 4.29; 2012-09-28: 4.29; 2012-10-01: 4.29; 2012-10-02: 4.29; 2012-10-03: 4.29; 2012-10-04: 4.29; 2012-10-05: 4.29; 2012-10-08: 4.29; 2012-10-09: 4.29; 2012-10-10: 4.29; 2012-10-11: 4.29; 2012-10-12: 4.29; 2012-10-15: 4.29; 2012-10-16: 4.29; 2012-10-17: 4.29; 2012-10-18: 2.57
EC2330 | 1345006 | 5000 | STDPAV | Courtyard Walks and Amenities | 91.2 | 91.2 | 0% | 2012-08-24 | 2012-12-31 | 248.8 | 720 | At Completion Labor Units | 2012-08-24: 3.16; 2012-08-27: 7.89; 2012-08-28: 7.89; 2012-08-29: 7.89; 2012-08-30: 7.89; 2012-08-31: 7.89; 2012-09-04: 7.89; 2012-09-05: 7.89; 2012-09-06: 7.89; 2012-09-07: 7.89; 2012-09-10: 7.89; 2012-09-11: 7.89; 2012-09-12: 7.89; 2012-09-13: 7.89; 2012-09-14: 7.89; 2012-09-17: 7.89; 2012-09-18: 7.89; 2012-09-19: 7.89; 2012-09-20: 7.89; 2012-09-21: 7.89; 2012-09-24: 7.89; 2012-09-25: 7.89; 2012-09-26: 7.89; 2012-09-27: 7.89; 2012-09-28: 7.89; 2012-10-01: 7.89; 2012-10-02: 7.89; 2012-10-03: 7.89; 2012-10-04: 7.89; 2012-10-05: 7.89; 2012-10-08: 7.89; 2012-10-09: 7.89; 2012-10-10: 7.89; 2012-10-11: 7.89; 2012-10-12: 7.89; 2012-10-15: 7.89; 2012-10-16: 7.89; 2012-10-17: 7.89; 2012-10-18: 7.89; 2012-10-19: 7.89; 2012-10-22: 7.89; 2012-10-23: 7.89; 2012-10-24: 7.89; 2012-10-25: 7.89; 2012-10-26: 7.89; 2012-10-29: 7.89; 2012-10-30: 7.89; 2012-10-31: 7.89; 2012-11-01: 7.89; 2012-11-02: 7.89; 2012-11-05: 7.89; 2012-11-06: 7.89; 2012-11-07: 7.89; 2012-11-08: 7.89; 2012-11-09: 7.89; 2012-11-12: 7.89; 2012-11-13: 7.89; 2012-11-14: 7.89; 2012-11-15: 7.89; 2012-11-16: 7.89; 2012-11-19: 7.89; 2012-11-20: 7.89; 2012-11-21: 7.89; 2012-11-23: 7.89; 2012-11-26: 7.89; 2012-11-27: 7.89; 2012-11-28: 7.89; 2012-11-29: 7.89; 2012-11-30: 7.89; 2012-12-03: 7.89; 2012-12-04: 7.89; 2012-12-05: 7.89; 2012-12-06: 7.89; 2012-12-07: 7.89; 2012-12-10: 7.89; 2012-12-11: 7.89; 2012-12-12: 7.89; 2012-12-13: 7.89; 2012-12-14: 7.89; 2012-12-17: 7.89; 2012-12-18: 7.89; 2012-12-19: 7.89; 2012-12-20: 7.89; 2012-12-21: 7.89; 2012-12-24: 7.89; 2012-12-26: 7.89; 2012-12-27: 7.89; 2012-12-28: 7.89; 2012-12-31: 7.89; 2013-01-02: 7.89; 2013-01-03: 7.89; 2013-01-04: 6.32
EC1020 | 1345006 | 6000 |  | Start Garage | 0 | 0 | 0% | 2010-11-01 |  | 390.6 | 0 | At Completion Labor Units
EC1030 | 1345006 | 6000 | STEEL | Shop Drawings, Review and Approval | 72 | 72 | 0% | 2010-11-01 | 2011-02-08 | 390.6 | 614.4 | At Completion Labor Units | 2010-11-01: 8.68; 2010-11-02: 8.68; 2010-11-03: 8.68; 2010-11-04: 8.68; 2010-11-05: 8.68; 2010-11-08: 8.68; 2010-11-09: 8.68; 2010-11-10: 8.68; 2010-11-11: 8.68; 2010-11-12: 8.68; 2010-11-15: 8.68; 2010-11-16: 8.68; 2010-11-17: 8.68; 2010-11-18: 8.68; 2010-11-19: 8.68; 2010-11-22: 8.68; 2010-11-23: 8.68; 2010-11-24: 8.68; 2010-11-26: 8.68; 2010-11-29: 8.68; 2010-11-30: 8.68; 2010-12-01: 8.68; 2010-12-02: 8.68; 2010-12-03: 8.68; 2010-12-06: 8.68; 2010-12-07: 8.68; 2010-12-08: 8.68; 2010-12-09: 8.68; 2010-12-10: 8.68; 2010-12-13: 8.68; 2010-12-14: 8.68; 2010-12-15: 8.68; 2010-12-16: 8.68; 2010-12-17: 8.68; 2010-12-20: 8.68; 2010-12-21: 8.68; 2010-12-22: 8.68; 2010-12-23: 8.68; 2010-12-27: 8.68; 2010-12-28: 8.68; 2010-12-29: 8.68; 2010-12-30: 8.68; 2011-01-03: 8.68; 2011-01-04: 8.68; 2011-01-05: 8.68; 2011-01-06: 8.68; 2011-01-07: 8.68; 2011-01-10: 8.68; 2011-01-11: 8.68; 2011-01-12: 8.68; 2011-01-13: 8.68; 2011-01-14: 8.68; 2011-01-17: 8.68; 2011-01-18: 8.68; 2011-01-19: 8.68; 2011-01-20: 8.68; 2011-01-21: 8.68; 2011-01-24: 8.68; 2011-01-25: 8.68; 2011-01-26: 8.68; 2011-01-27: 8.68; 2011-01-28: 8.68; 2011-01-31: 8.68; 2011-02-01: 8.68; 2011-02-02: 8.68; 2011-02-03: 8.68; 2011-02-04: 8.68; 2011-02-07: 8.68; 2011-02-08: 8.68; 2011-02-09: 6.94; 2011-02-10: 4.34; 2011-02-11: 4.34
EC1180 | 1345006 | 6000 | STEEL | Fab & Delivery | 72 | 72 | 0% | 2011-02-09 | 2011-05-19 | 390.6 | 460.8 | At Completion Labor Units | 2011-02-09: 6.4; 2011-02-10: 6.4; 2011-02-11: 6.4; 2011-02-14: 6.4; 2011-02-15: 6.4; 2011-02-16: 6.4; 2011-02-17: 6.4; 2011-02-18: 6.4; 2011-02-21: 6.4; 2011-02-22: 6.4; 2011-02-23: 6.4; 2011-02-24: 6.4; 2011-02-25: 6.4; 2011-02-28: 6.4; 2011-03-01: 6.4; 2011-03-02: 6.4; 2011-03-03: 6.4; 2011-03-04: 6.4; 2011-03-07: 6.4; 2011-03-08: 6.4; 2011-03-09: 6.4; 2011-03-10: 6.4; 2011-03-11: 6.4; 2011-03-14: 6.4; 2011-03-15: 6.4; 2011-03-16: 6.4; 2011-03-17: 6.4; 2011-03-18: 6.4; 2011-03-21: 6.4; 2011-03-22: 6.4; 2011-03-23: 6.4; 2011-03-24: 6.4; 2011-03-25: 6.4; 2011-03-28: 6.4; 2011-03-29: 6.4; 2011-03-30: 6.4; 2011-03-31: 6.4; 2011-04-01: 6.4; 2011-04-04: 6.4; 2011-04-05: 6.4; 2011-04-06: 6.4; 2011-04-07: 6.4; 2011-04-08: 6.4; 2011-04-11: 6.4; 2011-04-12: 6.4; 2011-04-13: 6.4; 2011-04-14: 6.4; 2011-04-15: 6.4; 2011-04-18: 6.4; 2011-04-19: 6.4; 2011-04-20: 6.4; 2011-04-21: 6.4; 2011-04-22: 6.4; 2011-04-25: 6.4; 2011-04-26: 6.4; 2011-04-27: 6.4; 2011-04-28: 6.4; 2011-04-29: 6.4; 2011-05-02: 6.4; 2011-05-03: 6.4; 2011-05-04: 6.4; 2011-05-05: 6.4; 2011-05-06: 6.4; 2011-05-09: 6.4; 2011-05-10: 6.4; 2011-05-11: 6.4; 2011-05-12: 6.4; 2011-05-13: 6.4; 2011-05-16: 6.4; 2011-05-17: 6.4; 2011-05-18: 6.4; 2011-05-19: 6.4
EC1280 | 1345006 | 6000 | STEEL | Erect Precast Structure | 96 | 96 | 0% | 2011-05-20 | 2011-09-30 | 390.6 | 576 | At Completion Labor Units | 2011-05-20: 6.23; 2011-05-23: 6.23; 2011-05-24: 6.23; 2011-05-25: 6.23; 2011-05-26: 6.23; 2011-05-27: 6.23; 2011-05-31: 6.23; 2011-06-01: 6.23; 2011-06-02: 6.23; 2011-06-03: 6.23; 2011-06-06: 6.23; 2011-06-07: 6.23; 2011-06-08: 6.23; 2011-06-09: 6.23; 2011-06-10: 6.23; 2011-06-13: 6.23; 2011-06-14: 6.23; 2011-06-15: 6.23; 2011-06-16: 6.23; 2011-06-17: 6.23; 2011-06-20: 6.23; 2011-06-21: 6.23; 2011-06-22: 6.23; 2011-06-23: 6.23; 2011-06-24: 6.23; 2011-06-27: 6.23; 2011-06-28: 6.23; 2011-06-29: 6.23; 2011-06-30: 6.23; 2011-07-01: 6.23; 2011-07-05: 6.23; 2011-07-06: 6.23; 2011-07-07: 6.23; 2011-07-08: 6.23; 2011-07-11: 6.23; 2011-07-12: 6.23; 2011-07-13: 6.23; 2011-07-14: 6.23; 2011-07-15: 6.23; 2011-07-18: 6.23; 2011-07-19: 6.23; 2011-07-20: 6.23; 2011-07-21: 6.23; 2011-07-22: 6.23; 2011-07-25: 6.23; 2011-07-26: 6.23; 2011-07-27: 6.23; 2011-07-28: 6.23; 2011-07-29: 6.23; 2011-08-01: 6.23; 2011-08-02: 6.23; 2011-08-03: 6.23; 2011-08-04: 6.23; 2011-08-05: 6.23; 2011-08-08: 6.23; 2011-08-09: 6.23; 2011-08-10: 6.23; 2011-08-11: 6.23; 2011-08-12: 6.23; 2011-08-15: 6.23; 2011-08-16: 6.23; 2011-08-17: 6.23; 2011-08-18: 6.23; 2011-08-19: 6.23; 2011-08-22: 6.23; 2011-08-23: 6.23; 2011-08-24: 6.23; 2011-08-25: 6.23; 2011-08-26: 6.23; 2011-08-29: 6.23; 2011-08-30: 6.23; 2011-08-31: 6.23; 2011-09-01: 6.23; 2011-09-02: 6.23; 2011-09-06: 6.23; 2011-09-07: 6.23; 2011-09-08: 6.23; 2011-09-09: 6.23; 2011-09-12: 6.23; 2011-09-13: 6.23; 2011-09-14: 6.23; 2011-09-15: 6.23; 2011-09-16: 6.23; 2011-09-19: 6.23; 2011-09-20: 6.23; 2011-09-21: 6.23; 2011-09-22: 6.23; 2011-09-23: 6.23; 2011-09-26: 5.61; 2011-09-27: 3.12; 2011-09-28: 3.12; 2011-09-29: 3.12; 2011-09-30: 3.12; 2011-10-03: 3.12; 2011-10-04: 3.12; 2011-10-05: 3.12
EC1590 | 1345006 | 6000 | STEEL | Fire Protection and Lighting | 72 | 72 | 0% | 2011-10-03 | 2012-01-10 | 390.6 | 480 | At Completion Labor Units | 2011-10-03: 6.84; 2011-10-04: 6.84; 2011-10-05: 6.84; 2011-10-06: 6.84; 2011-10-07: 6.84; 2011-10-10: 6.84; 2011-10-11: 6.84; 2011-10-12: 6.84; 2011-10-13: 6.84; 2011-10-14: 6.84; 2011-10-17: 6.84; 2011-10-18: 6.84; 2011-10-19: 6.84; 2011-10-20: 6.84; 2011-10-21: 6.84; 2011-10-24: 6.84; 2011-10-25: 6.84; 2011-10-26: 6.84; 2011-10-27: 6.84; 2011-10-28: 6.84; 2011-10-31: 6.84; 2011-11-01: 6.84; 2011-11-02: 6.84; 2011-11-03: 6.84; 2011-11-04: 6.84; 2011-11-07: 6.84; 2011-11-08: 6.84; 2011-11-09: 6.84; 2011-11-10: 6.84; 2011-11-11: 6.84; 2011-11-14: 6.84; 2011-11-15: 6.84; 2011-11-16: 6.84; 2011-11-17: 6.84; 2011-11-18: 6.84; 2011-11-21: 6.84; 2011-11-22: 6.84; 2011-11-23: 6.84; 2011-11-25: 6.84; 2011-11-28: 6.84; 2011-11-29: 6.84; 2011-11-30: 6.84; 2011-12-01: 6.84; 2011-12-02: 6.84; 2011-12-05: 6.84; 2011-12-06: 6.84; 2011-12-07: 6.84; 2011-12-08: 6.84; 2011-12-09: 6.84; 2011-12-12: 6.84; 2011-12-13: 6.84; 2011-12-14: 6.84; 2011-12-15: 6.84; 2011-12-16: 6.84; 2011-12-19: 6.84; 2011-12-20: 6.84; 2011-12-21: 6.84; 2011-12-22: 6.84; 2011-12-23: 6.84; 2011-12-27: 6.84; 2011-12-28: 6.84; 2011-12-29: 6.84; 2011-12-30: 6.84; 2012-01-03: 6.84; 2012-01-04: 6.84; 2012-01-05: 6.84; 2012-01-06: 6.84; 2012-01-09: 6.84; 2012-01-10: 6.84; 2012-01-11: 4.79; 2012-01-12: 1.71; 2012-01-13: 1.71
EC1680 | 1345006 | 6000 | STEEL | Finishes and Striping | 84 | 84 | 0% | 2011-12-14 | 2012-04-09 | 390.6 | 768 | At Completion Labor Units | 2011-12-14: 9.14; 2011-12-15: 9.14; 2011-12-16: 9.14; 2011-12-19: 9.14; 2011-12-20: 9.14; 2011-12-21: 9.14; 2011-12-22: 9.14; 2011-12-23: 9.14; 2011-12-27: 9.14; 2011-12-28: 9.14; 2011-12-29: 9.14; 2011-12-30: 9.14; 2012-01-03: 9.14; 2012-01-04: 9.14; 2012-01-05: 9.14; 2012-01-06: 9.14; 2012-01-09: 9.14; 2012-01-10: 9.14; 2012-01-11: 9.14; 2012-01-12: 9.14; 2012-01-13: 9.14; 2012-01-16: 9.14; 2012-01-17: 9.14; 2012-01-18: 9.14; 2012-01-19: 9.14; 2012-01-20: 9.14; 2012-01-23: 9.14; 2012-01-24: 9.14; 2012-01-25: 9.14; 2012-01-26: 9.14; 2012-01-27: 9.14; 2012-01-30: 9.14; 2012-01-31: 9.14; 2012-02-01: 9.14; 2012-02-02: 9.14; 2012-02-03: 9.14; 2012-02-06: 9.14; 2012-02-07: 9.14; 2012-02-08: 9.14; 2012-02-09: 9.14; 2012-02-10: 9.14; 2012-02-13: 9.14; 2012-02-14: 9.14; 2012-02-15: 9.14; 2012-02-16: 9.14; 2012-02-17: 9.14; 2012-02-20: 9.14; 2012-02-21: 9.14; 2012-02-22: 9.14; 2012-02-23: 9.14; 2012-02-24: 9.14; 2012-02-27: 9.14; 2012-02-28: 9.14; 2012-02-29: 9.14; 2012-03-01: 9.14; 2012-03-02: 9.14; 2012-03-05: 9.14; 2012-03-06: 9.14; 2012-03-07: 9.14; 2012-03-08: 9.14; 2012-03-09: 9.14; 2012-03-12: 9.14; 2012-03-13: 9.14; 2012-03-14: 9.14; 2012-03-15: 9.14; 2012-03-16: 9.14; 2012-03-19: 9.14; 2012-03-20: 9.14; 2012-03-21: 9.14; 2012-03-22: 9.14; 2012-03-23: 9.14; 2012-03-26: 9.14; 2012-03-27: 9.14; 2012-03-28: 9.14; 2012-03-29: 9.14; 2012-03-30: 9.14; 2012-04-02: 9.14; 2012-04-03: 9.14; 2012-04-04: 9.14; 2012-04-05: 9.14; 2012-04-06: 9.14; 2012-04-09: 9.14; 2012-04-10: 9.14; 2012-04-11: 9.14
EC2190 | 1345006 | 6000 |  | Complete Garage | 0 | 0 | 0% |  | 2012-06-14 | 390.6 | 0 | At Completion Labor Units
EC2060 | 1345006 | 6000 | STEEL | Punch List Garage | 48 | 48 | 0% | 2012-04-10 | 2012-06-14 | 390.6 | 192 | At Completion Labor Units | 2012-04-10: 4; 2012-04-11: 4; 2012-04-12: 4; 2012-04-13: 4; 2012-04-16: 4; 2012-04-17: 4; 2012-04-18: 4; 2012-04-19: 4; 2012-04-20: 4; 2012-04-23: 4; 2012-04-24: 4; 2012-04-25: 4; 2012-04-26: 4; 2012-04-27: 4; 2012-04-30: 4; 2012-05-01: 4; 2012-05-02: 4; 2012-05-03: 4; 2012-05-04: 4; 2012-05-07: 4; 2012-05-08: 4; 2012-05-09: 4; 2012-05-10: 4; 2012-05-11: 4; 2012-05-14: 4; 2012-05-15: 4; 2012-05-16: 4; 2012-05-17: 4; 2012-05-18: 4; 2012-05-21: 4; 2012-05-22: 4; 2012-05-23: 4; 2012-05-24: 4; 2012-05-25: 4; 2012-05-29: 4; 2012-05-30: 4; 2012-05-31: 4; 2012-06-01: 4; 2012-06-04: 4; 2012-06-05: 4; 2012-06-06: 4; 2012-06-07: 4; 2012-06-08: 4; 2012-06-11: 4; 2012-06-12: 4; 2012-06-13: 4; 2012-06-14: 4; 2012-06-15: 4
EC2180 | 1345006 | 6000 |  | Complete Garage 2 | 0 | 0 | 0% |  | 2012-06-14 | 390.6 | 0 | At Completion Labor Units
EC2340 | 1345006 | 7000 | STDPAV | Curbs & Paving | 79.2 | 79.2 | 0% | 2012-08-24 | 2012-12-13 | 260.8 | 633.6 | At Completion Labor Units | 2012-08-24: 3.2; 2012-08-27: 8; 2012-08-28: 8; 2012-08-29: 8; 2012-08-30: 8; 2012-08-31: 8; 2012-09-04: 8; 2012-09-05: 8; 2012-09-06: 8; 2012-09-07: 8; 2012-09-10: 8; 2012-09-11: 8; 2012-09-12: 8; 2012-09-13: 8; 2012-09-14: 8; 2012-09-17: 8; 2012-09-18: 8; 2012-09-19: 8; 2012-09-20: 8; 2012-09-21: 8; 2012-09-24: 8; 2012-09-25: 8; 2012-09-26: 8; 2012-09-27: 8; 2012-09-28: 8; 2012-10-01: 8; 2012-10-02: 8; 2012-10-03: 8; 2012-10-04: 8; 2012-10-05: 8; 2012-10-08: 8; 2012-10-09: 8; 2012-10-10: 8; 2012-10-11: 8; 2012-10-12: 8; 2012-10-15: 8; 2012-10-16: 8; 2012-10-17: 8; 2012-10-18: 8; 2012-10-19: 8; 2012-10-22: 8; 2012-10-23: 8; 2012-10-24: 8; 2012-10-25: 8; 2012-10-26: 8; 2012-10-29: 8; 2012-10-30: 8; 2012-10-31: 8; 2012-11-01: 8; 2012-11-02: 8; 2012-11-05: 8; 2012-11-06: 8; 2012-11-07: 8; 2012-11-08: 8; 2012-11-09: 8; 2012-11-12: 8; 2012-11-13: 8; 2012-11-14: 8; 2012-11-15: 8; 2012-11-16: 8; 2012-11-19: 8; 2012-11-20: 8; 2012-11-21: 8; 2012-11-23: 8; 2012-11-26: 8; 2012-11-27: 8; 2012-11-28: 8; 2012-11-29: 8; 2012-11-30: 8; 2012-12-03: 8; 2012-12-04: 8; 2012-12-05: 8; 2012-12-06: 8; 2012-12-07: 8; 2012-12-10: 8; 2012-12-11: 8; 2012-12-12: 8; 2012-12-13: 8; 2012-12-14: 8; 2012-12-17: 6.4
EC1610 | 1345006 | 7000 | STDPAV | Curbs & Paving | 57.6 | 57.6 | 0% | 2011-10-03 | 2011-12-21 | 517 | 460.8 | At Completion Labor Units | 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 8; 2011-10-28: 8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 8; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 8; 2011-11-29: 8; 2011-11-30: 8; 2011-12-01: 8; 2011-12-02: 8; 2011-12-05: 8; 2011-12-06: 8; 2011-12-07: 8; 2011-12-08: 8; 2011-12-09: 8; 2011-12-12: 8; 2011-12-13: 8; 2011-12-14: 8; 2011-12-15: 8; 2011-12-16: 8; 2011-12-19: 8; 2011-12-20: 8; 2011-12-21: 8; 2011-12-22: 4.8
EC1000 | 1345006 | 7000 | STDPAV | Curbing | 72 | 72 | 0% | 2010-11-01 | 2011-02-08 | 622.2 | 576 | At Completion Labor Units | 2010-11-01: 8; 2010-11-02: 8; 2010-11-03: 8; 2010-11-04: 8; 2010-11-05: 8; 2010-11-08: 8; 2010-11-09: 8; 2010-11-10: 8; 2010-11-11: 8; 2010-11-12: 8; 2010-11-15: 8; 2010-11-16: 8; 2010-11-17: 8; 2010-11-18: 8; 2010-11-19: 8; 2010-11-22: 8; 2010-11-23: 8; 2010-11-24: 8; 2010-11-26: 8; 2010-11-29: 8; 2010-11-30: 8; 2010-12-01: 8; 2010-12-02: 8; 2010-12-03: 8; 2010-12-06: 8; 2010-12-07: 8; 2010-12-08: 8; 2010-12-09: 8; 2010-12-10: 8; 2010-12-13: 8; 2010-12-14: 8; 2010-12-15: 8; 2010-12-16: 8; 2010-12-17: 8; 2010-12-20: 8; 2010-12-21: 8; 2010-12-22: 8; 2010-12-23: 8; 2010-12-27: 8; 2010-12-28: 8; 2010-12-29: 8; 2010-12-30: 8; 2011-01-03: 8; 2011-01-04: 8; 2011-01-05: 8; 2011-01-06: 8; 2011-01-07: 8; 2011-01-10: 8; 2011-01-11: 8; 2011-01-12: 8; 2011-01-13: 8; 2011-01-14: 8; 2011-01-17: 8; 2011-01-18: 8; 2011-01-19: 8; 2011-01-20: 8; 2011-01-21: 8; 2011-01-24: 8; 2011-01-25: 8; 2011-01-26: 8; 2011-01-27: 8; 2011-01-28: 8; 2011-01-31: 8; 2011-02-01: 8; 2011-02-02: 8; 2011-02-03: 8; 2011-02-04: 8; 2011-02-07: 8; 2011-02-08: 8; 2011-02-09: 8; 2011-02-10: 8; 2011-02-11: 8
EC2260 | 1345006 | 7000 | STDPAV | Entry Feature/Sign Wall | 103.2 | 103.2 | 0% | 2012-05-28 | 2012-10-18 | 301.4 | 825.6 | At Completion Labor Units | 2012-05-29: 8; 2012-05-30: 8; 2012-05-31: 8; 2012-06-01: 8; 2012-06-04: 8; 2012-06-05: 8; 2012-06-06: 8; 2012-06-07: 8; 2012-06-08: 8; 2012-06-11: 8; 2012-06-12: 8; 2012-06-13: 8; 2012-06-14: 8; 2012-06-15: 8; 2012-06-18: 8; 2012-06-19: 8; 2012-06-20: 8; 2012-06-21: 8; 2012-06-22: 8; 2012-06-25: 8; 2012-06-26: 8; 2012-06-27: 8; 2012-06-28: 8; 2012-06-29: 8; 2012-07-02: 8; 2012-07-03: 8; 2012-07-05: 8; 2012-07-06: 8; 2012-07-09: 8; 2012-07-10: 8; 2012-07-11: 8; 2012-07-12: 8; 2012-07-13: 8; 2012-07-16: 8; 2012-07-17: 8; 2012-07-18: 8; 2012-07-19: 8; 2012-07-20: 8; 2012-07-23: 8; 2012-07-24: 8; 2012-07-25: 8; 2012-07-26: 8; 2012-07-27: 8; 2012-07-30: 8; 2012-07-31: 8; 2012-08-01: 8; 2012-08-02: 8; 2012-08-03: 8; 2012-08-06: 8; 2012-08-07: 8; 2012-08-08: 8; 2012-08-09: 8; 2012-08-10: 8; 2012-08-13: 8; 2012-08-14: 8; 2012-08-15: 8; 2012-08-16: 8; 2012-08-17: 8; 2012-08-20: 8; 2012-08-21: 8; 2012-08-22: 8; 2012-08-23: 8; 2012-08-24: 8; 2012-08-27: 8; 2012-08-28: 8; 2012-08-29: 8; 2012-08-30: 8; 2012-08-31: 8; 2012-09-04: 8; 2012-09-05: 8; 2012-09-06: 8; 2012-09-07: 8; 2012-09-10: 8; 2012-09-11: 8; 2012-09-12: 8; 2012-09-13: 8; 2012-09-14: 8; 2012-09-17: 8; 2012-09-18: 8; 2012-09-19: 8; 2012-09-20: 8; 2012-09-21: 8; 2012-09-24: 8; 2012-09-25: 8; 2012-09-26: 8; 2012-09-27: 8; 2012-09-28: 8; 2012-10-01: 8; 2012-10-02: 8; 2012-10-03: 8; 2012-10-04: 8; 2012-10-05: 8; 2012-10-08: 8; 2012-10-09: 8; 2012-10-10: 8; 2012-10-11: 8; 2012-10-12: 8; 2012-10-15: 8; 2012-10-16: 8; 2012-10-17: 8; 2012-10-18: 8; 2012-10-19: 8; 2012-10-22: 8; 2012-10-23: 1.6
EC2250 | 1345006 | 7000 | STDPAV | Fountain/Water Feature | 115.2 | 115.2 | 0% | 2012-05-22 | 2012-10-30 | 293.4 | 921.6 | At Completion Labor Units | 2012-05-22: 8; 2012-05-23: 8; 2012-05-24: 8; 2012-05-25: 8; 2012-05-29: 8; 2012-05-30: 8; 2012-05-31: 8; 2012-06-01: 8; 2012-06-04: 8; 2012-06-05: 8; 2012-06-06: 8; 2012-06-07: 8; 2012-06-08: 8; 2012-06-11: 8; 2012-06-12: 8; 2012-06-13: 8; 2012-06-14: 8; 2012-06-15: 8; 2012-06-18: 8; 2012-06-19: 8; 2012-06-20: 8; 2012-06-21: 8; 2012-06-22: 8; 2012-06-25: 8; 2012-06-26: 8; 2012-06-27: 8; 2012-06-28: 8; 2012-06-29: 8; 2012-07-02: 8; 2012-07-03: 8; 2012-07-05: 8; 2012-07-06: 8; 2012-07-09: 8; 2012-07-10: 8; 2012-07-11: 8; 2012-07-12: 8; 2012-07-13: 8; 2012-07-16: 8; 2012-07-17: 8; 2012-07-18: 8; 2012-07-19: 8; 2012-07-20: 8; 2012-07-23: 8; 2012-07-24: 8; 2012-07-25: 8; 2012-07-26: 8; 2012-07-27: 8; 2012-07-30: 8; 2012-07-31: 8; 2012-08-01: 8; 2012-08-02: 8; 2012-08-03: 8; 2012-08-06: 8; 2012-08-07: 8; 2012-08-08: 8; 2012-08-09: 8; 2012-08-10: 8; 2012-08-13: 8; 2012-08-14: 8; 2012-08-15: 8; 2012-08-16: 8; 2012-08-17: 8; 2012-08-20: 8; 2012-08-21: 8; 2012-08-22: 8; 2012-08-23: 8; 2012-08-24: 8; 2012-08-27: 8; 2012-08-28: 8; 2012-08-29: 8; 2012-08-30: 8; 2012-08-31: 8; 2012-09-04: 8; 2012-09-05: 8; 2012-09-06: 8; 2012-09-07: 8; 2012-09-10: 8; 2012-09-11: 8; 2012-09-12: 8; 2012-09-13: 8; 2012-09-14: 8; 2012-09-17: 8; 2012-09-18: 8; 2012-09-19: 8; 2012-09-20: 8; 2012-09-21: 8; 2012-09-24: 8; 2012-09-25: 8; 2012-09-26: 8; 2012-09-27: 8; 2012-09-28: 8; 2012-10-01: 8; 2012-10-02: 8; 2012-10-03: 8; 2012-10-04: 8; 2012-10-05: 8; 2012-10-08: 8; 2012-10-09: 8; 2012-10-10: 8; 2012-10-11: 8; 2012-10-12: 8; 2012-10-15: 8; 2012-10-16: 8; 2012-10-17: 8; 2012-10-18: 8; 2012-10-19: 8; 2012-10-22: 8; 2012-10-23: 8; 2012-10-24: 8; 2012-10-25: 8; 2012-10-26: 8; 2012-10-29: 8; 2012-10-30: 8; 2012-10-31: 8; 2012-11-01: 8; 2012-11-02: 1.6
EC1270 | 1345006 | 7000 | STDPAV | Finish Paving, Striping and Signs | 48 | 48 | 0% | 2011-05-20 | 2011-07-27 | 622.2 | 384 | At Completion Labor Units | 2011-05-20: 4.8; 2011-05-23: 8; 2011-05-24: 8; 2011-05-25: 8; 2011-05-26: 8; 2011-05-27: 8; 2011-05-31: 8; 2011-06-01: 8; 2011-06-02: 8; 2011-06-03: 8; 2011-06-06: 8; 2011-06-07: 8; 2011-06-08: 8; 2011-06-09: 8; 2011-06-10: 8; 2011-06-13: 8; 2011-06-14: 8; 2011-06-15: 8; 2011-06-16: 8; 2011-06-17: 8; 2011-06-20: 8; 2011-06-21: 8; 2011-06-22: 8; 2011-06-23: 8; 2011-06-24: 8; 2011-06-27: 8; 2011-06-28: 8; 2011-06-29: 8; 2011-06-30: 8; 2011-07-01: 8; 2011-07-05: 8; 2011-07-06: 8; 2011-07-07: 8; 2011-07-08: 8; 2011-07-11: 8; 2011-07-12: 8; 2011-07-13: 8; 2011-07-14: 8; 2011-07-15: 8; 2011-07-18: 8; 2011-07-19: 8; 2011-07-20: 8; 2011-07-21: 8; 2011-07-22: 8; 2011-07-25: 8; 2011-07-26: 8; 2011-07-27: 8; 2011-07-28: 8; 2011-07-29: 3.2
EC1130 | 1345006 | 7000 | STDPAV | Walkways | 67.2 | 67.2 | 0% | 2010-11-15 | 2011-02-16 | 622.2 | 537.6 | At Completion Labor Units | 2010-11-15: 8; 2010-11-16: 8; 2010-11-17: 8; 2010-11-18: 8; 2010-11-19: 8; 2010-11-22: 8; 2010-11-23: 8; 2010-11-24: 8; 2010-11-26: 8; 2010-11-29: 8; 2010-11-30: 8; 2010-12-01: 8; 2010-12-02: 8; 2010-12-03: 8; 2010-12-06: 8; 2010-12-07: 8; 2010-12-08: 8; 2010-12-09: 8; 2010-12-10: 8; 2010-12-13: 8; 2010-12-14: 8; 2010-12-15: 8; 2010-12-16: 8; 2010-12-17: 8; 2010-12-20: 8; 2010-12-21: 8; 2010-12-22: 8; 2010-12-23: 8; 2010-12-27: 8; 2010-12-28: 8; 2010-12-29: 8; 2010-12-30: 8; 2011-01-03: 8; 2011-01-04: 8; 2011-01-05: 8; 2011-01-06: 8; 2011-01-07: 8; 2011-01-10: 8; 2011-01-11: 8; 2011-01-12: 8; 2011-01-13: 8; 2011-01-14: 8; 2011-01-17: 8; 2011-01-18: 8; 2011-01-19: 8; 2011-01-20: 8; 2011-01-21: 8; 2011-01-24: 8; 2011-01-25: 8; 2011-01-26: 8; 2011-01-27: 8; 2011-01-28: 8; 2011-01-31: 8; 2011-02-01: 8; 2011-02-02: 8; 2011-02-03: 8; 2011-02-04: 8; 2011-02-07: 8; 2011-02-08: 8; 2011-02-09: 8; 2011-02-10: 8; 2011-02-11: 8; 2011-02-14: 8; 2011-02-15: 8; 2011-02-16: 8; 2011-02-17: 8; 2011-02-18: 8; 2011-02-21: 1.6
EC1200 | 1345006 | 7000 | STDPAV | Roadway Pavers | 67.2 | 67.2 | 0% | 2011-02-16 | 2011-05-20 | 622.2 | 422.4 | At Completion Labor Units | 2011-02-16: 5.03; 2011-02-17: 6.29; 2011-02-18: 6.29; 2011-02-21: 6.29; 2011-02-22: 6.29; 2011-02-23: 6.29; 2011-02-24: 6.29; 2011-02-25: 6.29; 2011-02-28: 6.29; 2011-03-01: 6.29; 2011-03-02: 6.29; 2011-03-03: 6.29; 2011-03-04: 6.29; 2011-03-07: 6.29; 2011-03-08: 6.29; 2011-03-09: 6.29; 2011-03-10: 6.29; 2011-03-11: 6.29; 2011-03-14: 6.29; 2011-03-15: 6.29; 2011-03-16: 6.29; 2011-03-17: 6.29; 2011-03-18: 6.29; 2011-03-21: 6.29; 2011-03-22: 6.29; 2011-03-23: 6.29; 2011-03-24: 6.29; 2011-03-25: 6.29; 2011-03-28: 6.29; 2011-03-29: 6.29; 2011-03-30: 6.29; 2011-03-31: 6.29; 2011-04-01: 6.29; 2011-04-04: 6.29; 2011-04-05: 6.29; 2011-04-06: 6.29; 2011-04-07: 6.29; 2011-04-08: 6.29; 2011-04-11: 6.29; 2011-04-12: 6.29; 2011-04-13: 6.29; 2011-04-14: 6.29; 2011-04-15: 6.29; 2011-04-18: 6.29; 2011-04-19: 6.29; 2011-04-20: 6.29; 2011-04-21: 6.29; 2011-04-22: 6.29; 2011-04-25: 6.29; 2011-04-26: 6.29; 2011-04-27: 6.29; 2011-04-28: 6.29; 2011-04-29: 6.29; 2011-05-02: 6.29; 2011-05-03: 6.29; 2011-05-04: 6.29; 2011-05-05: 6.29; 2011-05-06: 6.29; 2011-05-09: 6.29; 2011-05-10: 6.29; 2011-05-11: 6.29; 2011-05-12: 6.29; 2011-05-13: 6.29; 2011-05-16: 6.29; 2011-05-17: 6.29; 2011-05-18: 6.29; 2011-05-19: 6.29; 2011-05-20: 2.51
EC1100 | 1345006 | 7000 | STDPAV | Storm Drainage Site Work | 72 | 72 | 0% | 2010-11-02 | 2011-02-09 | 36 | 576 | At Completion Labor Units | 2010-11-02: 8; 2010-11-03: 8; 2010-11-04: 8; 2010-11-05: 8; 2010-11-08: 8; 2010-11-09: 8; 2010-11-10: 8; 2010-11-11: 8; 2010-11-12: 8; 2010-11-15: 8; 2010-11-16: 8; 2010-11-17: 8; 2010-11-18: 8; 2010-11-19: 8; 2010-11-22: 8; 2010-11-23: 8; 2010-11-24: 8; 2010-11-26: 8; 2010-11-29: 8; 2010-11-30: 8; 2010-12-01: 8; 2010-12-02: 8; 2010-12-03: 8; 2010-12-06: 8; 2010-12-07: 8; 2010-12-08: 8; 2010-12-09: 8; 2010-12-10: 8; 2010-12-13: 8; 2010-12-14: 8; 2010-12-15: 8; 2010-12-16: 8; 2010-12-17: 8; 2010-12-20: 8; 2010-12-21: 8; 2010-12-22: 8; 2010-12-23: 8; 2010-12-27: 8; 2010-12-28: 8; 2010-12-29: 8; 2010-12-30: 8; 2011-01-03: 8; 2011-01-04: 8; 2011-01-05: 8; 2011-01-06: 8; 2011-01-07: 8; 2011-01-10: 8; 2011-01-11: 8; 2011-01-12: 8; 2011-01-13: 8; 2011-01-14: 8; 2011-01-17: 8; 2011-01-18: 8; 2011-01-19: 8; 2011-01-20: 8; 2011-01-21: 8; 2011-01-24: 8; 2011-01-25: 8; 2011-01-26: 8; 2011-01-27: 8; 2011-01-28: 8; 2011-01-31: 8; 2011-02-01: 8; 2011-02-02: 8; 2011-02-03: 8; 2011-02-04: 8; 2011-02-07: 8; 2011-02-08: 8; 2011-02-09: 8; 2011-02-10: 8; 2011-02-11: 8; 2011-02-14: 8
EC1110 | 1345006 | 7000 | ELECTR | Site Electrical Work & Temp Power | 12 | 12 | 0% | 2010-11-02 | 2010-11-17 | 36 | 96 | At Completion Labor Units | 2010-11-02: 8; 2010-11-03: 8; 2010-11-04: 8; 2010-11-05: 8; 2010-11-08: 8; 2010-11-09: 8; 2010-11-10: 8; 2010-11-11: 8; 2010-11-12: 8; 2010-11-15: 8; 2010-11-16: 8; 2010-11-17: 8
EC1440 | 1345006 | 7000 | ELECTR | Electric to Building 2 Power Vault | 91.2 | 91.2 | 0% | 2011-08-19 | 2011-12-26 | 407.6 | 729.6 | At Completion Labor Units | 2011-08-19: 1.6; 2011-08-22: 8; 2011-08-23: 8; 2011-08-24: 8; 2011-08-25: 8; 2011-08-26: 8; 2011-08-29: 8; 2011-08-30: 8; 2011-08-31: 8; 2011-09-01: 8; 2011-09-02: 8; 2011-09-06: 8; 2011-09-07: 8; 2011-09-08: 8; 2011-09-09: 8; 2011-09-12: 8; 2011-09-13: 8; 2011-09-14: 8; 2011-09-15: 8; 2011-09-16: 8; 2011-09-19: 8; 2011-09-20: 8; 2011-09-21: 8; 2011-09-22: 8; 2011-09-23: 8; 2011-09-26: 8; 2011-09-27: 8; 2011-09-28: 8; 2011-09-29: 8; 2011-09-30: 8; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 8; 2011-10-28: 8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 8; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 8; 2011-11-29: 8; 2011-11-30: 8; 2011-12-01: 8; 2011-12-02: 8; 2011-12-05: 8; 2011-12-06: 8; 2011-12-07: 8; 2011-12-08: 8; 2011-12-09: 8; 2011-12-12: 8; 2011-12-13: 8; 2011-12-14: 8; 2011-12-15: 8; 2011-12-16: 8; 2011-12-19: 8; 2011-12-20: 8; 2011-12-21: 8; 2011-12-22: 8; 2011-12-23: 8; 2011-12-27: 8; 2011-12-28: 8; 2011-12-29: 8
EC1040 | 1345006 | 7000 | ELECTR | Electric to Building 4 Power Vault | 72 | 72 | 0% | 2010-11-01 | 2011-02-08 | 742.6 | 576 | At Completion Labor Units | 2010-11-01: 8; 2010-11-02: 8; 2010-11-03: 8; 2010-11-04: 8; 2010-11-05: 8; 2010-11-08: 8; 2010-11-09: 8; 2010-11-10: 8; 2010-11-11: 8; 2010-11-12: 8; 2010-11-15: 8; 2010-11-16: 8; 2010-11-17: 8; 2010-11-18: 8; 2010-11-19: 8; 2010-11-22: 8; 2010-11-23: 8; 2010-11-24: 8; 2010-11-26: 8; 2010-11-29: 8; 2010-11-30: 8; 2010-12-01: 8; 2010-12-02: 8; 2010-12-03: 8; 2010-12-06: 8; 2010-12-07: 8; 2010-12-08: 8; 2010-12-09: 8; 2010-12-10: 8; 2010-12-13: 8; 2010-12-14: 8; 2010-12-15: 8; 2010-12-16: 8; 2010-12-17: 8; 2010-12-20: 8; 2010-12-21: 8; 2010-12-22: 8; 2010-12-23: 8; 2010-12-27: 8; 2010-12-28: 8; 2010-12-29: 8; 2010-12-30: 8; 2011-01-03: 8; 2011-01-04: 8; 2011-01-05: 8; 2011-01-06: 8; 2011-01-07: 8; 2011-01-10: 8; 2011-01-11: 8; 2011-01-12: 8; 2011-01-13: 8; 2011-01-14: 8; 2011-01-17: 8; 2011-01-18: 8; 2011-01-19: 8; 2011-01-20: 8; 2011-01-21: 8; 2011-01-24: 8; 2011-01-25: 8; 2011-01-26: 8; 2011-01-27: 8; 2011-01-28: 8; 2011-01-31: 8; 2011-02-01: 8; 2011-02-02: 8; 2011-02-03: 8; 2011-02-04: 8; 2011-02-07: 8; 2011-02-08: 8; 2011-02-09: 8; 2011-02-10: 8; 2011-02-11: 8
EC1750 | 1345006 | 7000 | ELECTR | Electric to Building 1 Power Vault | 69.6 | 69.6 | 0% | 2011-09-30 | 2012-01-05 | 366 | 556.8 | At Completion Labor Units | 2011-09-30: 4.8; 2011-10-03: 8; 2011-10-04: 8; 2011-10-05: 8; 2011-10-06: 8; 2011-10-07: 8; 2011-10-10: 8; 2011-10-11: 8; 2011-10-12: 8; 2011-10-13: 8; 2011-10-14: 8; 2011-10-17: 8; 2011-10-18: 8; 2011-10-19: 8; 2011-10-20: 8; 2011-10-21: 8; 2011-10-24: 8; 2011-10-25: 8; 2011-10-26: 8; 2011-10-27: 8; 2011-10-28: 8; 2011-10-31: 8; 2011-11-01: 8; 2011-11-02: 8; 2011-11-03: 8; 2011-11-04: 8; 2011-11-07: 8; 2011-11-08: 8; 2011-11-09: 8; 2011-11-10: 8; 2011-11-11: 8; 2011-11-14: 8; 2011-11-15: 8; 2011-11-16: 8; 2011-11-17: 8; 2011-11-18: 8; 2011-11-21: 8; 2011-11-22: 8; 2011-11-23: 8; 2011-11-25: 8; 2011-11-28: 8; 2011-11-29: 8; 2011-11-30: 8; 2011-12-01: 8; 2011-12-02: 8; 2011-12-05: 8; 2011-12-06: 8; 2011-12-07: 8; 2011-12-08: 8; 2011-12-09: 8; 2011-12-12: 8; 2011-12-13: 8; 2011-12-14: 8; 2011-12-15: 8; 2011-12-16: 8; 2011-12-19: 8; 2011-12-20: 8; 2011-12-21: 8; 2011-12-22: 8; 2011-12-23: 8; 2011-12-27: 8; 2011-12-28: 8; 2011-12-29: 8; 2011-12-30: 8; 2012-01-03: 8; 2012-01-04: 8; 2012-01-05: 8; 2012-01-06: 8; 2012-01-09: 8; 2012-01-10: 8
EC1050 | 1345006 | 7000 | ELECTR | Electric to Building 3 Power Vault | 24 | 24 | 0% | 2010-11-01 | 2010-12-02 | 790.6 | 192 | At Completion Labor Units | 2010-11-01: 8; 2010-11-02: 8; 2010-11-03: 8; 2010-11-04: 8; 2010-11-05: 8; 2010-11-08: 8; 2010-11-09: 8; 2010-11-10: 8; 2010-11-11: 8; 2010-11-12: 8; 2010-11-15: 8; 2010-11-16: 8; 2010-11-17: 8; 2010-11-18: 8; 2010-11-19: 8; 2010-11-22: 8; 2010-11-23: 8; 2010-11-24: 8; 2010-11-26: 8; 2010-11-29: 8; 2010-11-30: 8; 2010-12-01: 8; 2010-12-02: 8; 2010-12-03: 8
EC2290 | 1345006 | 7000 | STDPAV | Curbs & Paving | 72 | 72 | 0% | 2012-05-28 | 2012-09-04 | 317.6 | 576 | At Completion Labor Units | 2012-05-29: 8; 2012-05-30: 8; 2012-05-31: 8; 2012-06-01: 8; 2012-06-04: 8; 2012-06-05: 8; 2012-06-06: 8; 2012-06-07: 8; 2012-06-08: 8; 2012-06-11: 8; 2012-06-12: 8; 2012-06-13: 8; 2012-06-14: 8; 2012-06-15: 8; 2012-06-18: 8; 2012-06-19: 8; 2012-06-20: 8; 2012-06-21: 8; 2012-06-22: 8; 2012-06-25: 8; 2012-06-26: 8; 2012-06-27: 8; 2012-06-28: 8; 2012-06-29: 8; 2012-07-02: 8; 2012-07-03: 8; 2012-07-05: 8; 2012-07-06: 8; 2012-07-09: 8; 2012-07-10: 8; 2012-07-11: 8; 2012-07-12: 8; 2012-07-13: 8; 2012-07-16: 8; 2012-07-17: 8; 2012-07-18: 8; 2012-07-19: 8; 2012-07-20: 8; 2012-07-23: 8; 2012-07-24: 8; 2012-07-25: 8; 2012-07-26: 8; 2012-07-27: 8; 2012-07-30: 8; 2012-07-31: 8; 2012-08-01: 8; 2012-08-02: 8; 2012-08-03: 8; 2012-08-06: 8; 2012-08-07: 8; 2012-08-08: 8; 2012-08-09: 8; 2012-08-10: 8; 2012-08-13: 8; 2012-08-14: 8; 2012-08-15: 8; 2012-08-16: 8; 2012-08-17: 8; 2012-08-20: 8; 2012-08-21: 8; 2012-08-22: 8; 2012-08-23: 8; 2012-08-24: 8; 2012-08-27: 8; 2012-08-28: 8; 2012-08-29: 8; 2012-08-30: 8; 2012-08-31: 8; 2012-09-04: 8; 2012-09-05: 8; 2012-09-06: 8; 2012-09-07: 8
EC1600 | 1345006 | 8000 | BRINK | Site Cleanup | 48 | 48 | 0% | 2011-05-18 | 2011-07-22 | 624.6 | 384 | At Completion Labor Units | 2011-05-18: 8; 2011-05-19: 8; 2011-05-20: 8; 2011-05-23: 8; 2011-05-24: 8; 2011-05-25: 8; 2011-05-26: 8; 2011-05-27: 8; 2011-05-31: 8; 2011-06-01: 8; 2011-06-02: 8; 2011-06-03: 8; 2011-06-06: 8; 2011-06-07: 8; 2011-06-08: 8; 2011-06-09: 8; 2011-06-10: 8; 2011-06-13: 8; 2011-06-14: 8; 2011-06-15: 8; 2011-06-16: 8; 2011-06-17: 8; 2011-06-20: 8; 2011-06-21: 8; 2011-06-22: 8; 2011-06-23: 8; 2011-06-24: 8; 2011-06-27: 8; 2011-06-28: 8; 2011-06-29: 8; 2011-06-30: 8; 2011-07-01: 8; 2011-07-05: 8; 2011-07-06: 8; 2011-07-07: 8; 2011-07-08: 8; 2011-07-11: 8; 2011-07-12: 8; 2011-07-13: 8; 2011-07-14: 8; 2011-07-15: 8; 2011-07-18: 8; 2011-07-19: 8; 2011-07-20: 8; 2011-07-21: 8; 2011-07-22: 8; 2011-07-25: 8; 2011-07-26: 8
EC2360 | 1345006 | 8000 | BRINK | Landscape & Irrigation | 288 | 288 | 0% | 2012-11-06 | 2013-12-13 | 0 | 960 | At Completion Labor Units | 2012-11-06: 2.16; 2012-11-07: 5.41; 2012-11-08: 5.41; 2012-11-09: 5.41; 2012-11-12: 5.41; 2012-11-13: 5.41; 2012-11-14: 5.41; 2012-11-15: 5.41; 2012-11-16: 5.41; 2012-11-19: 5.41; 2012-11-20: 5.41; 2012-11-21: 5.41; 2012-11-23: 5.41; 2012-11-26: 5.41; 2012-11-27: 5.41; 2012-11-28: 5.41; 2012-11-29: 5.41; 2012-11-30: 5.41; 2012-12-03: 5.41; 2012-12-04: 5.41; 2012-12-05: 5.41; 2012-12-06: 5.41; 2012-12-07: 5.41; 2012-12-10: 5.41; 2012-12-11: 5.41; 2012-12-12: 5.41; 2012-12-13: 5.41; 2012-12-14: 5.41; 2012-12-17: 5.41; 2012-12-18: 5.41; 2012-12-19: 5.41; 2012-12-20: 5.41; 2012-12-21: 5.41; 2012-12-24: 5.41; 2012-12-26: 5.41; 2012-12-27: 5.41; 2012-12-28: 5.41; 2012-12-31: 5.41; 2013-01-02: 5.41; 2013-01-03: 5.41; 2013-01-04: 5.41; 2013-01-07: 5.41; 2013-01-08: 5.41; 2013-01-09: 5.41; 2013-01-10: 5.41; 2013-01-11: 5.41; 2013-01-14: 5.41; 2013-01-15: 5.41; 2013-01-16: 5.41; 2013-01-17: 5.41; 2013-01-18: 5.41; 2013-01-21: 5.41; 2013-01-22: 5.41; 2013-01-23: 5.41; 2013-01-24: 5.41; 2013-01-25: 5.41; 2013-01-28: 5.41; 2013-01-29: 5.41; 2013-01-30: 5.41; 2013-01-31: 5.41; 2013-02-01: 5.41; 2013-02-04: 5.41; 2013-02-05: 5.41; 2013-02-06: 5.41; 2013-02-07: 5.41; 2013-02-08: 5.41; 2013-02-11: 5.41; 2013-02-12: 4.86; 2013-02-13: 2.7; 2013-02-14: 2.7; 2013-02-15: 2.7; 2013-02-18: 2.7; 2013-02-19: 2.7; 2013-02-20: 2.7; 2013-02-21: 2.7; 2013-02-22: 2.7; 2013-02-25: 2.7; 2013-02-26: 2.7; 2013-02-27: 2.7; 2013-02-28: 2.7; 2013-03-01: 2.7; 2013-03-04: 2.7; 2013-03-05: 2.7; 2013-03-06: 2.7; 2013-03-07: 2.7; 2013-03-08: 2.7; 2013-03-11: 2.7; 2013-03-12: 2.7; 2013-03-13: 2.7; 2013-03-14: 2.7; 2013-03-15: 2.7; 2013-03-18: 2.7; 2013-03-19: 2.7; 2013-03-20: 2.7; 2013-03-21: 2.7; 2013-03-22: 2.7; 2013-03-25: 2.7; 2013-03-26: 2.7; 2013-03-27: 2.7; 2013-03-28: 2.7; 2013-03-29: 2.7; 2013-04-01: 2.7; 2013-04-02: 2.7; 2013-04-03: 2.7; 2013-04-04: 2.7; 2013-04-05: 2.7; 2013-04-08: 2.7; 2013-04-09: 2.7; 2013-04-10: 2.7; 2013-04-11: 2.7; 2013-04-12: 2.7; 2013-04-15: 2.7; 2013-04-16: 2.7; 2013-04-17: 2.7; 2013-04-18: 2.7; 2013-04-19: 2.7; 2013-04-22: 2.7; 2013-04-23: 2.7; 2013-04-24: 2.7; 2013-04-25: 2.7; 2013-04-26: 2.7; 2013-04-29: 2.7; 2013-04-30: 2.7; 2013-05-01: 2.7; 2013-05-02: 2.7; 2013-05-03: 2.7; 2013-05-06: 2.7; 2013-05-07: 2.7; 2013-05-08: 2.7; 2013-05-09: 2.7; 2013-05-10: 2.7; 2013-05-13: 2.7; 2013-05-14: 2.7; 2013-05-15: 2.7; 2013-05-16: 2.7; 2013-05-17: 2.7; 2013-05-20: 2.7; 2013-05-21: 2.7; 2013-05-22: 2.7; 2013-05-23: 2.7; 2013-05-24: 2.7; 2013-05-28: 2.7; 2013-05-29: 2.7; 2013-05-30: 2.7; 2013-05-31: 2.7; 2013-06-03: 2.7; 2013-06-04: 2.7; 2013-06-05: 2.7; 2013-06-06: 2.7; 2013-06-07: 2.7; 2013-06-10: 2.7; 2013-06-11: 2.7; 2013-06-12: 2.7; 2013-06-13: 2.7; 2013-06-14: 2.7; 2013-06-17: 2.7; 2013-06-18: 2.7; 2013-06-19: 2.7; 2013-06-20: 2.7; 2013-06-21: 2.7; 2013-06-24: 2.7; 2013-06-25: 2.7; 2013-06-26: 2.7; 2013-06-27: 2.7; 2013-06-28: 2.7; 2013-07-01: 2.7; 2013-07-02: 2.7; 2013-07-03: 2.7; 2013-07-05: 2.7; 2013-07-08: 2.7; 2013-07-09: 2.7; 2013-07-10: 2.7; 2013-07-11: 2.7; 2013-07-12: 2.7; 2013-07-15: 2.7; 2013-07-16: 2.7; 2013-07-17: 2.7; 2013-07-18: 2.7; 2013-07-19: 2.7; 2013-07-22: 2.7; 2013-07-23: 2.7; 2013-07-24: 2.7; 2013-07-25: 2.7; 2013-07-26: 2.7; 2013-07-29: 2.7; 2013-07-30: 2.7; 2013-07-31: 2.7; 2013-08-01: 2.7; 2013-08-02: 2.7; 2013-08-05: 2.7; 2013-08-06: 2.7; 2013-08-07: 2.7; 2013-08-08: 2.7; 2013-08-09: 2.7; 2013-08-12: 2.7; 2013-08-13: 2.7; 2013-08-14: 2.7; 2013-08-15: 2.7; 2013-08-16: 2.7; 2013-08-19: 2.7; 2013-08-20: 2.7; 2013-08-21: 2.7; 2013-08-22: 2.7; 2013-08-23: 2.7; 2013-08-26: 2.7; 2013-08-27: 2.7; 2013-08-28: 2.7; 2013-08-29: 2.7; 2013-08-30: 2.7; 2013-09-03: 2.7; 2013-09-04: 2.7; 2013-09-05: 2.7; 2013-09-06: 2.7; 2013-09-09: 2.7; 2013-09-10: 2.7; 2013-09-11: 2.7; 2013-09-12: 2.7; 2013-09-13: 2.7; 2013-09-16: 2.7; 2013-09-17: 2.7; 2013-09-18: 2.7; 2013-09-19: 2.7; 2013-09-20: 2.7; 2013-09-23: 2.7; 2013-09-24: 2.7; 2013-09-25: 2.7; 2013-09-26: 2.7; 2013-09-27: 2.7; 2013-09-30: 2.7; 2013-10-01: 2.7; 2013-10-02: 2.7; 2013-10-03: 2.7; 2013-10-04: 2.7; 2013-10-07: 2.7; 2013-10-08: 2.7; 2013-10-09: 2.7; 2013-10-10: 2.7; 2013-10-11: 2.7; 2013-10-14: 2.7; 2013-10-15: 2.7; 2013-10-16: 2.7; 2013-10-17: 2.7; 2013-10-18: 2.7; 2013-10-21: 2.7; 2013-10-22: 2.7; 2013-10-23: 2.7; 2013-10-24: 2.7; 2013-10-25: 2.7; 2013-10-28: 2.7; 2013-10-29: 2.7; 2013-10-30: 2.7; 2013-10-31: 2.7; 2013-11-01: 2.7; 2013-11-04: 2.7; 2013-11-05: 2.7; 2013-11-06: 2.7; 2013-11-07: 2.7; 2013-11-08: 2.7; 2013-11-11: 2.7; 2013-11-12: 2.7; 2013-11-13: 2.7; 2013-11-14: 2.7; 2013-11-15: 2.7; 2013-11-18: 2.7; 2013-11-19: 2.7; 2013-11-20: 2.7; 2013-11-21: 2.7; 2013-11-22: 2.7; 2013-11-25: 2.7; 2013-11-26: 2.7; 2013-11-27: 2.7; 2013-11-29: 2.7; 2013-12-02: 2.7; 2013-12-03: 2.7; 2013-12-04: 2.7; 2013-12-05: 2.7; 2013-12-06: 2.7; 2013-12-09: 2.7; 2013-12-10: 2.7; 2013-12-11: 2.7; 2013-12-12: 2.7; 2013-12-13: 2.7